SELLEROS

# Codex Implementation Task Master Plan

A dependency-aware plan for building and understanding the SE-331 capstone in controlled steps

Project: SellerOS — AI-Powered Business Intelligence and Decision Support for Social-Commerce Sellers

Course: SE-331 Software Engineering Capstone Project

Students: Monira Islam (232-35-017) and Rukaiya Akther Trisha (232-35-292)

Instructor: Farhan Tanvir, Lecturer, Department of Software Engineering, DIU

Prepared: 5 October 2026

Planning only. No implementation task is started by this document.

The next implementation prompt is intentionally withheld until the plan is reviewed and approved.

# 1. How to Use This Plan

This document converts the approved SellerOS proposal and execution roadmap into small, ordered Codex tasks. Give Codex one task ID at a time. Read the change, run its checks, understand the design, and commit it before starting a dependent task. A task is complete only when its Definition of Done and evidence are satisfied.

The proposal lead follows the work split in the proposal: Monira Islam leads backend, database, APIs, business rules, and AI/analytics implementation; Rukaiya Akther Trisha leads React workflows, API-connected interfaces, dashboards, visualization, and test design; shared planning, validation, integration, and review tasks are marked Joint. A proposal lead is a planned role assignment, not evidence that the person completed the task. At the student’s instruction, Monira Islam is the hands-on operator for every task, including frontend and UX work. Do not assume that Rukaiya contributed or reviewed; record only work that actually happened.

The phase batches are for organization only. They do not authorize combining separate tasks into a large Codex request. UI work may proceed in parallel with an API only after their data and endpoint contract is agreed; because one person will execute all work, parallel tracks are shown as optional planning opportunities, not a requirement.

## Operating loop

Understand requirement → define target → give Codex one task → inspect diff → run commands/tests → fix → explain in your own words → commit → update tracker → continue only when dependencies pass.

If repository inspection shows existing code, adapt the task to the actual code and preserve working behavior; never overwrite simply to match a suggested file layout.

If a decision is unresolved, stop that dependent implementation and record [DECISION REQUIRED]. Ask the instructor/team or use documented evidence to decide; do not let Codex guess.

Use synthetic or otherwise authorized data. Keep API keys server-side. Report observed results only; never invent forecast accuracy, AI quality, performance, or business impact.

# 2. Approved Project Baseline

| Baseline item | Approved scope / decision |
| --- | --- |
| Purpose | A standalone web application that organizes seller-entered business records and offers AI/ML analysis and decision support. |
| Core value | Explainable analysis and reviewable suggestions; product/order CRUD is the data foundation, not the AI value by itself. |
| Frontend | React, Vite, TypeScript, Tailwind CSS, shadcn/ui, TanStack Query, Recharts. |
| Backend | Python, Django, Django REST Framework, Django ORM. |
| Database | PostgreSQL. |
| Analytics/ML | Pandas, NumPy, Scikit-learn; XGBoost only if justified by data and evaluation. |
| LLM | Backend-isolated LLM API; provider and terms must be reviewed before selection. |
| Six features | AI Customer Assistant; AI Business Advisor; Customer Segmentation; Demand Forecasting; Profit Intelligence; What-if Business Simulator. |
| Included operations | Seller/store profile, products/variants, stock/movements, customers, orders/items/status, expenses, sales/dashboard. |
| Boundaries | No live social/courier/payment integrations, automatic message sending, autonomous business actions, sensitive profiling, guaranteed forecast, formal accounting, or tax advice in the prototype. |
| Institution | Daffodil International University (DIU), Department of Software Engineering; Instructor Farhan Tanvir. |

# 3. Decisions Required Before Dependent Coding

These items are intentionally open in the proposal or execution roadmap. Keep them marked [DECISION REQUIRED] until the team or instructor approves a written rule.

Account/store model: one store per account or multiple stores; staff roles and account/store membership (PLAN-04).

Order lifecycle: exact valid transitions; which statuses count toward sales/profit; cancellation, refund, and return behavior; when stock is deducted or restored (PLAN-03).

Financial definitions: discount level, delivery cost placement, other-expense allocation, missing cost behavior, date basis, timezone, currency, and rounding (PLAN-03, PROFIT-01).

Forecast: data sufficiency minimum, time granularity, horizon, baseline, candidate model, evaluation metric, and evaluation split (PLAN-05, FORECAST-02 through 06).

Simulator: supported price/discount scenarios, demand-response assumptions, and how baseline values are selected. Do not imply causal effects (SIM-01).

LLM provider: privacy/retention terms, key management, budget, availability, timeout, and fallback (PLAN-06).

Demo data: synthetic-only or otherwise authorized records and reset/retention controls (PLAN-06, DATA-01).

Optional product variants, SKU uniqueness, duplicate customer rules, and delete/archive behavior when the proposal is not specific (record in the decision log before schema/API implementation).

# 4. Complete Phase List and Recommended Order

01. Phase 0 — Scope and decisions — Confirm the source of truth, existing repository state, boundaries, data policy, and decisions that must be recorded before implementation. (6 tasks; PLAN-01–PLAN-06)

02. Phase 1 — Repository and development environment — Establish reproducible Git, Django, React, environment, and local run foundations without implementing product modules. (7 tasks; SETUP-01–SETUP-07)

03. Phase 2 — Backend, frontend, schema, and API contract — Agree the cross-layer vocabulary and error behavior before CRUD and feature screens diverge. (13 tasks; BACKEND-01–DB-05)

04. Phase 3 — Authentication and store isolation — Secure each request before product data is exposed. (6 tasks; AUTH-01–AUTH-06)

05. Phase 4 — Test-data policy and operational records — Build the structured, store-scoped data foundation that powers all analysis. (4 tasks; DATA-01–DATA-04)

06. Phase 5 — Product and inventory — Implement stock records and auditable updates before orders depend on them. (7 tasks; PRODUCT-01–PRODUCT-07)

07. Phase 6 — Inventory — Make every quantity change traceable and transaction-safe. (6 tasks; INV-01–INV-06)

08. Phase 7 — Customers and orders — Implement linked purchases and status transitions based on approved business rules. (13 tasks; CUSTOMER-01–ORDER-08)

09. Phase 8 — Expenses and synthetic demo data — Record costs transparently and make demo data reproducible. (4 tasks; EXPENSE-01–EXPENSE-04)

10. Phase 9 — Sales analytics, profit intelligence, and dashboard — Calculate explainable measures from verified transactions before asking AI to describe them. (11 tasks; ANALYTICS-01–PROFIT-06)

11. Phase 10 — Dashboard — Present the approved indicators clearly and provide empty/error states. (4 tasks; DASH-01–DASH-04)

12. Phase 11 — AI Customer Assistant — Retrieve store facts, draft a reply, and leave the decision with the seller. (8 tasks; ASSISTANT-01–ASSISTANT-08)

13. Phase 12 — AI Business Advisor — Calculate metrics in code, then use the LLM only to explain verified context. (5 tasks; ADVISOR-01–ADVISOR-05)

14. Phase 13 — Customer segmentation — Start with explainable behavior rules; use no sensitive attributes. (5 tasks; SEGMENT-01–SEGMENT-05)

15. Phase 14 — Demand forecasting — Audit data before choosing a model; compare candidates to a time-aware baseline. (10 tasks; FORECAST-01–FORECAST-10)

16. Phase 15 — What-if business simulator — Implement a transparent deterministic estimate for selected price or discount scenarios. (6 tasks; SIM-01–SIM-06)

17. Phase 16 — Integration and verification — Test the full record-to-insight flow and address concrete defects. (5 tasks; INTEGRATION-01–INTEGRATION-05)

18. Phase 17 — Testing, security, performance, and usability — Build evidence incrementally and report actual measurements only. (7 tasks; TEST-01–TEST-07)

19. Phase 18 — Demo readiness, documentation, and viva — Package the prototype and evidence so the student can explain every part honestly. (11 tasks; DEPLOY-01–VIVA-03)

# 5. Dependency Graph and Parallel Opportunities

Main path: PLAN-01 → PLAN-06 → SETUP → backend/frontend foundations → API contract + ERD → database → authentication/store isolation → synthetic data and operational modules → sales/profit/dashboard → AI/ML features → integration and evaluation → demo/release/docs/viva.

Product/API and product UI can be developed in separate tracks after the field contract and endpoint behavior are approved; integration waits for both. The same pattern applies to inventory, customers, orders, expenses, dashboard, and each AI feature.

Backend feature implementation depends on authentication, schema, and service contracts. Frontend feature implementation depends on FRONTEND-02/03 and the endpoint contract; do not let either side invent field names independently.

Order creation waits for product, customer, and inventory service contracts. Sales/profit waits for order status/revenue decisions and expense handling. Advisor waits for tested metrics. Forecast waits for a completed data audit and time-aware evaluation design.

The proposal allocates backend/API/database work to Monira and UI/visualization/usability work to Trisha after contract freeze; shared validation, integration, AI evaluation, and demo preparation remain joint. For this execution plan, Monira performs all hands-on tasks, including the Trisha-led frontend lane, and records actual work.

## Dependency map by feature

PLAN → SETUP → BACKEND/FRONTEND → API CONTRACT + ERD → DB → AUTH + STORE ISOLATION

AUTH → PRODUCT → INVENTORY; AUTH → CUSTOMER; PRODUCT + CUSTOMER + INVENTORY → ORDER → EXPENSE/SALES

ORDER + EXPENSE → ANALYTICS → PROFIT → DASHBOARD → BUSINESS ADVISOR

Product/stock → AI Customer Assistant; customer/order history → Segmentation; dated order history → Forecast; Profit + Analytics → What-if

All feature tests → full integration → security/performance/usability → demo release → documentation/viva

# 6. Codex Planning Batches

Complete one task at a time within each batch. A batch is a review milestone, not one combined Codex prompt.

Batch A — Decisions and baseline: PLAN-01 to PLAN-06

Batch B — Repository and app foundation: SETUP-01 to SETUP-07; BACKEND-01 to BACKEND-05; FRONTEND-01 to FRONTEND-03

Batch C — Schema, access, and test data: DB-01 to DB-05; AUTH-01 to AUTH-06; DATA-01 to DATA-04

Batch D — Operational records: PRODUCT-01 to PRODUCT-07; INV-01 to INV-06; CUSTOMER-01 to CUSTOMER-05; ORDER-01 to ORDER-08; EXPENSE-01 to EXPENSE-04

Batch E — Metrics and dashboard: ANALYTICS-01 to ANALYTICS-05; PROFIT-01 to PROFIT-06; DASH-01 to DASH-04

Batch F — AI/ML features: ASSISTANT-01 to ASSISTANT-08; ADVISOR-01 to ADVISOR-05; SEGMENT-01 to SEGMENT-05; FORECAST-01 to FORECAST-10; SIM-01 to SIM-06

Batch G — Integration and verification: INTEGRATION-01 to INTEGRATION-05; TEST-01 to TEST-07

Batch H — Release, docs, and viva: DEPLOY-01 to DEPLOY-03; DOC-01 to DOC-05; VIVA-01 to VIVA-03

# 7. Complete Task Register

This register is the working sequence. Every row begins NOT STARTED. Update state, tested evidence, and commit after the task is genuinely complete.

| ID | Task | Proposal lead | Hands-on operator | Dependency | Status | Tested |
| --- | --- | --- | --- | --- | --- | --- |
| PLAN-01 | Audit the current repository and tool environment | Joint | Monira (you) | — | NOT STARTED | ☐ |
| PLAN-02 | Lock project scope and proposal traceability | Joint | Monira (you) | PLAN-01 | NOT STARTED | ☐ |
| PLAN-03 | Decide order, revenue, refund, and inventory rules | Joint | Monira (you) | PLAN-02 | NOT STARTED | ☐ |
| PLAN-04 | Decide seller account and store access model | Joint | Monira (you) | PLAN-03 | NOT STARTED | ☐ |
| PLAN-05 | Decide analytics, forecast, and scenario rules | Joint | Monira (you) | PLAN-04 | NOT STARTED | ☐ |
| PLAN-06 | Approve data, LLM provider, and evaluation policy | Joint | Monira (you) | PLAN-05 | NOT STARTED | ☐ |
| SETUP-01 | Initialize or verify Git repository | Monira | Monira (you) | — | NOT STARTED | ☐ |
| SETUP-02 | Create the agreed project structure | Joint | Monira (you) | SETUP-01 | NOT STARTED | ☐ |
| SETUP-03 | Pin and document runtime versions | Joint | Monira (you) | SETUP-02 | NOT STARTED | ☐ |
| SETUP-04 | Create Django backend skeleton | Monira | Monira (you) | SETUP-03 | NOT STARTED | ☐ |
| SETUP-05 | Create React TypeScript frontend skeleton | Rukaiya | Monira (you) | SETUP-04 | NOT STARTED | ☐ |
| SETUP-06 | Add safe environment configuration templates | Joint | Monira (you) | SETUP-05 | NOT STARTED | ☐ |
| SETUP-07 | Write repeatable local setup and run instructions | Joint | Monira (you) | SETUP-06 | NOT STARTED | ☐ |
| BACKEND-01 | Configure Django settings by environment | Monira | Monira (you) | — | NOT STARTED | ☐ |
| BACKEND-02 | Add Django REST Framework baseline | Monira | Monira (you) | BACKEND-01 | NOT STARTED | ☐ |
| BACKEND-03 | Add backend health and readiness checks | Monira | Monira (you) | BACKEND-02 | NOT STARTED | ☐ |
| BACKEND-04 | Configure PostgreSQL development and test databases | Monira | Monira (you) | BACKEND-03 | NOT STARTED | ☐ |
| BACKEND-05 | Define API conventions and error contract | Joint | Monira (you) | BACKEND-04 | NOT STARTED | ☐ |
| FRONTEND-01 | Create accessible application shell and routing | Rukaiya | Monira (you) | SETUP-05 | NOT STARTED | ☐ |
| FRONTEND-02 | Create shared API client and error handling | Rukaiya | Monira (you) | BACKEND-05; SETUP-05 | NOT STARTED | ☐ |
| FRONTEND-03 | Create reusable form and status primitives | Rukaiya | Monira (you) | FRONTEND-01 | NOT STARTED | ☐ |
| DB-01 | Create and review SellerOS entity relationship design | Joint | Monira (you) | FRONTEND-03 | NOT STARTED | ☐ |
| DB-02 | Define field-level data dictionary and constraints | Joint | Monira (you) | DB-01 | NOT STARTED | ☐ |
| DB-03 | Implement core account and store models | Monira | Monira (you) | DB-02 | NOT STARTED | ☐ |
| DB-04 | Add migration and database constraint checks | Monira | Monira (you) | DB-03 | NOT STARTED | ☐ |
| DB-05 | Create shared test factories and test conventions | Joint | Monira (you) | DB-04 | NOT STARTED | ☐ |
| AUTH-01 | Implement registration and login API | Monira | Monira (you) | — | NOT STARTED | ☐ |
| AUTH-02 | Implement store profile create and read API | Monira | Monira (you) | AUTH-01 | NOT STARTED | ☐ |
| AUTH-03 | Add store-level permission enforcement | Monira | Monira (you) | AUTH-02 | NOT STARTED | ☐ |
| AUTH-04 | Add store isolation and permission test suite | Joint | Monira (you) | AUTH-03 | NOT STARTED | ☐ |
| AUTH-05 | Build frontend sign-in and session states | Rukaiya | Monira (you) | AUTH-04 | NOT STARTED | ☐ |
| AUTH-06 | Verify end-to-end authenticated store flow | Joint | Monira (you) | AUTH-05 | NOT STARTED | ☐ |
| DATA-01 | Create synthetic-data policy and seed strategy | Joint | Monira (you) | — | NOT STARTED | ☐ |
| DATA-02 | Create realistic synthetic product and customer records | Joint | Monira (you) | DATA-01 | NOT STARTED | ☐ |
| DATA-03 | Create synthetic order, expense, and time-series records | Joint | Monira (you) | DATA-02 | NOT STARTED | ☐ |
| DATA-04 | Create AI and evaluation case sets | Joint | Monira (you) | DATA-03 | NOT STARTED | ☐ |
| PRODUCT-01 | Create product and variant models | Monira | Monira (you) | — | NOT STARTED | ☐ |
| PRODUCT-02 | Add product and variant serializers | Monira | Monira (you) | PRODUCT-01 | NOT STARTED | ☐ |
| PRODUCT-03 | Implement product list and detail APIs | Monira | Monira (you) | PRODUCT-02 | NOT STARTED | ☐ |
| PRODUCT-04 | Implement product create and update APIs | Monira | Monira (you) | PRODUCT-03 | NOT STARTED | ☐ |
| PRODUCT-05 | Add product API validation and permission tests | Joint | Monira (you) | PRODUCT-04 | NOT STARTED | ☐ |
| PRODUCT-06 | Build product list and form UI | Rukaiya | Monira (you) | PRODUCT-02; BACKEND-05; FRONTEND-03 | NOT STARTED | ☐ |
| PRODUCT-07 | Connect product screens and verify workflow | Rukaiya | Monira (you) | PRODUCT-06 | NOT STARTED | ☐ |
| INV-01 | Create inventory movement model and low-stock rule | Monira | Monira (you) | — | NOT STARTED | ☐ |
| INV-02 | Implement atomic stock adjustment service | Monira | Monira (you) | INV-01 | NOT STARTED | ☐ |
| INV-03 | Add inventory list and adjustment APIs | Monira | Monira (you) | INV-02 | NOT STARTED | ☐ |
| INV-04 | Build inventory and low-stock UI | Rukaiya | Monira (you) | INV-03; BACKEND-05; FRONTEND-03 | NOT STARTED | ☐ |
| INV-05 | Verify product-to-inventory integration | Joint | Monira (you) | INV-04 | NOT STARTED | ☐ |
| INV-06 | Test stock concurrency and rollback boundaries | Joint | Monira (you) | INV-05 | NOT STARTED | ☐ |
| CUSTOMER-01 | Create customer model and store-scoped validation | Monira | Monira (you) | — | NOT STARTED | ☐ |
| CUSTOMER-02 | Implement customer list, detail, create, and update APIs | Monira | Monira (you) | CUSTOMER-01 | NOT STARTED | ☐ |
| CUSTOMER-03 | Implement order-derived purchase history | Monira | Monira (you) | CUSTOMER-02 | NOT STARTED | ☐ |
| CUSTOMER-04 | Build customer list and profile UI | Rukaiya | Monira (you) | CUSTOMER-02; FRONTEND-03 | NOT STARTED | ☐ |
| CUSTOMER-05 | Verify customer and order relationship | Joint | Monira (you) | CUSTOMER-04 | NOT STARTED | ☐ |
| ORDER-01 | Implement order and order-item models | Monira | Monira (you) | CUSTOMER-05 | NOT STARTED | ☐ |
| ORDER-02 | Implement order creation validation and serializers | Monira | Monira (you) | ORDER-01 | NOT STARTED | ☐ |
| ORDER-03 | Implement atomic order creation with stock reservation/deduction | Monira | Monira (you) | ORDER-02 | NOT STARTED | ☐ |
| ORDER-04 | Implement allowed order status transitions | Monira | Monira (you) | ORDER-03 | NOT STARTED | ☐ |
| ORDER-05 | Implement order list and detail APIs | Monira | Monira (you) | ORDER-04 | NOT STARTED | ☐ |
| ORDER-06 | Implement order status update API and audit record | Monira | Monira (you) | ORDER-05 | NOT STARTED | ☐ |
| ORDER-07 | Build order create and detail UI | Rukaiya | Monira (you) | ORDER-02; PRODUCT-03; CUSTOMER-02; BACKEND-05; FRONTEND-03 | NOT STARTED | ☐ |
| ORDER-08 | Build order list and status workflow UI | Rukaiya | Monira (you) | ORDER-05; ORDER-06; FRONTEND-03 | NOT STARTED | ☐ |
| EXPENSE-01 | Create expense model and validation | Monira | Monira (you) | — | NOT STARTED | ☐ |
| EXPENSE-02 | Implement expense list/create/update APIs | Monira | Monira (you) | EXPENSE-01 | NOT STARTED | ☐ |
| EXPENSE-03 | Build expense UI | Rukaiya | Monira (you) | EXPENSE-02; FRONTEND-03 | NOT STARTED | ☐ |
| EXPENSE-04 | Verify seeded demo records and reset command | Joint | Monira (you) | EXPENSE-03 | NOT STARTED | ☐ |
| ANALYTICS-01 | Define sales metric contract and eligible records | Joint | Monira (you) | — | NOT STARTED | ☐ |
| ANALYTICS-02 | Implement sales aggregation service | Monira | Monira (you) | ANALYTICS-01 | NOT STARTED | ☐ |
| ANALYTICS-03 | Implement sales summary API | Monira | Monira (you) | ANALYTICS-02 | NOT STARTED | ☐ |
| ANALYTICS-04 | Implement product performance breakdown | Monira | Monira (you) | ANALYTICS-03 | NOT STARTED | ☐ |
| ANALYTICS-05 | Add analytics API tests and query budget baseline | Joint | Monira (you) | ANALYTICS-04 | NOT STARTED | ☐ |
| PROFIT-01 | Approve estimated-profit formula and cost treatment | Joint | Monira (you) | ANALYTICS-05 | NOT STARTED | ☐ |
| PROFIT-02 | Implement order-level profit calculation service | Monira | Monira (you) | PROFIT-01 | NOT STARTED | ☐ |
| PROFIT-03 | Implement period-level profit aggregation | Monira | Monira (you) | PROFIT-02 | NOT STARTED | ☐ |
| PROFIT-04 | Implement profit API with calculation basis | Monira | Monira (you) | PROFIT-03 | NOT STARTED | ☐ |
| PROFIT-05 | Build profit table and visualization UI | Rukaiya | Monira (you) | PROFIT-04 | NOT STARTED | ☐ |
| PROFIT-06 | Audit profit examples and regression cases | Joint | Monira (you) | PROFIT-05 | NOT STARTED | ☐ |
| DASH-01 | Define dashboard layout and data contract | Joint | Monira (you) | — | NOT STARTED | ☐ |
| DASH-02 | Implement dashboard summary API composition | Monira | Monira (you) | DASH-01 | NOT STARTED | ☐ |
| DASH-03 | Build responsive dashboard charts and cards | Rukaiya | Monira (you) | DASH-01; DASH-02; FRONTEND-03 | NOT STARTED | ☐ |
| DASH-04 | Verify dashboard end-to-end with synthetic records | Joint | Monira (you) | DASH-03 | NOT STARTED | ☐ |
| ASSISTANT-01 | Specify supported assistant tasks and refusal behavior | Joint | Monira (you) | — | NOT STARTED | ☐ |
| ASSISTANT-02 | Implement store-scoped product and stock retrieval | Monira | Monira (you) | ASSISTANT-01 | NOT STARTED | ☐ |
| ASSISTANT-03 | Create minimal context builder and source metadata | Monira | Monira (you) | ASSISTANT-02 | NOT STARTED | ☐ |
| ASSISTANT-04 | Implement backend-only LLM adapter and safe configuration | Monira | Monira (you) | ASSISTANT-03 | NOT STARTED | ☐ |
| ASSISTANT-05 | Draft reply prompt and structured output validator | Monira | Monira (you) | ASSISTANT-04 | NOT STARTED | ☐ |
| ASSISTANT-06 | Implement assistant API and evaluation logging | Monira | Monira (you) | ASSISTANT-05 | NOT STARTED | ☐ |
| ASSISTANT-07 | Build internal AI inbox and draft review UI | Rukaiya | Monira (you) | ASSISTANT-06; FRONTEND-03 | NOT STARTED | ☐ |
| ASSISTANT-08 | Evaluate assistant grounding, injection, and fallback | Joint | Monira (you) | ASSISTANT-07 | NOT STARTED | ☐ |
| ADVISOR-01 | Define advisor metrics and insight templates | Joint | Monira (you) | — | NOT STARTED | ☐ |
| ADVISOR-02 | Implement advisor context from analytics services | Monira | Monira (you) | ADVISOR-01 | NOT STARTED | ☐ |
| ADVISOR-03 | Implement advisor generation and response validation | Monira | Monira (you) | ADVISOR-02 | NOT STARTED | ☐ |
| ADVISOR-04 | Build advisor insight UI | Rukaiya | Monira (you) | ADVISOR-03; FRONTEND-03 | NOT STARTED | ☐ |
| ADVISOR-05 | Evaluate advisor factuality and usefulness | Joint | Monira (you) | ADVISOR-04 | NOT STARTED | ☐ |
| SEGMENT-01 | Define customer behavior features and segment criteria | Joint | Monira (you) | — | NOT STARTED | ☐ |
| SEGMENT-02 | Implement customer feature calculation service | Monira | Monira (you) | SEGMENT-01 | NOT STARTED | ☐ |
| SEGMENT-03 | Implement rule assignment and explanation API | Monira | Monira (you) | SEGMENT-02 | NOT STARTED | ☐ |
| SEGMENT-04 | Build segment overview and customer list UI | Rukaiya | Monira (you) | SEGMENT-03; FRONTEND-03 | NOT STARTED | ☐ |
| SEGMENT-05 | Validate segment edge cases and stability | Joint | Monira (you) | SEGMENT-04 | NOT STARTED | ☐ |
| FORECAST-01 | Audit available historical sales data | Joint | Monira (you) | — | NOT STARTED | ☐ |
| FORECAST-02 | Define minimum-data and eligibility rule | Joint | Monira (you) | FORECAST-01 | NOT STARTED | ☐ |
| FORECAST-03 | Prepare chronological product demand dataset | Monira | Monira (you) | FORECAST-02 | NOT STARTED | ☐ |
| FORECAST-04 | Choose baseline and candidate model | Joint | Monira (you) | FORECAST-03 | NOT STARTED | ☐ |
| FORECAST-05 | Define metrics and rolling evaluation split | Joint | Monira (you) | FORECAST-04 | NOT STARTED | ☐ |
| FORECAST-06 | Implement training and baseline evaluation | Monira | Monira (you) | FORECAST-05 | NOT STARTED | ☐ |
| FORECAST-07 | Run leakage and plausibility checks | Joint | Monira (you) | FORECAST-06 | NOT STARTED | ☐ |
| FORECAST-08 | Implement forecast service and insufficient-data response | Monira | Monira (you) | FORECAST-07 | NOT STARTED | ☐ |
| FORECAST-09 | Implement forecast API, UI, and result disclosure | Rukaiya | Monira (you) | FORECAST-08; FRONTEND-03 | NOT STARTED | ☐ |
| FORECAST-10 | Document forecast limitations and tested performance | Joint | Monira (you) | FORECAST-09 | NOT STARTED | ☐ |
| SIM-01 | Define supported scenario and assumptions | Joint | Monira (you) | — | NOT STARTED | ☐ |
| SIM-02 | Design simulator request and response contract | Joint | Monira (you) | SIM-01 | NOT STARTED | ☐ |
| SIM-03 | Implement deterministic scenario calculation service | Monira | Monira (you) | SIM-02 | NOT STARTED | ☐ |
| SIM-04 | Implement simulator API and edge-case validation | Monira | Monira (you) | SIM-03 | NOT STARTED | ☐ |
| SIM-05 | Build simulator UI and assumption disclosure | Rukaiya | Monira (you) | SIM-04; FRONTEND-03 | NOT STARTED | ☐ |
| SIM-06 | Evaluate simulator examples and boundaries | Joint | Monira (you) | SIM-05 | NOT STARTED | ☐ |
| INTEGRATION-01 | Run cross-module contract review | Joint | Monira (you) | — | NOT STARTED | ☐ |
| INTEGRATION-02 | Verify end-to-end seller workflow | Joint | Monira (you) | INTEGRATION-01 | NOT STARTED | ☐ |
| INTEGRATION-03 | Verify AI workflow against operational data | Joint | Monira (you) | INTEGRATION-02 | NOT STARTED | ☐ |
| INTEGRATION-04 | Triage and fix verified integration defects | Joint | Monira (you) | INTEGRATION-03 | NOT STARTED | ☐ |
| INTEGRATION-05 | Run full regression and record results | Joint | Monira (you) | INTEGRATION-04 | NOT STARTED | ☐ |
| TEST-01 | Add model and constraint tests across modules | Monira | Monira (you) | — | NOT STARTED | ☐ |
| TEST-02 | Add serializer and validation test matrix | Monira | Monira (you) | TEST-01 | NOT STARTED | ☐ |
| TEST-03 | Add API and permission test matrix | Joint | Monira (you) | TEST-02 | NOT STARTED | ☐ |
| TEST-04 | Add frontend form and state tests | Rukaiya | Monira (you) | TEST-03 | NOT STARTED | ☐ |
| TEST-05 | Add end-to-end workflow tests | Joint | Monira (you) | TEST-04 | NOT STARTED | ☐ |
| TEST-06 | Run security review and remediation | Joint | Monira (you) | TEST-05 | NOT STARTED | ☐ |
| TEST-07 | Measure performance and run usability checks | Joint | Monira (you) | TEST-06 | NOT STARTED | ☐ |
| DEPLOY-01 | Choose local demo or approved deployment target | Joint | Monira (you) | — | NOT STARTED | ☐ |
| DEPLOY-02 | Prepare repeatable demo build and environment | Monira | Monira (you) | DEPLOY-01 | NOT STARTED | ☐ |
| DEPLOY-03 | Run release smoke test and rollback rehearsal | Joint | Monira (you) | DEPLOY-02 | NOT STARTED | ☐ |
| DOC-01 | Write system architecture and data-flow documentation | Joint | Monira (you) | DEPLOY-03 | NOT STARTED | ☐ |
| DOC-02 | Write API, database, and business-rule documentation | Monira | Monira (you) | DOC-01 | NOT STARTED | ☐ |
| DOC-03 | Write setup, user, and troubleshooting guide | Rukaiya | Monira (you) | DOC-02 | NOT STARTED | ☐ |
| DOC-04 | Prepare testing, AI evaluation, and limitation report | Joint | Monira (you) | DOC-03 | NOT STARTED | ☐ |
| DOC-05 | Prepare demo script, screenshots, and reset procedure | Joint | Monira (you) | DOC-04 | NOT STARTED | ☐ |
| VIVA-01 | Build module-by-module viva question bank | Joint | Monira (you) | DOC-05 | NOT STARTED | ☐ |
| VIVA-02 | Conduct mock viva and close understanding gaps | Joint | Monira (you) | VIVA-01 | NOT STARTED | ☐ |
| VIVA-03 | Freeze final release, evidence, and contribution record | Joint | Monira (you) | VIVA-02 | NOT STARTED | ☐ |

# 8. Detailed Codex Task Cards

Each prompt below is ready to paste after its prerequisites pass. It authorizes only that task. The commands are deliberately environment-aware where exact versions/ports remain to be verified; use the commands recorded in SETUP-07 rather than guessing.

# Phase 0 — Scope and decisions

Confirm the source of truth, existing repository state, boundaries, data policy, and decisions that must be recorded before implementation.

## PLAN-01 — Audit the current repository and tool environment

Proposal lead / workstream assignment: Jointly assigned to Monira Islam and Rukaiya Akther Trisha — follows the proposal split; this is a planned role, not a contribution record.

Hands-on operator: Monira Islam (you) — you will carry out every task, including tasks assigned to the frontend/UI workstream.

Requirement: The plan must not assume code or setup that may already exist.

Target: A short verified inventory of repository, branches, installed tools, existing code, and run status is recorded.

Why this task matters: A short verified inventory of repository, branches, installed tools, existing code, and run status is recorded. It isolates one change so the student can inspect, test, and explain it before moving on.

Prerequisites: None beyond repository inspection and the approved project baseline.

Concepts to understand: Repository inspection; Git status; environment inventory.

Expected files/modules: Repository tree; README; package manifests; Python/Django settings; Git status/log.

Implementation scope: Inspect only; record evidence and gaps; do not change code.

Not in this task: Other modules, unrelated refactors, new dependencies, and unapproved features.

Ready-to-paste Codex prompt

You are implementing SellerOS, the SE-331 standalone social-commerce seller BI/decision-support capstone. Implement only PLAN-01 — Audit the current repository and tool environment. Requirement: The plan must not assume code or setup that may already exist. Objective/acceptance target: A short verified inventory of repository, branches, installed tools, existing code, and run status is recorded. Scope allowed: Inspect only; record evidence and gaps; do not change code. Likely files/modules: Repository tree; README; package manifests; Python/Django settings; Git status/log. Prerequisites: none beyond the approved project baseline. Constraints: follow the approved React/Vite/TypeScript + Django/DRF + PostgreSQL architecture and existing API/data contracts; inspect the repository first; preserve existing working behavior; do not invent unresolved business rules—mark [DECISION REQUIRED]; do not modify unrelated files, add unnecessary dependencies, expose secrets, bypass authentication/store permissions, fabricate AI/ML results, or create autonomous actions. Out of scope for this task: Other modules, unrelated refactors, new dependencies, and unapproved features. Test requirement: Checklist: clean/dirty tree, existing code, versions, run commands; no files modified. Run the narrow relevant checks and report exact commands and outcomes. Expected output: focused implementation, meaningful tests, and concise notes on files changed, decisions, risks, and next dependency. Code quality: small readable changes, type/validation/error handling appropriate to the existing project, no duplicated business formulas, and no generated or sensitive data committed.

Expected Codex output: A focused change for PLAN-01, relevant tests, a file-change summary, and exact commands/results. No unrelated implementation.

How to inspect: Review the diff for these boundaries: Inspect only; record evidence and gaps; do not change code. Confirm only expected files changed, validation/permissions match the contract, and tests exercise the requirement.

How to understand: Explain in your own words how Repository inspection; Git status; environment inventory. support this task; trace one normal case and one failure case through the code.

Run commands: Use verified environment commands from SETUP-07. Typical checks: backend: `python manage.py check` and the focused Django test module; frontend: `npm run lint`, focused test, and `npm run build`. Run only commands applicable to changed code and report exact outcomes.

Test steps / expected result: Checklist: clean/dirty tree, existing code, versions, run commands; no files modified. Success means the target is present, tests pass, and failure behavior is understandable.

Common errors: If the DB is unavailable, verify PostgreSQL service, database name, credentials, and env loading. If imports/routes fail, check app registration and URL inclusion. If an API/UI mismatch appears, compare against docs/api-contract.md and correct the contract or implementation deliberately; do not patch around it.

Git milestone: After review and passing tests, commit only this task. Suggested: `git add <reviewed-files> && git commit -m "PLAN-01: audit the current repository and tool environment"`. Use a feature branch only when it helps isolate a risky/long feature; no empty commits.

Viva questions: 1. What requirement does PLAN-01 satisfy? 2. Which data/API/UI boundary does it change? 3. How is invalid or unauthorized input handled? 4. What test proves it works? 5. What limitation remains?

Definition of Done: ☐ Scope met  ☐ Code understood  ☐ Focused tests pass  ☐ No unrelated changes  ☐ Evidence recorded  ☐ Commit created  ☐ Docs updated if affected  ☐ Viva explanation ready

## PLAN-02 — Lock project scope and proposal traceability

Proposal lead / workstream assignment: Jointly assigned to Monira Islam and Rukaiya Akther Trisha — follows the proposal split; this is a planned role, not a contribution record.

Hands-on operator: Monira Islam (you) — you will carry out every task, including tasks assigned to the frontend/UI workstream.

Requirement: Preserve proposal objectives, in-scope features, exclusions, and FR/AIR/NFR mappings.

Target: A traceable scope register maps each proposal requirement to modules and evidence.

Why this task matters: A traceable scope register maps each proposal requirement to modules and evidence. It isolates one change so the student can inspect, test, and explain it before moving on.

Prerequisites: PLAN-01

Concepts to understand: Functional/non-functional requirements; scope baseline; acceptance criteria.

Expected files/modules: docs/requirements; traceability register.

Implementation scope: Map proposal requirements and six AI/analytics features; carry exclusions into a no-build list.

Not in this task: Other modules, unrelated refactors, new dependencies, and unapproved features.

Ready-to-paste Codex prompt

You are implementing SellerOS, the SE-331 standalone social-commerce seller BI/decision-support capstone. Implement only PLAN-02 — Lock project scope and proposal traceability. Requirement: Preserve proposal objectives, in-scope features, exclusions, and FR/AIR/NFR mappings. Objective/acceptance target: A traceable scope register maps each proposal requirement to modules and evidence. Scope allowed: Map proposal requirements and six AI/analytics features; carry exclusions into a no-build list. Likely files/modules: docs/requirements; traceability register. Prerequisites: PLAN-01. Constraints: follow the approved React/Vite/TypeScript + Django/DRF + PostgreSQL architecture and existing API/data contracts; inspect the repository first; preserve existing working behavior; do not invent unresolved business rules—mark [DECISION REQUIRED]; do not modify unrelated files, add unnecessary dependencies, expose secrets, bypass authentication/store permissions, fabricate AI/ML results, or create autonomous actions. Out of scope for this task: Other modules, unrelated refactors, new dependencies, and unapproved features. Test requirement: Every approved requirement has a planned implementation/test location; every exclusion is listed. Run the narrow relevant checks and report exact commands and outcomes. Expected output: focused implementation, meaningful tests, and concise notes on files changed, decisions, risks, and next dependency. Code quality: small readable changes, type/validation/error handling appropriate to the existing project, no duplicated business formulas, and no generated or sensitive data committed.

Expected Codex output: A focused change for PLAN-02, relevant tests, a file-change summary, and exact commands/results. No unrelated implementation.

How to inspect: Review the diff for these boundaries: Map proposal requirements and six AI/analytics features; carry exclusions into a no-build list. Confirm only expected files changed, validation/permissions match the contract, and tests exercise the requirement.

How to understand: Explain in your own words how Functional/non-functional requirements; scope baseline; acceptance criteria. support this task; trace one normal case and one failure case through the code.

Run commands: Use verified environment commands from SETUP-07. Typical checks: backend: `python manage.py check` and the focused Django test module; frontend: `npm run lint`, focused test, and `npm run build`. Run only commands applicable to changed code and report exact outcomes.

Test steps / expected result: Every approved requirement has a planned implementation/test location; every exclusion is listed. Success means the target is present, tests pass, and failure behavior is understandable.

Common errors: If the DB is unavailable, verify PostgreSQL service, database name, credentials, and env loading. If imports/routes fail, check app registration and URL inclusion. If an API/UI mismatch appears, compare against docs/api-contract.md and correct the contract or implementation deliberately; do not patch around it.

Git milestone: After review and passing tests, commit only this task. Suggested: `git add <reviewed-files> && git commit -m "PLAN-02: lock project scope and proposal traceability"`. Use a feature branch only when it helps isolate a risky/long feature; no empty commits.

Viva questions: 1. What requirement does PLAN-02 satisfy? 2. Which data/API/UI boundary does it change? 3. How is invalid or unauthorized input handled? 4. What test proves it works? 5. What limitation remains?

Definition of Done: ☐ Scope met  ☐ Code understood  ☐ Focused tests pass  ☐ No unrelated changes  ☐ Evidence recorded  ☐ Commit created  ☐ Docs updated if affected  ☐ Viva explanation ready

## PLAN-03 — Decide order, revenue, refund, and inventory rules

Proposal lead / workstream assignment: Jointly assigned to Monira Islam and Rukaiya Akther Trisha — follows the proposal split; this is a planned role, not a contribution record.

Hands-on operator: Monira Islam (you) — you will carry out every task, including tasks assigned to the frontend/UI workstream.

Requirement: Order status and sales/profit treatment must be consistent.

Target: Written decision record defines status transitions, revenue recognition, cancellation/refund behavior, stock timing, and discount level.

Why this task matters: Written decision record defines status transitions, revenue recognition, cancellation/refund behavior, stock timing, and discount level. It isolates one change so the student can inspect, test, and explain it before moving on.

Prerequisites: PLAN-02

Concepts to understand: State transitions; transactions; revenue vs. cash; reversals.

Expected files/modules: docs/decisions/order-and-inventory.md.

Implementation scope: Present alternatives for team/instructor decision; mark unknown choices [DECISION REQUIRED]; do not invent one.

Not in this task: Other modules, unrelated refactors, new dependencies, and unapproved features.

Ready-to-paste Codex prompt

You are implementing SellerOS, the SE-331 standalone social-commerce seller BI/decision-support capstone. Implement only PLAN-03 — Decide order, revenue, refund, and inventory rules. Requirement: Order status and sales/profit treatment must be consistent. Objective/acceptance target: Written decision record defines status transitions, revenue recognition, cancellation/refund behavior, stock timing, and discount level. Scope allowed: Present alternatives for team/instructor decision; mark unknown choices [DECISION REQUIRED]; do not invent one. Likely files/modules: docs/decisions/order-and-inventory.md. Prerequisites: PLAN-02. Constraints: follow the approved React/Vite/TypeScript + Django/DRF + PostgreSQL architecture and existing API/data contracts; inspect the repository first; preserve existing working behavior; do not invent unresolved business rules—mark [DECISION REQUIRED]; do not modify unrelated files, add unnecessary dependencies, expose secrets, bypass authentication/store permissions, fabricate AI/ML results, or create autonomous actions. Out of scope for this task: Other modules, unrelated refactors, new dependencies, and unapproved features. Test requirement: Decision record approved before ORDER implementation. Run the narrow relevant checks and report exact commands and outcomes. Expected output: focused implementation, meaningful tests, and concise notes on files changed, decisions, risks, and next dependency. Code quality: small readable changes, type/validation/error handling appropriate to the existing project, no duplicated business formulas, and no generated or sensitive data committed.

Expected Codex output: A focused change for PLAN-03, relevant tests, a file-change summary, and exact commands/results. No unrelated implementation.

How to inspect: Review the diff for these boundaries: Present alternatives for team/instructor decision; mark unknown choices [DECISION REQUIRED]; do not invent one. Confirm only expected files changed, validation/permissions match the contract, and tests exercise the requirement.

How to understand: Explain in your own words how State transitions; transactions; revenue vs. cash; reversals. support this task; trace one normal case and one failure case through the code.

Run commands: Use verified environment commands from SETUP-07. Typical checks: backend: `python manage.py check` and the focused Django test module; frontend: `npm run lint`, focused test, and `npm run build`. Run only commands applicable to changed code and report exact outcomes.

Test steps / expected result: Decision record approved before ORDER implementation. Success means the target is present, tests pass, and failure behavior is understandable.

Common errors: If the DB is unavailable, verify PostgreSQL service, database name, credentials, and env loading. If imports/routes fail, check app registration and URL inclusion. If an API/UI mismatch appears, compare against docs/api-contract.md and correct the contract or implementation deliberately; do not patch around it.

Git milestone: After review and passing tests, commit only this task. Suggested: `git add <reviewed-files> && git commit -m "PLAN-03: decide order, revenue, refund, and inventory rules"`. Use a feature branch only when it helps isolate a risky/long feature; no empty commits.

Viva questions: 1. What requirement does PLAN-03 satisfy? 2. Which data/API/UI boundary does it change? 3. How is invalid or unauthorized input handled? 4. What test proves it works? 5. What limitation remains?

Definition of Done: ☐ Scope met  ☐ Code understood  ☐ Focused tests pass  ☐ No unrelated changes  ☐ Evidence recorded  ☐ Commit created  ☐ Docs updated if affected  ☐ Viva explanation ready

## PLAN-04 — Decide seller account and store access model

Proposal lead / workstream assignment: Jointly assigned to Monira Islam and Rukaiya Akther Trisha — follows the proposal split; this is a planned role, not a contribution record.

Hands-on operator: Monira Islam (you) — you will carry out every task, including tasks assigned to the frontend/UI workstream.

Requirement: The prototype requires authenticated seller/store records and server-side authorization.

Target: A written decision states one-store or multi-store account model, user roles, account creation, and store isolation.

Why this task matters: A written decision states one-store or multi-store account model, user roles, account creation, and store isolation. It isolates one change so the student can inspect, test, and explain it before moving on.

Prerequisites: PLAN-03

Concepts to understand: Authentication; authorization; tenant isolation; least privilege.

Expected files/modules: docs/decisions/auth-and-store.md; proposed ERD.

Implementation scope: Select the minimum prototype model with instructor/team; document permissions and test cases.

Not in this task: Other modules, unrelated refactors, new dependencies, and unapproved features.

Ready-to-paste Codex prompt

You are implementing SellerOS, the SE-331 standalone social-commerce seller BI/decision-support capstone. Implement only PLAN-04 — Decide seller account and store access model. Requirement: The prototype requires authenticated seller/store records and server-side authorization. Objective/acceptance target: A written decision states one-store or multi-store account model, user roles, account creation, and store isolation. Scope allowed: Select the minimum prototype model with instructor/team; document permissions and test cases. Likely files/modules: docs/decisions/auth-and-store.md; proposed ERD. Prerequisites: PLAN-03. Constraints: follow the approved React/Vite/TypeScript + Django/DRF + PostgreSQL architecture and existing API/data contracts; inspect the repository first; preserve existing working behavior; do not invent unresolved business rules—mark [DECISION REQUIRED]; do not modify unrelated files, add unnecessary dependencies, expose secrets, bypass authentication/store permissions, fabricate AI/ML results, or create autonomous actions. Out of scope for this task: Other modules, unrelated refactors, new dependencies, and unapproved features. Test requirement: One chosen policy is testable; cross-store access cases are listed. Run the narrow relevant checks and report exact commands and outcomes. Expected output: focused implementation, meaningful tests, and concise notes on files changed, decisions, risks, and next dependency. Code quality: small readable changes, type/validation/error handling appropriate to the existing project, no duplicated business formulas, and no generated or sensitive data committed.

Expected Codex output: A focused change for PLAN-04, relevant tests, a file-change summary, and exact commands/results. No unrelated implementation.

How to inspect: Review the diff for these boundaries: Select the minimum prototype model with instructor/team; document permissions and test cases. Confirm only expected files changed, validation/permissions match the contract, and tests exercise the requirement.

How to understand: Explain in your own words how Authentication; authorization; tenant isolation; least privilege. support this task; trace one normal case and one failure case through the code.

Run commands: Use verified environment commands from SETUP-07. Typical checks: backend: `python manage.py check` and the focused Django test module; frontend: `npm run lint`, focused test, and `npm run build`. Run only commands applicable to changed code and report exact outcomes.

Test steps / expected result: One chosen policy is testable; cross-store access cases are listed. Success means the target is present, tests pass, and failure behavior is understandable.

Common errors: If the DB is unavailable, verify PostgreSQL service, database name, credentials, and env loading. If imports/routes fail, check app registration and URL inclusion. If an API/UI mismatch appears, compare against docs/api-contract.md and correct the contract or implementation deliberately; do not patch around it.

Git milestone: After review and passing tests, commit only this task. Suggested: `git add <reviewed-files> && git commit -m "PLAN-04: decide seller account and store access model"`. Use a feature branch only when it helps isolate a risky/long feature; no empty commits.

Viva questions: 1. What requirement does PLAN-04 satisfy? 2. Which data/API/UI boundary does it change? 3. How is invalid or unauthorized input handled? 4. What test proves it works? 5. What limitation remains?

Definition of Done: ☐ Scope met  ☐ Code understood  ☐ Focused tests pass  ☐ No unrelated changes  ☐ Evidence recorded  ☐ Commit created  ☐ Docs updated if affected  ☐ Viva explanation ready

## PLAN-05 — Decide analytics, forecast, and scenario rules

Proposal lead / workstream assignment: Jointly assigned to Monira Islam and Rukaiya Akther Trisha — follows the proposal split; this is a planned role, not a contribution record.

Hands-on operator: Monira Islam (you) — you will carry out every task, including tasks assigned to the frontend/UI workstream.

Requirement: AI/ML outputs depend on explicit definitions, sufficient data, and disclosed assumptions.

Target: Metric definitions and data sufficiency, baseline, horizon, scenario variables, and fallback decisions are recorded.

Why this task matters: Metric definitions and data sufficiency, baseline, horizon, scenario variables, and fallback decisions are recorded. It isolates one change so the student can inspect, test, and explain it before moving on.

Prerequisites: PLAN-04

Concepts to understand: Forecasting; time-aware validation; deterministic metrics; assumption disclosure.

Expected files/modules: docs/decisions/analytics-and-ai.md.

Implementation scope: Define candidate choices, what data is needed, how insufficient data is shown; retain [DECISION REQUIRED] where unresolved.

Not in this task: Other modules, unrelated refactors, new dependencies, and unapproved features.

Ready-to-paste Codex prompt

You are implementing SellerOS, the SE-331 standalone social-commerce seller BI/decision-support capstone. Implement only PLAN-05 — Decide analytics, forecast, and scenario rules. Requirement: AI/ML outputs depend on explicit definitions, sufficient data, and disclosed assumptions. Objective/acceptance target: Metric definitions and data sufficiency, baseline, horizon, scenario variables, and fallback decisions are recorded. Scope allowed: Define candidate choices, what data is needed, how insufficient data is shown; retain [DECISION REQUIRED] where unresolved. Likely files/modules: docs/decisions/analytics-and-ai.md. Prerequisites: PLAN-04. Constraints: follow the approved React/Vite/TypeScript + Django/DRF + PostgreSQL architecture and existing API/data contracts; inspect the repository first; preserve existing working behavior; do not invent unresolved business rules—mark [DECISION REQUIRED]; do not modify unrelated files, add unnecessary dependencies, expose secrets, bypass authentication/store permissions, fabricate AI/ML results, or create autonomous actions. Out of scope for this task: Other modules, unrelated refactors, new dependencies, and unapproved features. Test requirement: Each output has inputs, formula/method, limitations, and a planned verification. Run the narrow relevant checks and report exact commands and outcomes. Expected output: focused implementation, meaningful tests, and concise notes on files changed, decisions, risks, and next dependency. Code quality: small readable changes, type/validation/error handling appropriate to the existing project, no duplicated business formulas, and no generated or sensitive data committed.

Expected Codex output: A focused change for PLAN-05, relevant tests, a file-change summary, and exact commands/results. No unrelated implementation.

How to inspect: Review the diff for these boundaries: Define candidate choices, what data is needed, how insufficient data is shown; retain [DECISION REQUIRED] where unresolved. Confirm only expected files changed, validation/permissions match the contract, and tests exercise the requirement.

How to understand: Explain in your own words how Forecasting; time-aware validation; deterministic metrics; assumption disclosure. support this task; trace one normal case and one failure case through the code.

Run commands: Use verified environment commands from SETUP-07. Typical checks: backend: `python manage.py check` and the focused Django test module; frontend: `npm run lint`, focused test, and `npm run build`. Run only commands applicable to changed code and report exact outcomes.

Test steps / expected result: Each output has inputs, formula/method, limitations, and a planned verification. Success means the target is present, tests pass, and failure behavior is understandable.

Common errors: If the DB is unavailable, verify PostgreSQL service, database name, credentials, and env loading. If imports/routes fail, check app registration and URL inclusion. If an API/UI mismatch appears, compare against docs/api-contract.md and correct the contract or implementation deliberately; do not patch around it.

Git milestone: After review and passing tests, commit only this task. Suggested: `git add <reviewed-files> && git commit -m "PLAN-05: decide analytics, forecast, and scenario rules"`. Use a feature branch only when it helps isolate a risky/long feature; no empty commits.

Viva questions: 1. What requirement does PLAN-05 satisfy? 2. Which data/API/UI boundary does it change? 3. How is invalid or unauthorized input handled? 4. What test proves it works? 5. What limitation remains?

Definition of Done: ☐ Scope met  ☐ Code understood  ☐ Focused tests pass  ☐ No unrelated changes  ☐ Evidence recorded  ☐ Commit created  ☐ Docs updated if affected  ☐ Viva explanation ready

## PLAN-06 — Approve data, LLM provider, and evaluation policy

Proposal lead / workstream assignment: Jointly assigned to Monira Islam and Rukaiya Akther Trisha — follows the proposal split; this is a planned role, not a contribution record.

Hands-on operator: Monira Islam (you) — you will carry out every task, including tasks assigned to the frontend/UI workstream.

Requirement: Testing must use authorized or synthetic data; LLM use must protect secrets and minimize context.

Target: Approved data policy, provider selection criteria, retention/privacy review, cost limits, and evaluation rubric are recorded.

Why this task matters: Approved data policy, provider selection criteria, retention/privacy review, cost limits, and evaluation rubric are recorded. It isolates one change so the student can inspect, test, and explain it before moving on.

Prerequisites: PLAN-05

Concepts to understand: PII minimization; secrets; provider retention; AI evaluation.

Expected files/modules: docs/decisions/data-and-provider.md; evaluation checklist.

Implementation scope: Decide whether the demo uses synthetic/authorized data; keep provider undecided until review if needed.

Not in this task: Other modules, unrelated refactors, new dependencies, and unapproved features.

Ready-to-paste Codex prompt

You are implementing SellerOS, the SE-331 standalone social-commerce seller BI/decision-support capstone. Implement only PLAN-06 — Approve data, LLM provider, and evaluation policy. Requirement: Testing must use authorized or synthetic data; LLM use must protect secrets and minimize context. Objective/acceptance target: Approved data policy, provider selection criteria, retention/privacy review, cost limits, and evaluation rubric are recorded. Scope allowed: Decide whether the demo uses synthetic/authorized data; keep provider undecided until review if needed. Likely files/modules: docs/decisions/data-and-provider.md; evaluation checklist. Prerequisites: PLAN-05. Constraints: follow the approved React/Vite/TypeScript + Django/DRF + PostgreSQL architecture and existing API/data contracts; inspect the repository first; preserve existing working behavior; do not invent unresolved business rules—mark [DECISION REQUIRED]; do not modify unrelated files, add unnecessary dependencies, expose secrets, bypass authentication/store permissions, fabricate AI/ML results, or create autonomous actions. Out of scope for this task: Other modules, unrelated refactors, new dependencies, and unapproved features. Test requirement: No real customer data or provider key is used before approval. Run the narrow relevant checks and report exact commands and outcomes. Expected output: focused implementation, meaningful tests, and concise notes on files changed, decisions, risks, and next dependency. Code quality: small readable changes, type/validation/error handling appropriate to the existing project, no duplicated business formulas, and no generated or sensitive data committed.

Expected Codex output: A focused change for PLAN-06, relevant tests, a file-change summary, and exact commands/results. No unrelated implementation.

How to inspect: Review the diff for these boundaries: Decide whether the demo uses synthetic/authorized data; keep provider undecided until review if needed. Confirm only expected files changed, validation/permissions match the contract, and tests exercise the requirement.

How to understand: Explain in your own words how PII minimization; secrets; provider retention; AI evaluation. support this task; trace one normal case and one failure case through the code.

Run commands: Use verified environment commands from SETUP-07. Typical checks: backend: `python manage.py check` and the focused Django test module; frontend: `npm run lint`, focused test, and `npm run build`. Run only commands applicable to changed code and report exact outcomes.

Test steps / expected result: No real customer data or provider key is used before approval. Success means the target is present, tests pass, and failure behavior is understandable.

Common errors: If the DB is unavailable, verify PostgreSQL service, database name, credentials, and env loading. If imports/routes fail, check app registration and URL inclusion. If an API/UI mismatch appears, compare against docs/api-contract.md and correct the contract or implementation deliberately; do not patch around it.

Git milestone: After review and passing tests, commit only this task. Suggested: `git add <reviewed-files> && git commit -m "PLAN-06: approve data, llm provider, and evaluation policy"`. Use a feature branch only when it helps isolate a risky/long feature; no empty commits.

Viva questions: 1. What requirement does PLAN-06 satisfy? 2. Which data/API/UI boundary does it change? 3. How is invalid or unauthorized input handled? 4. What test proves it works? 5. What limitation remains?

Definition of Done: ☐ Scope met  ☐ Code understood  ☐ Focused tests pass  ☐ No unrelated changes  ☐ Evidence recorded  ☐ Commit created  ☐ Docs updated if affected  ☐ Viva explanation ready

# Phase 1 — Repository and development environment

Establish reproducible Git, Django, React, environment, and local run foundations without implementing product modules.

## SETUP-01 — Initialize or verify Git repository

Proposal lead / workstream assignment: Monira Islam — follows the proposal split; this is a planned role, not a contribution record.

Hands-on operator: Monira Islam (you) — you will carry out every task, including tasks assigned to the frontend/UI workstream.

Requirement: All implementation needs a known repository and clean change history.

Target: A verified repository has an agreed default branch, ignore rules, and documented status.

Why this task matters: A verified repository has an agreed default branch, ignore rules, and documented status. It isolates one change so the student can inspect, test, and explain it before moving on.

Prerequisites: None beyond repository inspection and the approved project baseline.

Concepts to understand: Working tree; staging; commit; secret exclusion.

Expected files/modules: Git metadata; .gitignore; README.md.

Implementation scope: If already initialized, inspect and document; otherwise initialize Git, set ignore rules, and create an initial foundation commit.

Not in this task: Other modules, unrelated refactors, new dependencies, and unapproved features.

Ready-to-paste Codex prompt

You are implementing SellerOS, the SE-331 standalone social-commerce seller BI/decision-support capstone. Implement only SETUP-01 — Initialize or verify Git repository. Requirement: All implementation needs a known repository and clean change history. Objective/acceptance target: A verified repository has an agreed default branch, ignore rules, and documented status. Scope allowed: If already initialized, inspect and document; otherwise initialize Git, set ignore rules, and create an initial foundation commit. Likely files/modules: Git metadata; .gitignore; README.md. Prerequisites: none beyond the approved project baseline. Constraints: follow the approved React/Vite/TypeScript + Django/DRF + PostgreSQL architecture and existing API/data contracts; inspect the repository first; preserve existing working behavior; do not invent unresolved business rules—mark [DECISION REQUIRED]; do not modify unrelated files, add unnecessary dependencies, expose secrets, bypass authentication/store permissions, fabricate AI/ML results, or create autonomous actions. Out of scope for this task: Other modules, unrelated refactors, new dependencies, and unapproved features. Test requirement: git status and git log show the intended baseline; .env is ignored. Run the narrow relevant checks and report exact commands and outcomes. Expected output: focused implementation, meaningful tests, and concise notes on files changed, decisions, risks, and next dependency. Code quality: small readable changes, type/validation/error handling appropriate to the existing project, no duplicated business formulas, and no generated or sensitive data committed.

Expected Codex output: A focused change for SETUP-01, relevant tests, a file-change summary, and exact commands/results. No unrelated implementation.

How to inspect: Review the diff for these boundaries: If already initialized, inspect and document; otherwise initialize Git, set ignore rules, and create an initial foundation commit. Confirm only expected files changed, validation/permissions match the contract, and tests exercise the requirement.

How to understand: Explain in your own words how Working tree; staging; commit; secret exclusion. support this task; trace one normal case and one failure case through the code.

Run commands: Use verified environment commands from SETUP-07. Typical checks: backend: `python manage.py check` and the focused Django test module; frontend: `npm run lint`, focused test, and `npm run build`. Run only commands applicable to changed code and report exact outcomes.

Test steps / expected result: git status and git log show the intended baseline; .env is ignored. Success means the target is present, tests pass, and failure behavior is understandable.

Common errors: If the DB is unavailable, verify PostgreSQL service, database name, credentials, and env loading. If imports/routes fail, check app registration and URL inclusion. If an API/UI mismatch appears, compare against docs/api-contract.md and correct the contract or implementation deliberately; do not patch around it.

Git milestone: After review and passing tests, commit only this task. Suggested: `git add <reviewed-files> && git commit -m "SETUP-01: initialize or verify git repository"`. Use a feature branch only when it helps isolate a risky/long feature; no empty commits.

Viva questions: 1. What requirement does SETUP-01 satisfy? 2. Which data/API/UI boundary does it change? 3. How is invalid or unauthorized input handled? 4. What test proves it works? 5. What limitation remains?

Definition of Done: ☐ Scope met  ☐ Code understood  ☐ Focused tests pass  ☐ No unrelated changes  ☐ Evidence recorded  ☐ Commit created  ☐ Docs updated if affected  ☐ Viva explanation ready

## SETUP-02 — Create the agreed project structure

Proposal lead / workstream assignment: Jointly assigned to Monira Islam and Rukaiya Akther Trisha — follows the proposal split; this is a planned role, not a contribution record.

Hands-on operator: Monira Islam (you) — you will carry out every task, including tasks assigned to the frontend/UI workstream.

Requirement: Backend, frontend, docs, and test data need stable locations.

Target: A documented root layout exists and matches the plan.

Why this task matters: A documented root layout exists and matches the plan. It isolates one change so the student can inspect, test, and explain it before moving on.

Prerequisites: SETUP-01

Concepts to understand: Separation of concerns; monorepo layout.

Expected files/modules: backend/; frontend/; docs/; data/sample/; README.md.

Implementation scope: Create only agreed top-level directories and minimal README; no module implementation.

Not in this task: Other modules, unrelated refactors, new dependencies, and unapproved features.

Ready-to-paste Codex prompt

You are implementing SellerOS, the SE-331 standalone social-commerce seller BI/decision-support capstone. Implement only SETUP-02 — Create the agreed project structure. Requirement: Backend, frontend, docs, and test data need stable locations. Objective/acceptance target: A documented root layout exists and matches the plan. Scope allowed: Create only agreed top-level directories and minimal README; no module implementation. Likely files/modules: backend/; frontend/; docs/; data/sample/; README.md. Prerequisites: SETUP-01. Constraints: follow the approved React/Vite/TypeScript + Django/DRF + PostgreSQL architecture and existing API/data contracts; inspect the repository first; preserve existing working behavior; do not invent unresolved business rules—mark [DECISION REQUIRED]; do not modify unrelated files, add unnecessary dependencies, expose secrets, bypass authentication/store permissions, fabricate AI/ML results, or create autonomous actions. Out of scope for this task: Other modules, unrelated refactors, new dependencies, and unapproved features. Test requirement: Tree is clear; no generated secrets or unrelated scaffold. Run the narrow relevant checks and report exact commands and outcomes. Expected output: focused implementation, meaningful tests, and concise notes on files changed, decisions, risks, and next dependency. Code quality: small readable changes, type/validation/error handling appropriate to the existing project, no duplicated business formulas, and no generated or sensitive data committed.

Expected Codex output: A focused change for SETUP-02, relevant tests, a file-change summary, and exact commands/results. No unrelated implementation.

How to inspect: Review the diff for these boundaries: Create only agreed top-level directories and minimal README; no module implementation. Confirm only expected files changed, validation/permissions match the contract, and tests exercise the requirement.

How to understand: Explain in your own words how Separation of concerns; monorepo layout. support this task; trace one normal case and one failure case through the code.

Run commands: Use verified environment commands from SETUP-07. Typical checks: backend: `python manage.py check` and the focused Django test module; frontend: `npm run lint`, focused test, and `npm run build`. Run only commands applicable to changed code and report exact outcomes.

Test steps / expected result: Tree is clear; no generated secrets or unrelated scaffold. Success means the target is present, tests pass, and failure behavior is understandable.

Common errors: If the DB is unavailable, verify PostgreSQL service, database name, credentials, and env loading. If imports/routes fail, check app registration and URL inclusion. If an API/UI mismatch appears, compare against docs/api-contract.md and correct the contract or implementation deliberately; do not patch around it.

Git milestone: After review and passing tests, commit only this task. Suggested: `git add <reviewed-files> && git commit -m "SETUP-02: create the agreed project structure"`. Use a feature branch only when it helps isolate a risky/long feature; no empty commits.

Viva questions: 1. What requirement does SETUP-02 satisfy? 2. Which data/API/UI boundary does it change? 3. How is invalid or unauthorized input handled? 4. What test proves it works? 5. What limitation remains?

Definition of Done: ☐ Scope met  ☐ Code understood  ☐ Focused tests pass  ☐ No unrelated changes  ☐ Evidence recorded  ☐ Commit created  ☐ Docs updated if affected  ☐ Viva explanation ready

## SETUP-03 — Pin and document runtime versions

Proposal lead / workstream assignment: Jointly assigned to Monira Islam and Rukaiya Akther Trisha — follows the proposal split; this is a planned role, not a contribution record.

Hands-on operator: Monira Islam (you) — you will carry out every task, including tasks assigned to the frontend/UI workstream.

Requirement: Reproducible setup requires compatible, recorded runtime versions.

Target: Python, Node, package manager, PostgreSQL, and supported OS versions are documented after checking the actual environment.

Why this task matters: Python, Node, package manager, PostgreSQL, and supported OS versions are documented after checking the actual environment. It isolates one change so the student can inspect, test, and explain it before moving on.

Prerequisites: SETUP-02

Concepts to understand: Runtime compatibility; dependency pinning.

Expected files/modules: README; backend requirements/lock file; frontend package manifest.

Implementation scope: Choose versions compatible with project tooling; record exact verified versions.

Not in this task: Other modules, unrelated refactors, new dependencies, and unapproved features.

Ready-to-paste Codex prompt

You are implementing SellerOS, the SE-331 standalone social-commerce seller BI/decision-support capstone. Implement only SETUP-03 — Pin and document runtime versions. Requirement: Reproducible setup requires compatible, recorded runtime versions. Objective/acceptance target: Python, Node, package manager, PostgreSQL, and supported OS versions are documented after checking the actual environment. Scope allowed: Choose versions compatible with project tooling; record exact verified versions. Likely files/modules: README; backend requirements/lock file; frontend package manifest. Prerequisites: SETUP-02. Constraints: follow the approved React/Vite/TypeScript + Django/DRF + PostgreSQL architecture and existing API/data contracts; inspect the repository first; preserve existing working behavior; do not invent unresolved business rules—mark [DECISION REQUIRED]; do not modify unrelated files, add unnecessary dependencies, expose secrets, bypass authentication/store permissions, fabricate AI/ML results, or create autonomous actions. Out of scope for this task: Other modules, unrelated refactors, new dependencies, and unapproved features. Test requirement: Fresh environment can identify versions and install dependencies. Run the narrow relevant checks and report exact commands and outcomes. Expected output: focused implementation, meaningful tests, and concise notes on files changed, decisions, risks, and next dependency. Code quality: small readable changes, type/validation/error handling appropriate to the existing project, no duplicated business formulas, and no generated or sensitive data committed.

Expected Codex output: A focused change for SETUP-03, relevant tests, a file-change summary, and exact commands/results. No unrelated implementation.

How to inspect: Review the diff for these boundaries: Choose versions compatible with project tooling; record exact verified versions. Confirm only expected files changed, validation/permissions match the contract, and tests exercise the requirement.

How to understand: Explain in your own words how Runtime compatibility; dependency pinning. support this task; trace one normal case and one failure case through the code.

Run commands: Use verified environment commands from SETUP-07. Typical checks: backend: `python manage.py check` and the focused Django test module; frontend: `npm run lint`, focused test, and `npm run build`. Run only commands applicable to changed code and report exact outcomes.

Test steps / expected result: Fresh environment can identify versions and install dependencies. Success means the target is present, tests pass, and failure behavior is understandable.

Common errors: If the DB is unavailable, verify PostgreSQL service, database name, credentials, and env loading. If imports/routes fail, check app registration and URL inclusion. If an API/UI mismatch appears, compare against docs/api-contract.md and correct the contract or implementation deliberately; do not patch around it.

Git milestone: After review and passing tests, commit only this task. Suggested: `git add <reviewed-files> && git commit -m "SETUP-03: pin and document runtime versions"`. Use a feature branch only when it helps isolate a risky/long feature; no empty commits.

Viva questions: 1. What requirement does SETUP-03 satisfy? 2. Which data/API/UI boundary does it change? 3. How is invalid or unauthorized input handled? 4. What test proves it works? 5. What limitation remains?

Definition of Done: ☐ Scope met  ☐ Code understood  ☐ Focused tests pass  ☐ No unrelated changes  ☐ Evidence recorded  ☐ Commit created  ☐ Docs updated if affected  ☐ Viva explanation ready

## SETUP-04 — Create Django backend skeleton

Proposal lead / workstream assignment: Monira Islam — follows the proposal split; this is a planned role, not a contribution record.

Hands-on operator: Monira Islam (you) — you will carry out every task, including tasks assigned to the frontend/UI workstream.

Requirement: Backend foundation is required for API and data work.

Target: Django project starts with minimal settings and a verified health endpoint.

Why this task matters: Django project starts with minimal settings and a verified health endpoint. It isolates one change so the student can inspect, test, and explain it before moving on.

Prerequisites: SETUP-03

Concepts to understand: Django settings; apps; environment config; health endpoint.

Expected files/modules: backend/manage.py; backend config; minimal core app; backend tests.

Implementation scope: Create project/app skeleton and health check only; keep secrets in environment.

Not in this task: Other modules, unrelated refactors, new dependencies, and unapproved features.

Ready-to-paste Codex prompt

You are implementing SellerOS, the SE-331 standalone social-commerce seller BI/decision-support capstone. Implement only SETUP-04 — Create Django backend skeleton. Requirement: Backend foundation is required for API and data work. Objective/acceptance target: Django project starts with minimal settings and a verified health endpoint. Scope allowed: Create project/app skeleton and health check only; keep secrets in environment. Likely files/modules: backend/manage.py; backend config; minimal core app; backend tests. Prerequisites: SETUP-03. Constraints: follow the approved React/Vite/TypeScript + Django/DRF + PostgreSQL architecture and existing API/data contracts; inspect the repository first; preserve existing working behavior; do not invent unresolved business rules—mark [DECISION REQUIRED]; do not modify unrelated files, add unnecessary dependencies, expose secrets, bypass authentication/store permissions, fabricate AI/ML results, or create autonomous actions. Out of scope for this task: Other modules, unrelated refactors, new dependencies, and unapproved features. Test requirement: Backend check and health request pass locally. Run the narrow relevant checks and report exact commands and outcomes. Expected output: focused implementation, meaningful tests, and concise notes on files changed, decisions, risks, and next dependency. Code quality: small readable changes, type/validation/error handling appropriate to the existing project, no duplicated business formulas, and no generated or sensitive data committed.

Expected Codex output: A focused change for SETUP-04, relevant tests, a file-change summary, and exact commands/results. No unrelated implementation.

How to inspect: Review the diff for these boundaries: Create project/app skeleton and health check only; keep secrets in environment. Confirm only expected files changed, validation/permissions match the contract, and tests exercise the requirement.

How to understand: Explain in your own words how Django settings; apps; environment config; health endpoint. support this task; trace one normal case and one failure case through the code.

Run commands: Use verified environment commands from SETUP-07. Typical checks: backend: `python manage.py check` and the focused Django test module; frontend: `npm run lint`, focused test, and `npm run build`. Run only commands applicable to changed code and report exact outcomes.

Test steps / expected result: Backend check and health request pass locally. Success means the target is present, tests pass, and failure behavior is understandable.

Common errors: If the DB is unavailable, verify PostgreSQL service, database name, credentials, and env loading. If imports/routes fail, check app registration and URL inclusion. If an API/UI mismatch appears, compare against docs/api-contract.md and correct the contract or implementation deliberately; do not patch around it.

Git milestone: After review and passing tests, commit only this task. Suggested: `git add <reviewed-files> && git commit -m "SETUP-04: create django backend skeleton"`. Use a feature branch only when it helps isolate a risky/long feature; no empty commits.

Viva questions: 1. What requirement does SETUP-04 satisfy? 2. Which data/API/UI boundary does it change? 3. How is invalid or unauthorized input handled? 4. What test proves it works? 5. What limitation remains?

Definition of Done: ☐ Scope met  ☐ Code understood  ☐ Focused tests pass  ☐ No unrelated changes  ☐ Evidence recorded  ☐ Commit created  ☐ Docs updated if affected  ☐ Viva explanation ready

## SETUP-05 — Create React TypeScript frontend skeleton

Proposal lead / workstream assignment: Rukaiya Akther Trisha — follows the proposal split; this is a planned role, not a contribution record.

Hands-on operator: Monira Islam (you) — you will carry out every task, including tasks assigned to the frontend/UI workstream.

Requirement: The application needs a testable client shell.

Target: Vite React TypeScript app starts and displays a minimal SellerOS shell.

Why this task matters: Vite React TypeScript app starts and displays a minimal SellerOS shell. It isolates one change so the student can inspect, test, and explain it before moving on.

Prerequisites: SETUP-04

Concepts to understand: Vite; TypeScript; component entry point; CSS pipeline.

Expected files/modules: frontend/package.json; src/app; src/styles; frontend README.

Implementation scope: Set up Vite and agreed styling dependencies only after checking compatibility; no feature screens.

Not in this task: Other modules, unrelated refactors, new dependencies, and unapproved features.

Ready-to-paste Codex prompt

You are implementing SellerOS, the SE-331 standalone social-commerce seller BI/decision-support capstone. Implement only SETUP-05 — Create React TypeScript frontend skeleton. Requirement: The application needs a testable client shell. Objective/acceptance target: Vite React TypeScript app starts and displays a minimal SellerOS shell. Scope allowed: Set up Vite and agreed styling dependencies only after checking compatibility; no feature screens. Likely files/modules: frontend/package.json; src/app; src/styles; frontend README. Prerequisites: SETUP-04. Constraints: follow the approved React/Vite/TypeScript + Django/DRF + PostgreSQL architecture and existing API/data contracts; inspect the repository first; preserve existing working behavior; do not invent unresolved business rules—mark [DECISION REQUIRED]; do not modify unrelated files, add unnecessary dependencies, expose secrets, bypass authentication/store permissions, fabricate AI/ML results, or create autonomous actions. Out of scope for this task: Other modules, unrelated refactors, new dependencies, and unapproved features. Test requirement: Install/build/dev-server commands work; no console errors. Run the narrow relevant checks and report exact commands and outcomes. Expected output: focused implementation, meaningful tests, and concise notes on files changed, decisions, risks, and next dependency. Code quality: small readable changes, type/validation/error handling appropriate to the existing project, no duplicated business formulas, and no generated or sensitive data committed.

Expected Codex output: A focused change for SETUP-05, relevant tests, a file-change summary, and exact commands/results. No unrelated implementation.

How to inspect: Review the diff for these boundaries: Set up Vite and agreed styling dependencies only after checking compatibility; no feature screens. Confirm only expected files changed, validation/permissions match the contract, and tests exercise the requirement.

How to understand: Explain in your own words how Vite; TypeScript; component entry point; CSS pipeline. support this task; trace one normal case and one failure case through the code.

Run commands: Use verified environment commands from SETUP-07. Typical checks: backend: `python manage.py check` and the focused Django test module; frontend: `npm run lint`, focused test, and `npm run build`. Run only commands applicable to changed code and report exact outcomes.

Test steps / expected result: Install/build/dev-server commands work; no console errors. Success means the target is present, tests pass, and failure behavior is understandable.

Common errors: If the DB is unavailable, verify PostgreSQL service, database name, credentials, and env loading. If imports/routes fail, check app registration and URL inclusion. If an API/UI mismatch appears, compare against docs/api-contract.md and correct the contract or implementation deliberately; do not patch around it.

Git milestone: After review and passing tests, commit only this task. Suggested: `git add <reviewed-files> && git commit -m "SETUP-05: create react typescript frontend skeleton"`. Use a feature branch only when it helps isolate a risky/long feature; no empty commits.

Viva questions: 1. What requirement does SETUP-05 satisfy? 2. Which data/API/UI boundary does it change? 3. How is invalid or unauthorized input handled? 4. What test proves it works? 5. What limitation remains?

Definition of Done: ☐ Scope met  ☐ Code understood  ☐ Focused tests pass  ☐ No unrelated changes  ☐ Evidence recorded  ☐ Commit created  ☐ Docs updated if affected  ☐ Viva explanation ready

## SETUP-06 — Add safe environment configuration templates

Proposal lead / workstream assignment: Jointly assigned to Monira Islam and Rukaiya Akther Trisha — follows the proposal split; this is a planned role, not a contribution record.

Hands-on operator: Monira Islam (you) — you will carry out every task, including tasks assigned to the frontend/UI workstream.

Requirement: Database and LLM configuration must not leak credentials.

Target: Example environment files, validation notes, and secret-handling rules are documented.

Why this task matters: Example environment files, validation notes, and secret-handling rules are documented. It isolates one change so the student can inspect, test, and explain it before moving on.

Prerequisites: SETUP-05

Concepts to understand: Environment variables; server-only secrets; configuration validation.

Expected files/modules: backend/.env.example; frontend/.env.example; .gitignore; docs/setup.

Implementation scope: Add placeholder-only templates; fail clearly when required config is absent; never add real keys.

Not in this task: Other modules, unrelated refactors, new dependencies, and unapproved features.

Ready-to-paste Codex prompt

You are implementing SellerOS, the SE-331 standalone social-commerce seller BI/decision-support capstone. Implement only SETUP-06 — Add safe environment configuration templates. Requirement: Database and LLM configuration must not leak credentials. Objective/acceptance target: Example environment files, validation notes, and secret-handling rules are documented. Scope allowed: Add placeholder-only templates; fail clearly when required config is absent; never add real keys. Likely files/modules: backend/.env.example; frontend/.env.example; .gitignore; docs/setup. Prerequisites: SETUP-05. Constraints: follow the approved React/Vite/TypeScript + Django/DRF + PostgreSQL architecture and existing API/data contracts; inspect the repository first; preserve existing working behavior; do not invent unresolved business rules—mark [DECISION REQUIRED]; do not modify unrelated files, add unnecessary dependencies, expose secrets, bypass authentication/store permissions, fabricate AI/ML results, or create autonomous actions. Out of scope for this task: Other modules, unrelated refactors, new dependencies, and unapproved features. Test requirement: Secret scan and Git status show no credentials; app reports missing configuration clearly. Run the narrow relevant checks and report exact commands and outcomes. Expected output: focused implementation, meaningful tests, and concise notes on files changed, decisions, risks, and next dependency. Code quality: small readable changes, type/validation/error handling appropriate to the existing project, no duplicated business formulas, and no generated or sensitive data committed.

Expected Codex output: A focused change for SETUP-06, relevant tests, a file-change summary, and exact commands/results. No unrelated implementation.

How to inspect: Review the diff for these boundaries: Add placeholder-only templates; fail clearly when required config is absent; never add real keys. Confirm only expected files changed, validation/permissions match the contract, and tests exercise the requirement.

How to understand: Explain in your own words how Environment variables; server-only secrets; configuration validation. support this task; trace one normal case and one failure case through the code.

Run commands: Use verified environment commands from SETUP-07. Typical checks: backend: `python manage.py check` and the focused Django test module; frontend: `npm run lint`, focused test, and `npm run build`. Run only commands applicable to changed code and report exact outcomes.

Test steps / expected result: Secret scan and Git status show no credentials; app reports missing configuration clearly. Success means the target is present, tests pass, and failure behavior is understandable.

Common errors: If the DB is unavailable, verify PostgreSQL service, database name, credentials, and env loading. If imports/routes fail, check app registration and URL inclusion. If an API/UI mismatch appears, compare against docs/api-contract.md and correct the contract or implementation deliberately; do not patch around it.

Git milestone: After review and passing tests, commit only this task. Suggested: `git add <reviewed-files> && git commit -m "SETUP-06: add safe environment configuration templates"`. Use a feature branch only when it helps isolate a risky/long feature; no empty commits.

Viva questions: 1. What requirement does SETUP-06 satisfy? 2. Which data/API/UI boundary does it change? 3. How is invalid or unauthorized input handled? 4. What test proves it works? 5. What limitation remains?

Definition of Done: ☐ Scope met  ☐ Code understood  ☐ Focused tests pass  ☐ No unrelated changes  ☐ Evidence recorded  ☐ Commit created  ☐ Docs updated if affected  ☐ Viva explanation ready

## SETUP-07 — Write repeatable local setup and run instructions

Proposal lead / workstream assignment: Jointly assigned to Monira Islam and Rukaiya Akther Trisha — follows the proposal split; this is a planned role, not a contribution record.

Hands-on operator: Monira Islam (you) — you will carry out every task, including tasks assigned to the frontend/UI workstream.

Requirement: Both members must independently run and explain the application.

Target: README setup, migration, test, frontend, and shutdown commands are verified.

Why this task matters: README setup, migration, test, frontend, and shutdown commands are verified. It isolates one change so the student can inspect, test, and explain it before moving on.

Prerequisites: SETUP-06

Concepts to understand: Virtual environments; package installation; services; ports.

Expected files/modules: README.md; backend/README.md; frontend/README.md.

Implementation scope: Document commands for the confirmed environment; note database prerequisites.

Not in this task: Other modules, unrelated refactors, new dependencies, and unapproved features.

Ready-to-paste Codex prompt

You are implementing SellerOS, the SE-331 standalone social-commerce seller BI/decision-support capstone. Implement only SETUP-07 — Write repeatable local setup and run instructions. Requirement: Both members must independently run and explain the application. Objective/acceptance target: README setup, migration, test, frontend, and shutdown commands are verified. Scope allowed: Document commands for the confirmed environment; note database prerequisites. Likely files/modules: README.md; backend/README.md; frontend/README.md. Prerequisites: SETUP-06. Constraints: follow the approved React/Vite/TypeScript + Django/DRF + PostgreSQL architecture and existing API/data contracts; inspect the repository first; preserve existing working behavior; do not invent unresolved business rules—mark [DECISION REQUIRED]; do not modify unrelated files, add unnecessary dependencies, expose secrets, bypass authentication/store permissions, fabricate AI/ML results, or create autonomous actions. Out of scope for this task: Other modules, unrelated refactors, new dependencies, and unapproved features. Test requirement: A clean setup rehearsal succeeds from written instructions. Run the narrow relevant checks and report exact commands and outcomes. Expected output: focused implementation, meaningful tests, and concise notes on files changed, decisions, risks, and next dependency. Code quality: small readable changes, type/validation/error handling appropriate to the existing project, no duplicated business formulas, and no generated or sensitive data committed.

Expected Codex output: A focused change for SETUP-07, relevant tests, a file-change summary, and exact commands/results. No unrelated implementation.

How to inspect: Review the diff for these boundaries: Document commands for the confirmed environment; note database prerequisites. Confirm only expected files changed, validation/permissions match the contract, and tests exercise the requirement.

How to understand: Explain in your own words how Virtual environments; package installation; services; ports. support this task; trace one normal case and one failure case through the code.

Run commands: Use verified environment commands from SETUP-07. Typical checks: backend: `python manage.py check` and the focused Django test module; frontend: `npm run lint`, focused test, and `npm run build`. Run only commands applicable to changed code and report exact outcomes.

Test steps / expected result: A clean setup rehearsal succeeds from written instructions. Success means the target is present, tests pass, and failure behavior is understandable.

Common errors: If the DB is unavailable, verify PostgreSQL service, database name, credentials, and env loading. If imports/routes fail, check app registration and URL inclusion. If an API/UI mismatch appears, compare against docs/api-contract.md and correct the contract or implementation deliberately; do not patch around it.

Git milestone: After review and passing tests, commit only this task. Suggested: `git add <reviewed-files> && git commit -m "SETUP-07: write repeatable local setup and run instructions"`. Use a feature branch only when it helps isolate a risky/long feature; no empty commits.

Viva questions: 1. What requirement does SETUP-07 satisfy? 2. Which data/API/UI boundary does it change? 3. How is invalid or unauthorized input handled? 4. What test proves it works? 5. What limitation remains?

Definition of Done: ☐ Scope met  ☐ Code understood  ☐ Focused tests pass  ☐ No unrelated changes  ☐ Evidence recorded  ☐ Commit created  ☐ Docs updated if affected  ☐ Viva explanation ready

# Phase 2 — Backend, frontend, schema, and API contract

Agree the cross-layer vocabulary and error behavior before CRUD and feature screens diverge.

## BACKEND-01 — Configure Django settings by environment

Proposal lead / workstream assignment: Monira Islam — follows the proposal split; this is a planned role, not a contribution record.

Hands-on operator: Monira Islam (you) — you will carry out every task, including tasks assigned to the frontend/UI workstream.

Requirement: Development configuration must be repeatable and secrets protected.

Target: Settings load safely for local development and tests.

Why this task matters: Settings load safely for local development and tests. It isolates one change so the student can inspect, test, and explain it before moving on.

Prerequisites: None beyond repository inspection and the approved project baseline.

Concepts to understand: Settings modules; environment separation; secure defaults.

Expected files/modules: backend/config/settings; backend/core/config.

Implementation scope: Separate local/test settings as needed; configure allowed hosts, installed apps, timezone, static/media policy, and env validation.

Not in this task: Other modules, unrelated refactors, new dependencies, and unapproved features.

Ready-to-paste Codex prompt

You are implementing SellerOS, the SE-331 standalone social-commerce seller BI/decision-support capstone. Implement only BACKEND-01 — Configure Django settings by environment. Requirement: Development configuration must be repeatable and secrets protected. Objective/acceptance target: Settings load safely for local development and tests. Scope allowed: Separate local/test settings as needed; configure allowed hosts, installed apps, timezone, static/media policy, and env validation. Likely files/modules: backend/config/settings; backend/core/config. Prerequisites: none beyond the approved project baseline. Constraints: follow the approved React/Vite/TypeScript + Django/DRF + PostgreSQL architecture and existing API/data contracts; inspect the repository first; preserve existing working behavior; do not invent unresolved business rules—mark [DECISION REQUIRED]; do not modify unrelated files, add unnecessary dependencies, expose secrets, bypass authentication/store permissions, fabricate AI/ML results, or create autonomous actions. Out of scope for this task: Other modules, unrelated refactors, new dependencies, and unapproved features. Test requirement: Django system checks pass in local and test modes. Run the narrow relevant checks and report exact commands and outcomes. Expected output: focused implementation, meaningful tests, and concise notes on files changed, decisions, risks, and next dependency. Code quality: small readable changes, type/validation/error handling appropriate to the existing project, no duplicated business formulas, and no generated or sensitive data committed.

Expected Codex output: A focused change for BACKEND-01, relevant tests, a file-change summary, and exact commands/results. No unrelated implementation.

How to inspect: Review the diff for these boundaries: Separate local/test settings as needed; configure allowed hosts, installed apps, timezone, static/media policy, and env validation. Confirm only expected files changed, validation/permissions match the contract, and tests exercise the requirement.

How to understand: Explain in your own words how Settings modules; environment separation; secure defaults. support this task; trace one normal case and one failure case through the code.

Run commands: Use verified environment commands from SETUP-07. Typical checks: backend: `python manage.py check` and the focused Django test module; frontend: `npm run lint`, focused test, and `npm run build`. Run only commands applicable to changed code and report exact outcomes.

Test steps / expected result: Django system checks pass in local and test modes. Success means the target is present, tests pass, and failure behavior is understandable.

Common errors: If the DB is unavailable, verify PostgreSQL service, database name, credentials, and env loading. If imports/routes fail, check app registration and URL inclusion. If an API/UI mismatch appears, compare against docs/api-contract.md and correct the contract or implementation deliberately; do not patch around it.

Git milestone: After review and passing tests, commit only this task. Suggested: `git add <reviewed-files> && git commit -m "BACKEND-01: configure django settings by environment"`. Use a feature branch only when it helps isolate a risky/long feature; no empty commits.

Viva questions: 1. What requirement does BACKEND-01 satisfy? 2. Which data/API/UI boundary does it change? 3. How is invalid or unauthorized input handled? 4. What test proves it works? 5. What limitation remains?

Definition of Done: ☐ Scope met  ☐ Code understood  ☐ Focused tests pass  ☐ No unrelated changes  ☐ Evidence recorded  ☐ Commit created  ☐ Docs updated if affected  ☐ Viva explanation ready

## BACKEND-02 — Add Django REST Framework baseline

Proposal lead / workstream assignment: Monira Islam — follows the proposal split; this is a planned role, not a contribution record.

Hands-on operator: Monira Islam (you) — you will carry out every task, including tasks assigned to the frontend/UI workstream.

Requirement: SellerOS APIs require consistent serialization and validation.

Target: DRF is configured with a shared response/error convention.

Why this task matters: DRF is configured with a shared response/error convention. It isolates one change so the student can inspect, test, and explain it before moving on.

Prerequisites: BACKEND-01

Concepts to understand: Serializer; validation; HTTP status; error envelope.

Expected files/modules: backend/config/settings; backend/core/api.

Implementation scope: Configure only required DRF settings and a small error response handler.

Not in this task: Other modules, unrelated refactors, new dependencies, and unapproved features.

Ready-to-paste Codex prompt

You are implementing SellerOS, the SE-331 standalone social-commerce seller BI/decision-support capstone. Implement only BACKEND-02 — Add Django REST Framework baseline. Requirement: SellerOS APIs require consistent serialization and validation. Objective/acceptance target: DRF is configured with a shared response/error convention. Scope allowed: Configure only required DRF settings and a small error response handler. Likely files/modules: backend/config/settings; backend/core/api. Prerequisites: BACKEND-01. Constraints: follow the approved React/Vite/TypeScript + Django/DRF + PostgreSQL architecture and existing API/data contracts; inspect the repository first; preserve existing working behavior; do not invent unresolved business rules—mark [DECISION REQUIRED]; do not modify unrelated files, add unnecessary dependencies, expose secrets, bypass authentication/store permissions, fabricate AI/ML results, or create autonomous actions. Out of scope for this task: Other modules, unrelated refactors, new dependencies, and unapproved features. Test requirement: Tests cover validation and not-found response shape. Run the narrow relevant checks and report exact commands and outcomes. Expected output: focused implementation, meaningful tests, and concise notes on files changed, decisions, risks, and next dependency. Code quality: small readable changes, type/validation/error handling appropriate to the existing project, no duplicated business formulas, and no generated or sensitive data committed.

Expected Codex output: A focused change for BACKEND-02, relevant tests, a file-change summary, and exact commands/results. No unrelated implementation.

How to inspect: Review the diff for these boundaries: Configure only required DRF settings and a small error response handler. Confirm only expected files changed, validation/permissions match the contract, and tests exercise the requirement.

How to understand: Explain in your own words how Serializer; validation; HTTP status; error envelope. support this task; trace one normal case and one failure case through the code.

Run commands: Use verified environment commands from SETUP-07. Typical checks: backend: `python manage.py check` and the focused Django test module; frontend: `npm run lint`, focused test, and `npm run build`. Run only commands applicable to changed code and report exact outcomes.

Test steps / expected result: Tests cover validation and not-found response shape. Success means the target is present, tests pass, and failure behavior is understandable.

Common errors: If the DB is unavailable, verify PostgreSQL service, database name, credentials, and env loading. If imports/routes fail, check app registration and URL inclusion. If an API/UI mismatch appears, compare against docs/api-contract.md and correct the contract or implementation deliberately; do not patch around it.

Git milestone: After review and passing tests, commit only this task. Suggested: `git add <reviewed-files> && git commit -m "BACKEND-02: add django rest framework baseline"`. Use a feature branch only when it helps isolate a risky/long feature; no empty commits.

Viva questions: 1. What requirement does BACKEND-02 satisfy? 2. Which data/API/UI boundary does it change? 3. How is invalid or unauthorized input handled? 4. What test proves it works? 5. What limitation remains?

Definition of Done: ☐ Scope met  ☐ Code understood  ☐ Focused tests pass  ☐ No unrelated changes  ☐ Evidence recorded  ☐ Commit created  ☐ Docs updated if affected  ☐ Viva explanation ready

## BACKEND-03 — Add backend health and readiness checks

Proposal lead / workstream assignment: Monira Islam — follows the proposal split; this is a planned role, not a contribution record.

Hands-on operator: Monira Islam (you) — you will carry out every task, including tasks assigned to the frontend/UI workstream.

Requirement: Local setup and later deployment need visible service status.

Target: Health and dependency readiness routes distinguish app and database status.

Why this task matters: Health and dependency readiness routes distinguish app and database status. It isolates one change so the student can inspect, test, and explain it before moving on.

Prerequisites: BACKEND-02

Concepts to understand: Liveness vs readiness; safe diagnostics.

Expected files/modules: backend/core/health; URL config; tests.

Implementation scope: Implement minimal routes without exposing secrets or internal traces.

Not in this task: Other modules, unrelated refactors, new dependencies, and unapproved features.

Ready-to-paste Codex prompt

You are implementing SellerOS, the SE-331 standalone social-commerce seller BI/decision-support capstone. Implement only BACKEND-03 — Add backend health and readiness checks. Requirement: Local setup and later deployment need visible service status. Objective/acceptance target: Health and dependency readiness routes distinguish app and database status. Scope allowed: Implement minimal routes without exposing secrets or internal traces. Likely files/modules: backend/core/health; URL config; tests. Prerequisites: BACKEND-02. Constraints: follow the approved React/Vite/TypeScript + Django/DRF + PostgreSQL architecture and existing API/data contracts; inspect the repository first; preserve existing working behavior; do not invent unresolved business rules—mark [DECISION REQUIRED]; do not modify unrelated files, add unnecessary dependencies, expose secrets, bypass authentication/store permissions, fabricate AI/ML results, or create autonomous actions. Out of scope for this task: Other modules, unrelated refactors, new dependencies, and unapproved features. Test requirement: Health route returns documented status; failure does not leak configuration. Run the narrow relevant checks and report exact commands and outcomes. Expected output: focused implementation, meaningful tests, and concise notes on files changed, decisions, risks, and next dependency. Code quality: small readable changes, type/validation/error handling appropriate to the existing project, no duplicated business formulas, and no generated or sensitive data committed.

Expected Codex output: A focused change for BACKEND-03, relevant tests, a file-change summary, and exact commands/results. No unrelated implementation.

How to inspect: Review the diff for these boundaries: Implement minimal routes without exposing secrets or internal traces. Confirm only expected files changed, validation/permissions match the contract, and tests exercise the requirement.

How to understand: Explain in your own words how Liveness vs readiness; safe diagnostics. support this task; trace one normal case and one failure case through the code.

Run commands: Use verified environment commands from SETUP-07. Typical checks: backend: `python manage.py check` and the focused Django test module; frontend: `npm run lint`, focused test, and `npm run build`. Run only commands applicable to changed code and report exact outcomes.

Test steps / expected result: Health route returns documented status; failure does not leak configuration. Success means the target is present, tests pass, and failure behavior is understandable.

Common errors: If the DB is unavailable, verify PostgreSQL service, database name, credentials, and env loading. If imports/routes fail, check app registration and URL inclusion. If an API/UI mismatch appears, compare against docs/api-contract.md and correct the contract or implementation deliberately; do not patch around it.

Git milestone: After review and passing tests, commit only this task. Suggested: `git add <reviewed-files> && git commit -m "BACKEND-03: add backend health and readiness checks"`. Use a feature branch only when it helps isolate a risky/long feature; no empty commits.

Viva questions: 1. What requirement does BACKEND-03 satisfy? 2. Which data/API/UI boundary does it change? 3. How is invalid or unauthorized input handled? 4. What test proves it works? 5. What limitation remains?

Definition of Done: ☐ Scope met  ☐ Code understood  ☐ Focused tests pass  ☐ No unrelated changes  ☐ Evidence recorded  ☐ Commit created  ☐ Docs updated if affected  ☐ Viva explanation ready

## BACKEND-04 — Configure PostgreSQL development and test databases

Proposal lead / workstream assignment: Monira Islam — follows the proposal split; this is a planned role, not a contribution record.

Hands-on operator: Monira Islam (you) — you will carry out every task, including tasks assigned to the frontend/UI workstream.

Requirement: The approved storage layer is PostgreSQL.

Target: Application and tests connect to PostgreSQL using environment configuration.

Why this task matters: Application and tests connect to PostgreSQL using environment configuration. It isolates one change so the student can inspect, test, and explain it before moving on.

Prerequisites: BACKEND-03

Concepts to understand: PostgreSQL URL/credentials; migrations; test DB lifecycle.

Expected files/modules: backend/config/settings; docs/setup; test settings.

Implementation scope: Configure database access and test database behavior; do not silently substitute SQLite.

Not in this task: Other modules, unrelated refactors, new dependencies, and unapproved features.

Ready-to-paste Codex prompt

You are implementing SellerOS, the SE-331 standalone social-commerce seller BI/decision-support capstone. Implement only BACKEND-04 — Configure PostgreSQL development and test databases. Requirement: The approved storage layer is PostgreSQL. Objective/acceptance target: Application and tests connect to PostgreSQL using environment configuration. Scope allowed: Configure database access and test database behavior; do not silently substitute SQLite. Likely files/modules: backend/config/settings; docs/setup; test settings. Prerequisites: BACKEND-03. Constraints: follow the approved React/Vite/TypeScript + Django/DRF + PostgreSQL architecture and existing API/data contracts; inspect the repository first; preserve existing working behavior; do not invent unresolved business rules—mark [DECISION REQUIRED]; do not modify unrelated files, add unnecessary dependencies, expose secrets, bypass authentication/store permissions, fabricate AI/ML results, or create autonomous actions. Out of scope for this task: Other modules, unrelated refactors, new dependencies, and unapproved features. Test requirement: Connection and migration smoke checks pass. Run the narrow relevant checks and report exact commands and outcomes. Expected output: focused implementation, meaningful tests, and concise notes on files changed, decisions, risks, and next dependency. Code quality: small readable changes, type/validation/error handling appropriate to the existing project, no duplicated business formulas, and no generated or sensitive data committed.

Expected Codex output: A focused change for BACKEND-04, relevant tests, a file-change summary, and exact commands/results. No unrelated implementation.

How to inspect: Review the diff for these boundaries: Configure database access and test database behavior; do not silently substitute SQLite. Confirm only expected files changed, validation/permissions match the contract, and tests exercise the requirement.

How to understand: Explain in your own words how PostgreSQL URL/credentials; migrations; test DB lifecycle. support this task; trace one normal case and one failure case through the code.

Run commands: Use verified environment commands from SETUP-07. Typical checks: backend: `python manage.py check` and the focused Django test module; frontend: `npm run lint`, focused test, and `npm run build`. Run only commands applicable to changed code and report exact outcomes.

Test steps / expected result: Connection and migration smoke checks pass. Success means the target is present, tests pass, and failure behavior is understandable.

Common errors: If the DB is unavailable, verify PostgreSQL service, database name, credentials, and env loading. If imports/routes fail, check app registration and URL inclusion. If an API/UI mismatch appears, compare against docs/api-contract.md and correct the contract or implementation deliberately; do not patch around it.

Git milestone: After review and passing tests, commit only this task. Suggested: `git add <reviewed-files> && git commit -m "BACKEND-04: configure postgresql development and test databases"`. Use a feature branch only when it helps isolate a risky/long feature; no empty commits.

Viva questions: 1. What requirement does BACKEND-04 satisfy? 2. Which data/API/UI boundary does it change? 3. How is invalid or unauthorized input handled? 4. What test proves it works? 5. What limitation remains?

Definition of Done: ☐ Scope met  ☐ Code understood  ☐ Focused tests pass  ☐ No unrelated changes  ☐ Evidence recorded  ☐ Commit created  ☐ Docs updated if affected  ☐ Viva explanation ready

## BACKEND-05 — Define API conventions and error contract

Proposal lead / workstream assignment: Jointly assigned to Monira Islam and Rukaiya Akther Trisha — follows the proposal split; this is a planned role, not a contribution record.

Hands-on operator: Monira Islam (you) — you will carry out every task, including tasks assigned to the frontend/UI workstream.

Requirement: Frontend and backend need one agreed API contract.

Target: Version prefix, pagination, filtering, validation errors, permission errors, and response shapes are documented and tested.

Why this task matters: Version prefix, pagination, filtering, validation errors, permission errors, and response shapes are documented and tested. It isolates one change so the student can inspect, test, and explain it before moving on.

Prerequisites: BACKEND-04

Concepts to understand: REST; HTTP verbs/status; pagination; idempotency; error formats.

Expected files/modules: docs/api-contract.md; backend/core/api; frontend API types.

Implementation scope: Record endpoint naming and stable error fields; avoid building every endpoint here.

Not in this task: Other modules, unrelated refactors, new dependencies, and unapproved features.

Ready-to-paste Codex prompt

You are implementing SellerOS, the SE-331 standalone social-commerce seller BI/decision-support capstone. Implement only BACKEND-05 — Define API conventions and error contract. Requirement: Frontend and backend need one agreed API contract. Objective/acceptance target: Version prefix, pagination, filtering, validation errors, permission errors, and response shapes are documented and tested. Scope allowed: Record endpoint naming and stable error fields; avoid building every endpoint here. Likely files/modules: docs/api-contract.md; backend/core/api; frontend API types. Prerequisites: BACKEND-04. Constraints: follow the approved React/Vite/TypeScript + Django/DRF + PostgreSQL architecture and existing API/data contracts; inspect the repository first; preserve existing working behavior; do not invent unresolved business rules—mark [DECISION REQUIRED]; do not modify unrelated files, add unnecessary dependencies, expose secrets, bypass authentication/store permissions, fabricate AI/ML results, or create autonomous actions. Out of scope for this task: Other modules, unrelated refactors, new dependencies, and unapproved features. Test requirement: Contract examples can be consumed by frontend without guessing. Run the narrow relevant checks and report exact commands and outcomes. Expected output: focused implementation, meaningful tests, and concise notes on files changed, decisions, risks, and next dependency. Code quality: small readable changes, type/validation/error handling appropriate to the existing project, no duplicated business formulas, and no generated or sensitive data committed.

Expected Codex output: A focused change for BACKEND-05, relevant tests, a file-change summary, and exact commands/results. No unrelated implementation.

How to inspect: Review the diff for these boundaries: Record endpoint naming and stable error fields; avoid building every endpoint here. Confirm only expected files changed, validation/permissions match the contract, and tests exercise the requirement.

How to understand: Explain in your own words how REST; HTTP verbs/status; pagination; idempotency; error formats. support this task; trace one normal case and one failure case through the code.

Run commands: Use verified environment commands from SETUP-07. Typical checks: backend: `python manage.py check` and the focused Django test module; frontend: `npm run lint`, focused test, and `npm run build`. Run only commands applicable to changed code and report exact outcomes.

Test steps / expected result: Contract examples can be consumed by frontend without guessing. Success means the target is present, tests pass, and failure behavior is understandable.

Common errors: If the DB is unavailable, verify PostgreSQL service, database name, credentials, and env loading. If imports/routes fail, check app registration and URL inclusion. If an API/UI mismatch appears, compare against docs/api-contract.md and correct the contract or implementation deliberately; do not patch around it.

Git milestone: After review and passing tests, commit only this task. Suggested: `git add <reviewed-files> && git commit -m "BACKEND-05: define api conventions and error contract"`. Use a feature branch only when it helps isolate a risky/long feature; no empty commits.

Viva questions: 1. What requirement does BACKEND-05 satisfy? 2. Which data/API/UI boundary does it change? 3. How is invalid or unauthorized input handled? 4. What test proves it works? 5. What limitation remains?

Definition of Done: ☐ Scope met  ☐ Code understood  ☐ Focused tests pass  ☐ No unrelated changes  ☐ Evidence recorded  ☐ Commit created  ☐ Docs updated if affected  ☐ Viva explanation ready

## FRONTEND-01 — Create accessible application shell and routing

Proposal lead / workstream assignment: Rukaiya Akther Trisha — follows the proposal split; this is a planned role, not a contribution record.

Hands-on operator: Monira Islam (you) — you will carry out every task, including tasks assigned to the frontend/UI workstream.

Requirement: Feature pages need a consistent navigation shell.

Target: React app has agreed routes, layout, and accessible navigation placeholders.

Why this task matters: React app has agreed routes, layout, and accessible navigation placeholders. It isolates one change so the student can inspect, test, and explain it before moving on.

Prerequisites: SETUP-05

Concepts to understand: React routing; semantic HTML; accessibility basics.

Expected files/modules: frontend/src/app; routes; shared layout.

Implementation scope: Add shell, route placeholders, responsive layout, and not-found state only.

Not in this task: Other modules, unrelated refactors, new dependencies, and unapproved features.

Ready-to-paste Codex prompt

You are implementing SellerOS, the SE-331 standalone social-commerce seller BI/decision-support capstone. Implement only FRONTEND-01 — Create accessible application shell and routing. Requirement: Feature pages need a consistent navigation shell. Objective/acceptance target: React app has agreed routes, layout, and accessible navigation placeholders. Scope allowed: Add shell, route placeholders, responsive layout, and not-found state only. Likely files/modules: frontend/src/app; routes; shared layout. Prerequisites: SETUP-05. Constraints: follow the approved React/Vite/TypeScript + Django/DRF + PostgreSQL architecture and existing API/data contracts; inspect the repository first; preserve existing working behavior; do not invent unresolved business rules—mark [DECISION REQUIRED]; do not modify unrelated files, add unnecessary dependencies, expose secrets, bypass authentication/store permissions, fabricate AI/ML results, or create autonomous actions. Out of scope for this task: Other modules, unrelated refactors, new dependencies, and unapproved features. Test requirement: Route smoke tests; keyboard navigation of shell. Run the narrow relevant checks and report exact commands and outcomes. Expected output: focused implementation, meaningful tests, and concise notes on files changed, decisions, risks, and next dependency. Code quality: small readable changes, type/validation/error handling appropriate to the existing project, no duplicated business formulas, and no generated or sensitive data committed.

Expected Codex output: A focused change for FRONTEND-01, relevant tests, a file-change summary, and exact commands/results. No unrelated implementation.

How to inspect: Review the diff for these boundaries: Add shell, route placeholders, responsive layout, and not-found state only. Confirm only expected files changed, validation/permissions match the contract, and tests exercise the requirement.

How to understand: Explain in your own words how React routing; semantic HTML; accessibility basics. support this task; trace one normal case and one failure case through the code.

Run commands: Use verified environment commands from SETUP-07. Typical checks: backend: `python manage.py check` and the focused Django test module; frontend: `npm run lint`, focused test, and `npm run build`. Run only commands applicable to changed code and report exact outcomes.

Test steps / expected result: Route smoke tests; keyboard navigation of shell. Success means the target is present, tests pass, and failure behavior is understandable.

Common errors: If the DB is unavailable, verify PostgreSQL service, database name, credentials, and env loading. If imports/routes fail, check app registration and URL inclusion. If an API/UI mismatch appears, compare against docs/api-contract.md and correct the contract or implementation deliberately; do not patch around it.

Git milestone: After review and passing tests, commit only this task. Suggested: `git add <reviewed-files> && git commit -m "FRONTEND-01: create accessible application shell and routing"`. Use a feature branch only when it helps isolate a risky/long feature; no empty commits.

Viva questions: 1. What requirement does FRONTEND-01 satisfy? 2. Which data/API/UI boundary does it change? 3. How is invalid or unauthorized input handled? 4. What test proves it works? 5. What limitation remains?

Definition of Done: ☐ Scope met  ☐ Code understood  ☐ Focused tests pass  ☐ No unrelated changes  ☐ Evidence recorded  ☐ Commit created  ☐ Docs updated if affected  ☐ Viva explanation ready

## FRONTEND-02 — Create shared API client and error handling

Proposal lead / workstream assignment: Rukaiya Akther Trisha — follows the proposal split; this is a planned role, not a contribution record.

Hands-on operator: Monira Islam (you) — you will carry out every task, including tasks assigned to the frontend/UI workstream.

Requirement: Every screen must follow the backend contract.

Target: Frontend has a typed API client with common auth, error, loading, and request behavior.

Why this task matters: Frontend has a typed API client with common auth, error, loading, and request behavior. It isolates one change so the student can inspect, test, and explain it before moving on.

Prerequisites: BACKEND-05; SETUP-05

Concepts to understand: Fetch/client lifecycle; HTTP errors; TypeScript types.

Expected files/modules: frontend/src/api; shared types; tests.

Implementation scope: Implement transport layer from approved API contract; do not invent endpoints.

Not in this task: Other modules, unrelated refactors, new dependencies, and unapproved features.

Ready-to-paste Codex prompt

You are implementing SellerOS, the SE-331 standalone social-commerce seller BI/decision-support capstone. Implement only FRONTEND-02 — Create shared API client and error handling. Requirement: Every screen must follow the backend contract. Objective/acceptance target: Frontend has a typed API client with common auth, error, loading, and request behavior. Scope allowed: Implement transport layer from approved API contract; do not invent endpoints. Likely files/modules: frontend/src/api; shared types; tests. Prerequisites: BACKEND-05; SETUP-05. Constraints: follow the approved React/Vite/TypeScript + Django/DRF + PostgreSQL architecture and existing API/data contracts; inspect the repository first; preserve existing working behavior; do not invent unresolved business rules—mark [DECISION REQUIRED]; do not modify unrelated files, add unnecessary dependencies, expose secrets, bypass authentication/store permissions, fabricate AI/ML results, or create autonomous actions. Out of scope for this task: Other modules, unrelated refactors, new dependencies, and unapproved features. Test requirement: Unit tests cover success, validation error, auth error, network error. Run the narrow relevant checks and report exact commands and outcomes. Expected output: focused implementation, meaningful tests, and concise notes on files changed, decisions, risks, and next dependency. Code quality: small readable changes, type/validation/error handling appropriate to the existing project, no duplicated business formulas, and no generated or sensitive data committed.

Expected Codex output: A focused change for FRONTEND-02, relevant tests, a file-change summary, and exact commands/results. No unrelated implementation.

How to inspect: Review the diff for these boundaries: Implement transport layer from approved API contract; do not invent endpoints. Confirm only expected files changed, validation/permissions match the contract, and tests exercise the requirement.

How to understand: Explain in your own words how Fetch/client lifecycle; HTTP errors; TypeScript types. support this task; trace one normal case and one failure case through the code.

Run commands: Use verified environment commands from SETUP-07. Typical checks: backend: `python manage.py check` and the focused Django test module; frontend: `npm run lint`, focused test, and `npm run build`. Run only commands applicable to changed code and report exact outcomes.

Test steps / expected result: Unit tests cover success, validation error, auth error, network error. Success means the target is present, tests pass, and failure behavior is understandable.

Common errors: If the DB is unavailable, verify PostgreSQL service, database name, credentials, and env loading. If imports/routes fail, check app registration and URL inclusion. If an API/UI mismatch appears, compare against docs/api-contract.md and correct the contract or implementation deliberately; do not patch around it.

Git milestone: After review and passing tests, commit only this task. Suggested: `git add <reviewed-files> && git commit -m "FRONTEND-02: create shared api client and error handling"`. Use a feature branch only when it helps isolate a risky/long feature; no empty commits.

Viva questions: 1. What requirement does FRONTEND-02 satisfy? 2. Which data/API/UI boundary does it change? 3. How is invalid or unauthorized input handled? 4. What test proves it works? 5. What limitation remains?

Definition of Done: ☐ Scope met  ☐ Code understood  ☐ Focused tests pass  ☐ No unrelated changes  ☐ Evidence recorded  ☐ Commit created  ☐ Docs updated if affected  ☐ Viva explanation ready

## FRONTEND-03 — Create reusable form and status primitives

Proposal lead / workstream assignment: Rukaiya Akther Trisha — follows the proposal split; this is a planned role, not a contribution record.

Hands-on operator: Monira Islam (you) — you will carry out every task, including tasks assigned to the frontend/UI workstream.

Requirement: CRUD screens need predictable accessible feedback.

Target: Shared form fields, confirmation, loading, empty, and error components are available.

Why this task matters: Shared form fields, confirmation, loading, empty, and error components are available. It isolates one change so the student can inspect, test, and explain it before moving on.

Prerequisites: FRONTEND-01

Concepts to understand: Controlled inputs; labels; focus; status announcement.

Expected files/modules: frontend/src/components; frontend tests.

Implementation scope: Build only reusable primitives tied to accessibility and agreed design system.

Not in this task: Other modules, unrelated refactors, new dependencies, and unapproved features.

Ready-to-paste Codex prompt

You are implementing SellerOS, the SE-331 standalone social-commerce seller BI/decision-support capstone. Implement only FRONTEND-03 — Create reusable form and status primitives. Requirement: CRUD screens need predictable accessible feedback. Objective/acceptance target: Shared form fields, confirmation, loading, empty, and error components are available. Scope allowed: Build only reusable primitives tied to accessibility and agreed design system. Likely files/modules: frontend/src/components; frontend tests. Prerequisites: FRONTEND-01. Constraints: follow the approved React/Vite/TypeScript + Django/DRF + PostgreSQL architecture and existing API/data contracts; inspect the repository first; preserve existing working behavior; do not invent unresolved business rules—mark [DECISION REQUIRED]; do not modify unrelated files, add unnecessary dependencies, expose secrets, bypass authentication/store permissions, fabricate AI/ML results, or create autonomous actions. Out of scope for this task: Other modules, unrelated refactors, new dependencies, and unapproved features. Test requirement: Component tests verify validation and keyboard behavior. Run the narrow relevant checks and report exact commands and outcomes. Expected output: focused implementation, meaningful tests, and concise notes on files changed, decisions, risks, and next dependency. Code quality: small readable changes, type/validation/error handling appropriate to the existing project, no duplicated business formulas, and no generated or sensitive data committed.

Expected Codex output: A focused change for FRONTEND-03, relevant tests, a file-change summary, and exact commands/results. No unrelated implementation.

How to inspect: Review the diff for these boundaries: Build only reusable primitives tied to accessibility and agreed design system. Confirm only expected files changed, validation/permissions match the contract, and tests exercise the requirement.

How to understand: Explain in your own words how Controlled inputs; labels; focus; status announcement. support this task; trace one normal case and one failure case through the code.

Run commands: Use verified environment commands from SETUP-07. Typical checks: backend: `python manage.py check` and the focused Django test module; frontend: `npm run lint`, focused test, and `npm run build`. Run only commands applicable to changed code and report exact outcomes.

Test steps / expected result: Component tests verify validation and keyboard behavior. Success means the target is present, tests pass, and failure behavior is understandable.

Common errors: If the DB is unavailable, verify PostgreSQL service, database name, credentials, and env loading. If imports/routes fail, check app registration and URL inclusion. If an API/UI mismatch appears, compare against docs/api-contract.md and correct the contract or implementation deliberately; do not patch around it.

Git milestone: After review and passing tests, commit only this task. Suggested: `git add <reviewed-files> && git commit -m "FRONTEND-03: create reusable form and status primitives"`. Use a feature branch only when it helps isolate a risky/long feature; no empty commits.

Viva questions: 1. What requirement does FRONTEND-03 satisfy? 2. Which data/API/UI boundary does it change? 3. How is invalid or unauthorized input handled? 4. What test proves it works? 5. What limitation remains?

Definition of Done: ☐ Scope met  ☐ Code understood  ☐ Focused tests pass  ☐ No unrelated changes  ☐ Evidence recorded  ☐ Commit created  ☐ Docs updated if affected  ☐ Viva explanation ready

## DB-01 — Create and review SellerOS entity relationship design

Proposal lead / workstream assignment: Jointly assigned to Monira Islam and Rukaiya Akther Trisha — follows the proposal split; this is a planned role, not a contribution record.

Hands-on operator: Monira Islam (you) — you will carry out every task, including tasks assigned to the frontend/UI workstream.

Requirement: Models must preserve store ownership and linked operational history.

Target: ERD covers account/store, products/variants, inventory movements, customers, orders/items, expenses, and analysis logs.

Why this task matters: ERD covers account/store, products/variants, inventory movements, customers, orders/items, expenses, and analysis logs. It isolates one change so the student can inspect, test, and explain it before moving on.

Prerequisites: FRONTEND-03

Concepts to understand: Relational modeling; keys; constraints; cardinality.

Expected files/modules: docs/erd.md or editable diagram source.

Implementation scope: Use proposal scope and decisions; show optionality, keys, uniqueness, and delete behavior.

Not in this task: Other modules, unrelated refactors, new dependencies, and unapproved features.

Ready-to-paste Codex prompt

You are implementing SellerOS, the SE-331 standalone social-commerce seller BI/decision-support capstone. Implement only DB-01 — Create and review SellerOS entity relationship design. Requirement: Models must preserve store ownership and linked operational history. Objective/acceptance target: ERD covers account/store, products/variants, inventory movements, customers, orders/items, expenses, and analysis logs. Scope allowed: Use proposal scope and decisions; show optionality, keys, uniqueness, and delete behavior. Likely files/modules: docs/erd.md or editable diagram source. Prerequisites: FRONTEND-03. Constraints: follow the approved React/Vite/TypeScript + Django/DRF + PostgreSQL architecture and existing API/data contracts; inspect the repository first; preserve existing working behavior; do not invent unresolved business rules—mark [DECISION REQUIRED]; do not modify unrelated files, add unnecessary dependencies, expose secrets, bypass authentication/store permissions, fabricate AI/ML results, or create autonomous actions. Out of scope for this task: Other modules, unrelated refactors, new dependencies, and unapproved features. Test requirement: Both members can explain all relationships; unresolved fields tagged. Run the narrow relevant checks and report exact commands and outcomes. Expected output: focused implementation, meaningful tests, and concise notes on files changed, decisions, risks, and next dependency. Code quality: small readable changes, type/validation/error handling appropriate to the existing project, no duplicated business formulas, and no generated or sensitive data committed.

Expected Codex output: A focused change for DB-01, relevant tests, a file-change summary, and exact commands/results. No unrelated implementation.

How to inspect: Review the diff for these boundaries: Use proposal scope and decisions; show optionality, keys, uniqueness, and delete behavior. Confirm only expected files changed, validation/permissions match the contract, and tests exercise the requirement.

How to understand: Explain in your own words how Relational modeling; keys; constraints; cardinality. support this task; trace one normal case and one failure case through the code.

Run commands: Use verified environment commands from SETUP-07. Typical checks: backend: `python manage.py check` and the focused Django test module; frontend: `npm run lint`, focused test, and `npm run build`. Run only commands applicable to changed code and report exact outcomes.

Test steps / expected result: Both members can explain all relationships; unresolved fields tagged. Success means the target is present, tests pass, and failure behavior is understandable.

Common errors: If the DB is unavailable, verify PostgreSQL service, database name, credentials, and env loading. If imports/routes fail, check app registration and URL inclusion. If an API/UI mismatch appears, compare against docs/api-contract.md and correct the contract or implementation deliberately; do not patch around it.

Git milestone: After review and passing tests, commit only this task. Suggested: `git add <reviewed-files> && git commit -m "DB-01: create and review selleros entity relationship design"`. Use a feature branch only when it helps isolate a risky/long feature; no empty commits.

Viva questions: 1. What requirement does DB-01 satisfy? 2. Which data/API/UI boundary does it change? 3. How is invalid or unauthorized input handled? 4. What test proves it works? 5. What limitation remains?

Definition of Done: ☐ Scope met  ☐ Code understood  ☐ Focused tests pass  ☐ No unrelated changes  ☐ Evidence recorded  ☐ Commit created  ☐ Docs updated if affected  ☐ Viva explanation ready

## DB-02 — Define field-level data dictionary and constraints

Proposal lead / workstream assignment: Jointly assigned to Monira Islam and Rukaiya Akther Trisha — follows the proposal split; this is a planned role, not a contribution record.

Hands-on operator: Monira Islam (you) — you will carry out every task, including tasks assigned to the frontend/UI workstream.

Requirement: API and database names need a shared contract.

Target: Data dictionary defines each field, type, nullable rule, units, validation, and ownership.

Why this task matters: Data dictionary defines each field, type, nullable rule, units, validation, and ownership. It isolates one change so the student can inspect, test, and explain it before moving on.

Prerequisites: DB-01

Concepts to understand: Nullability; precision; indexes; soft delete; units.

Expected files/modules: docs/data-dictionary.md.

Implementation scope: Only fields needed by proposal; avoid speculative schema expansion.

Not in this task: Other modules, unrelated refactors, new dependencies, and unapproved features.

Ready-to-paste Codex prompt

You are implementing SellerOS, the SE-331 standalone social-commerce seller BI/decision-support capstone. Implement only DB-02 — Define field-level data dictionary and constraints. Requirement: API and database names need a shared contract. Objective/acceptance target: Data dictionary defines each field, type, nullable rule, units, validation, and ownership. Scope allowed: Only fields needed by proposal; avoid speculative schema expansion. Likely files/modules: docs/data-dictionary.md. Prerequisites: DB-01. Constraints: follow the approved React/Vite/TypeScript + Django/DRF + PostgreSQL architecture and existing API/data contracts; inspect the repository first; preserve existing working behavior; do not invent unresolved business rules—mark [DECISION REQUIRED]; do not modify unrelated files, add unnecessary dependencies, expose secrets, bypass authentication/store permissions, fabricate AI/ML results, or create autonomous actions. Out of scope for this task: Other modules, unrelated refactors, new dependencies, and unapproved features. Test requirement: ERD, API contract, and dictionary agree. Run the narrow relevant checks and report exact commands and outcomes. Expected output: focused implementation, meaningful tests, and concise notes on files changed, decisions, risks, and next dependency. Code quality: small readable changes, type/validation/error handling appropriate to the existing project, no duplicated business formulas, and no generated or sensitive data committed.

Expected Codex output: A focused change for DB-02, relevant tests, a file-change summary, and exact commands/results. No unrelated implementation.

How to inspect: Review the diff for these boundaries: Only fields needed by proposal; avoid speculative schema expansion. Confirm only expected files changed, validation/permissions match the contract, and tests exercise the requirement.

How to understand: Explain in your own words how Nullability; precision; indexes; soft delete; units. support this task; trace one normal case and one failure case through the code.

Run commands: Use verified environment commands from SETUP-07. Typical checks: backend: `python manage.py check` and the focused Django test module; frontend: `npm run lint`, focused test, and `npm run build`. Run only commands applicable to changed code and report exact outcomes.

Test steps / expected result: ERD, API contract, and dictionary agree. Success means the target is present, tests pass, and failure behavior is understandable.

Common errors: If the DB is unavailable, verify PostgreSQL service, database name, credentials, and env loading. If imports/routes fail, check app registration and URL inclusion. If an API/UI mismatch appears, compare against docs/api-contract.md and correct the contract or implementation deliberately; do not patch around it.

Git milestone: After review and passing tests, commit only this task. Suggested: `git add <reviewed-files> && git commit -m "DB-02: define field-level data dictionary and constraints"`. Use a feature branch only when it helps isolate a risky/long feature; no empty commits.

Viva questions: 1. What requirement does DB-02 satisfy? 2. Which data/API/UI boundary does it change? 3. How is invalid or unauthorized input handled? 4. What test proves it works? 5. What limitation remains?

Definition of Done: ☐ Scope met  ☐ Code understood  ☐ Focused tests pass  ☐ No unrelated changes  ☐ Evidence recorded  ☐ Commit created  ☐ Docs updated if affected  ☐ Viva explanation ready

## DB-03 — Implement core account and store models

Proposal lead / workstream assignment: Monira Islam — follows the proposal split; this is a planned role, not a contribution record.

Hands-on operator: Monira Islam (you) — you will carry out every task, including tasks assigned to the frontend/UI workstream.

Requirement: Business data must belong to an authorized store.

Target: Account/store entities and approved membership relation exist with migrations.

Why this task matters: Account/store entities and approved membership relation exist with migrations. It isolates one change so the student can inspect, test, and explain it before moving on.

Prerequisites: DB-02

Concepts to understand: Django models; foreign keys; unique constraints.

Expected files/modules: backend/apps/accounts/models; migrations; model tests.

Implementation scope: Implement only fields approved in PLAN-04 and DB-02.

Not in this task: Other modules, unrelated refactors, new dependencies, and unapproved features.

Ready-to-paste Codex prompt

You are implementing SellerOS, the SE-331 standalone social-commerce seller BI/decision-support capstone. Implement only DB-03 — Implement core account and store models. Requirement: Business data must belong to an authorized store. Objective/acceptance target: Account/store entities and approved membership relation exist with migrations. Scope allowed: Implement only fields approved in PLAN-04 and DB-02. Likely files/modules: backend/apps/accounts/models; migrations; model tests. Prerequisites: DB-02. Constraints: follow the approved React/Vite/TypeScript + Django/DRF + PostgreSQL architecture and existing API/data contracts; inspect the repository first; preserve existing working behavior; do not invent unresolved business rules—mark [DECISION REQUIRED]; do not modify unrelated files, add unnecessary dependencies, expose secrets, bypass authentication/store permissions, fabricate AI/ML results, or create autonomous actions. Out of scope for this task: Other modules, unrelated refactors, new dependencies, and unapproved features. Test requirement: Migrations apply on clean PostgreSQL; ownership tests pass. Run the narrow relevant checks and report exact commands and outcomes. Expected output: focused implementation, meaningful tests, and concise notes on files changed, decisions, risks, and next dependency. Code quality: small readable changes, type/validation/error handling appropriate to the existing project, no duplicated business formulas, and no generated or sensitive data committed.

Expected Codex output: A focused change for DB-03, relevant tests, a file-change summary, and exact commands/results. No unrelated implementation.

How to inspect: Review the diff for these boundaries: Implement only fields approved in PLAN-04 and DB-02. Confirm only expected files changed, validation/permissions match the contract, and tests exercise the requirement.

How to understand: Explain in your own words how Django models; foreign keys; unique constraints. support this task; trace one normal case and one failure case through the code.

Run commands: Use verified environment commands from SETUP-07. Typical checks: backend: `python manage.py check` and the focused Django test module; frontend: `npm run lint`, focused test, and `npm run build`. Run only commands applicable to changed code and report exact outcomes.

Test steps / expected result: Migrations apply on clean PostgreSQL; ownership tests pass. Success means the target is present, tests pass, and failure behavior is understandable.

Common errors: If the DB is unavailable, verify PostgreSQL service, database name, credentials, and env loading. If imports/routes fail, check app registration and URL inclusion. If an API/UI mismatch appears, compare against docs/api-contract.md and correct the contract or implementation deliberately; do not patch around it.

Git milestone: After review and passing tests, commit only this task. Suggested: `git add <reviewed-files> && git commit -m "DB-03: implement core account and store models"`. Use a feature branch only when it helps isolate a risky/long feature; no empty commits.

Viva questions: 1. What requirement does DB-03 satisfy? 2. Which data/API/UI boundary does it change? 3. How is invalid or unauthorized input handled? 4. What test proves it works? 5. What limitation remains?

Definition of Done: ☐ Scope met  ☐ Code understood  ☐ Focused tests pass  ☐ No unrelated changes  ☐ Evidence recorded  ☐ Commit created  ☐ Docs updated if affected  ☐ Viva explanation ready

## DB-04 — Add migration and database constraint checks

Proposal lead / workstream assignment: Monira Islam — follows the proposal split; this is a planned role, not a contribution record.

Hands-on operator: Monira Islam (you) — you will carry out every task, including tasks assigned to the frontend/UI workstream.

Requirement: Schema changes must be reproducible and protect invariants.

Target: Initial migrations and constraint tests are stable.

Why this task matters: Initial migrations and constraint tests are stable. It isolates one change so the student can inspect, test, and explain it before moving on.

Prerequisites: DB-03

Concepts to understand: Django migrations; uniqueness; check constraints.

Expected files/modules: backend/apps/*/migrations; tests.

Implementation scope: Review generated migration; add justified DB constraints and migration smoke tests.

Not in this task: Other modules, unrelated refactors, new dependencies, and unapproved features.

Ready-to-paste Codex prompt

You are implementing SellerOS, the SE-331 standalone social-commerce seller BI/decision-support capstone. Implement only DB-04 — Add migration and database constraint checks. Requirement: Schema changes must be reproducible and protect invariants. Objective/acceptance target: Initial migrations and constraint tests are stable. Scope allowed: Review generated migration; add justified DB constraints and migration smoke tests. Likely files/modules: backend/apps/*/migrations; tests. Prerequisites: DB-03. Constraints: follow the approved React/Vite/TypeScript + Django/DRF + PostgreSQL architecture and existing API/data contracts; inspect the repository first; preserve existing working behavior; do not invent unresolved business rules—mark [DECISION REQUIRED]; do not modify unrelated files, add unnecessary dependencies, expose secrets, bypass authentication/store permissions, fabricate AI/ML results, or create autonomous actions. Out of scope for this task: Other modules, unrelated refactors, new dependencies, and unapproved features. Test requirement: Fresh DB migration and rollback/reapply workflow works. Run the narrow relevant checks and report exact commands and outcomes. Expected output: focused implementation, meaningful tests, and concise notes on files changed, decisions, risks, and next dependency. Code quality: small readable changes, type/validation/error handling appropriate to the existing project, no duplicated business formulas, and no generated or sensitive data committed.

Expected Codex output: A focused change for DB-04, relevant tests, a file-change summary, and exact commands/results. No unrelated implementation.

How to inspect: Review the diff for these boundaries: Review generated migration; add justified DB constraints and migration smoke tests. Confirm only expected files changed, validation/permissions match the contract, and tests exercise the requirement.

How to understand: Explain in your own words how Django migrations; uniqueness; check constraints. support this task; trace one normal case and one failure case through the code.

Run commands: Use verified environment commands from SETUP-07. Typical checks: backend: `python manage.py check` and the focused Django test module; frontend: `npm run lint`, focused test, and `npm run build`. Run only commands applicable to changed code and report exact outcomes.

Test steps / expected result: Fresh DB migration and rollback/reapply workflow works. Success means the target is present, tests pass, and failure behavior is understandable.

Common errors: If the DB is unavailable, verify PostgreSQL service, database name, credentials, and env loading. If imports/routes fail, check app registration and URL inclusion. If an API/UI mismatch appears, compare against docs/api-contract.md and correct the contract or implementation deliberately; do not patch around it.

Git milestone: After review and passing tests, commit only this task. Suggested: `git add <reviewed-files> && git commit -m "DB-04: add migration and database constraint checks"`. Use a feature branch only when it helps isolate a risky/long feature; no empty commits.

Viva questions: 1. What requirement does DB-04 satisfy? 2. Which data/API/UI boundary does it change? 3. How is invalid or unauthorized input handled? 4. What test proves it works? 5. What limitation remains?

Definition of Done: ☐ Scope met  ☐ Code understood  ☐ Focused tests pass  ☐ No unrelated changes  ☐ Evidence recorded  ☐ Commit created  ☐ Docs updated if affected  ☐ Viva explanation ready

## DB-05 — Create shared test factories and test conventions

Proposal lead / workstream assignment: Jointly assigned to Monira Islam and Rukaiya Akther Trisha — follows the proposal split; this is a planned role, not a contribution record.

Hands-on operator: Monira Islam (you) — you will carry out every task, including tasks assigned to the frontend/UI workstream.

Requirement: Feature tests need consistent, isolated records.

Target: Test factories/builders create related store-owned records deterministically.

Why this task matters: Test factories/builders create related store-owned records deterministically. It isolates one change so the student can inspect, test, and explain it before moving on.

Prerequisites: DB-04

Concepts to understand: Factories; isolation; deterministic tests.

Expected files/modules: backend/tests/factories; frontend test helpers; docs/testing.

Implementation scope: Use synthetic fixtures; no customer names or credentials from real users.

Not in this task: Other modules, unrelated refactors, new dependencies, and unapproved features.

Ready-to-paste Codex prompt

You are implementing SellerOS, the SE-331 standalone social-commerce seller BI/decision-support capstone. Implement only DB-05 — Create shared test factories and test conventions. Requirement: Feature tests need consistent, isolated records. Objective/acceptance target: Test factories/builders create related store-owned records deterministically. Scope allowed: Use synthetic fixtures; no customer names or credentials from real users. Likely files/modules: backend/tests/factories; frontend test helpers; docs/testing. Prerequisites: DB-04. Constraints: follow the approved React/Vite/TypeScript + Django/DRF + PostgreSQL architecture and existing API/data contracts; inspect the repository first; preserve existing working behavior; do not invent unresolved business rules—mark [DECISION REQUIRED]; do not modify unrelated files, add unnecessary dependencies, expose secrets, bypass authentication/store permissions, fabricate AI/ML results, or create autonomous actions. Out of scope for this task: Other modules, unrelated refactors, new dependencies, and unapproved features. Test requirement: Factories generate valid core graph; test data is reproducible. Run the narrow relevant checks and report exact commands and outcomes. Expected output: focused implementation, meaningful tests, and concise notes on files changed, decisions, risks, and next dependency. Code quality: small readable changes, type/validation/error handling appropriate to the existing project, no duplicated business formulas, and no generated or sensitive data committed.

Expected Codex output: A focused change for DB-05, relevant tests, a file-change summary, and exact commands/results. No unrelated implementation.

How to inspect: Review the diff for these boundaries: Use synthetic fixtures; no customer names or credentials from real users. Confirm only expected files changed, validation/permissions match the contract, and tests exercise the requirement.

How to understand: Explain in your own words how Factories; isolation; deterministic tests. support this task; trace one normal case and one failure case through the code.

Run commands: Use verified environment commands from SETUP-07. Typical checks: backend: `python manage.py check` and the focused Django test module; frontend: `npm run lint`, focused test, and `npm run build`. Run only commands applicable to changed code and report exact outcomes.

Test steps / expected result: Factories generate valid core graph; test data is reproducible. Success means the target is present, tests pass, and failure behavior is understandable.

Common errors: If the DB is unavailable, verify PostgreSQL service, database name, credentials, and env loading. If imports/routes fail, check app registration and URL inclusion. If an API/UI mismatch appears, compare against docs/api-contract.md and correct the contract or implementation deliberately; do not patch around it.

Git milestone: After review and passing tests, commit only this task. Suggested: `git add <reviewed-files> && git commit -m "DB-05: create shared test factories and test conventions"`. Use a feature branch only when it helps isolate a risky/long feature; no empty commits.

Viva questions: 1. What requirement does DB-05 satisfy? 2. Which data/API/UI boundary does it change? 3. How is invalid or unauthorized input handled? 4. What test proves it works? 5. What limitation remains?

Definition of Done: ☐ Scope met  ☐ Code understood  ☐ Focused tests pass  ☐ No unrelated changes  ☐ Evidence recorded  ☐ Commit created  ☐ Docs updated if affected  ☐ Viva explanation ready

# Phase 3 — Authentication and store isolation

Secure each request before product data is exposed.

## AUTH-01 — Implement registration and login API

Proposal lead / workstream assignment: Monira Islam — follows the proposal split; this is a planned role, not a contribution record.

Hands-on operator: Monira Islam (you) — you will carry out every task, including tasks assigned to the frontend/UI workstream.

Requirement: The proposal includes seller account access.

Target: Approved authentication flow issues and validates user sessions/tokens safely.

Why this task matters: Approved authentication flow issues and validates user sessions/tokens safely. It isolates one change so the student can inspect, test, and explain it before moving on.

Prerequisites: None beyond repository inspection and the approved project baseline.

Concepts to understand: Authentication vs authorization; password hashing; CSRF/token basics.

Expected files/modules: backend/apps/accounts/api; serializers; tests.

Implementation scope: Use a maintained framework-supported approach; rate/validation rules are documented.

Not in this task: Other modules, unrelated refactors, new dependencies, and unapproved features.

Ready-to-paste Codex prompt

You are implementing SellerOS, the SE-331 standalone social-commerce seller BI/decision-support capstone. Implement only AUTH-01 — Implement registration and login API. Requirement: The proposal includes seller account access. Objective/acceptance target: Approved authentication flow issues and validates user sessions/tokens safely. Scope allowed: Use a maintained framework-supported approach; rate/validation rules are documented. Likely files/modules: backend/apps/accounts/api; serializers; tests. Prerequisites: none beyond the approved project baseline. Constraints: follow the approved React/Vite/TypeScript + Django/DRF + PostgreSQL architecture and existing API/data contracts; inspect the repository first; preserve existing working behavior; do not invent unresolved business rules—mark [DECISION REQUIRED]; do not modify unrelated files, add unnecessary dependencies, expose secrets, bypass authentication/store permissions, fabricate AI/ML results, or create autonomous actions. Out of scope for this task: Other modules, unrelated refactors, new dependencies, and unapproved features. Test requirement: Success, invalid credentials, duplicate account, and unauthenticated cases pass. Run the narrow relevant checks and report exact commands and outcomes. Expected output: focused implementation, meaningful tests, and concise notes on files changed, decisions, risks, and next dependency. Code quality: small readable changes, type/validation/error handling appropriate to the existing project, no duplicated business formulas, and no generated or sensitive data committed.

Expected Codex output: A focused change for AUTH-01, relevant tests, a file-change summary, and exact commands/results. No unrelated implementation.

How to inspect: Review the diff for these boundaries: Use a maintained framework-supported approach; rate/validation rules are documented. Confirm only expected files changed, validation/permissions match the contract, and tests exercise the requirement.

How to understand: Explain in your own words how Authentication vs authorization; password hashing; CSRF/token basics. support this task; trace one normal case and one failure case through the code.

Run commands: Use verified environment commands from SETUP-07. Typical checks: backend: `python manage.py check` and the focused Django test module; frontend: `npm run lint`, focused test, and `npm run build`. Run only commands applicable to changed code and report exact outcomes.

Test steps / expected result: Success, invalid credentials, duplicate account, and unauthenticated cases pass. Success means the target is present, tests pass, and failure behavior is understandable.

Common errors: If the DB is unavailable, verify PostgreSQL service, database name, credentials, and env loading. If imports/routes fail, check app registration and URL inclusion. If an API/UI mismatch appears, compare against docs/api-contract.md and correct the contract or implementation deliberately; do not patch around it.

Git milestone: After review and passing tests, commit only this task. Suggested: `git add <reviewed-files> && git commit -m "AUTH-01: implement registration and login api"`. Use a feature branch only when it helps isolate a risky/long feature; no empty commits.

Viva questions: 1. What requirement does AUTH-01 satisfy? 2. Which data/API/UI boundary does it change? 3. How is invalid or unauthorized input handled? 4. What test proves it works? 5. What limitation remains?

Definition of Done: ☐ Scope met  ☐ Code understood  ☐ Focused tests pass  ☐ No unrelated changes  ☐ Evidence recorded  ☐ Commit created  ☐ Docs updated if affected  ☐ Viva explanation ready

## AUTH-02 — Implement store profile create and read API

Proposal lead / workstream assignment: Monira Islam — follows the proposal split; this is a planned role, not a contribution record.

Hands-on operator: Monira Islam (you) — you will carry out every task, including tasks assigned to the frontend/UI workstream.

Requirement: A seller workspace provides the scope for records.

Target: Authorized account can create/read only permitted store profile data.

Why this task matters: Authorized account can create/read only permitted store profile data. It isolates one change so the student can inspect, test, and explain it before moving on.

Prerequisites: AUTH-01

Concepts to understand: Ownership; CRUD; serializer validation.

Expected files/modules: backend/apps/stores/models; serializers; views; URLs; tests.

Implementation scope: Follow PLAN-04; implement minimum profile fields.

Not in this task: Other modules, unrelated refactors, new dependencies, and unapproved features.

Ready-to-paste Codex prompt

You are implementing SellerOS, the SE-331 standalone social-commerce seller BI/decision-support capstone. Implement only AUTH-02 — Implement store profile create and read API. Requirement: A seller workspace provides the scope for records. Objective/acceptance target: Authorized account can create/read only permitted store profile data. Scope allowed: Follow PLAN-04; implement minimum profile fields. Likely files/modules: backend/apps/stores/models; serializers; views; URLs; tests. Prerequisites: AUTH-01. Constraints: follow the approved React/Vite/TypeScript + Django/DRF + PostgreSQL architecture and existing API/data contracts; inspect the repository first; preserve existing working behavior; do not invent unresolved business rules—mark [DECISION REQUIRED]; do not modify unrelated files, add unnecessary dependencies, expose secrets, bypass authentication/store permissions, fabricate AI/ML results, or create autonomous actions. Out of scope for this task: Other modules, unrelated refactors, new dependencies, and unapproved features. Test requirement: Store access follows approved membership policy. Run the narrow relevant checks and report exact commands and outcomes. Expected output: focused implementation, meaningful tests, and concise notes on files changed, decisions, risks, and next dependency. Code quality: small readable changes, type/validation/error handling appropriate to the existing project, no duplicated business formulas, and no generated or sensitive data committed.

Expected Codex output: A focused change for AUTH-02, relevant tests, a file-change summary, and exact commands/results. No unrelated implementation.

How to inspect: Review the diff for these boundaries: Follow PLAN-04; implement minimum profile fields. Confirm only expected files changed, validation/permissions match the contract, and tests exercise the requirement.

How to understand: Explain in your own words how Ownership; CRUD; serializer validation. support this task; trace one normal case and one failure case through the code.

Run commands: Use verified environment commands from SETUP-07. Typical checks: backend: `python manage.py check` and the focused Django test module; frontend: `npm run lint`, focused test, and `npm run build`. Run only commands applicable to changed code and report exact outcomes.

Test steps / expected result: Store access follows approved membership policy. Success means the target is present, tests pass, and failure behavior is understandable.

Common errors: If the DB is unavailable, verify PostgreSQL service, database name, credentials, and env loading. If imports/routes fail, check app registration and URL inclusion. If an API/UI mismatch appears, compare against docs/api-contract.md and correct the contract or implementation deliberately; do not patch around it.

Git milestone: After review and passing tests, commit only this task. Suggested: `git add <reviewed-files> && git commit -m "AUTH-02: implement store profile create and read api"`. Use a feature branch only when it helps isolate a risky/long feature; no empty commits.

Viva questions: 1. What requirement does AUTH-02 satisfy? 2. Which data/API/UI boundary does it change? 3. How is invalid or unauthorized input handled? 4. What test proves it works? 5. What limitation remains?

Definition of Done: ☐ Scope met  ☐ Code understood  ☐ Focused tests pass  ☐ No unrelated changes  ☐ Evidence recorded  ☐ Commit created  ☐ Docs updated if affected  ☐ Viva explanation ready

## AUTH-03 — Add store-level permission enforcement

Proposal lead / workstream assignment: Monira Islam — follows the proposal split; this is a planned role, not a contribution record.

Hands-on operator: Monira Islam (you) — you will carry out every task, including tasks assigned to the frontend/UI workstream.

Requirement: Every store-owned record must be authorized server-side.

Target: Shared permission/queryset helpers consistently restrict store data.

Why this task matters: Shared permission/queryset helpers consistently restrict store data. It isolates one change so the student can inspect, test, and explain it before moving on.

Prerequisites: AUTH-02

Concepts to understand: Object-level permissions; queryset filtering; least privilege.

Expected files/modules: backend/core/permissions; account/store APIs; tests.

Implementation scope: Centralize access checks; deny missing or unauthorized store context.

Not in this task: Other modules, unrelated refactors, new dependencies, and unapproved features.

Ready-to-paste Codex prompt

You are implementing SellerOS, the SE-331 standalone social-commerce seller BI/decision-support capstone. Implement only AUTH-03 — Add store-level permission enforcement. Requirement: Every store-owned record must be authorized server-side. Objective/acceptance target: Shared permission/queryset helpers consistently restrict store data. Scope allowed: Centralize access checks; deny missing or unauthorized store context. Likely files/modules: backend/core/permissions; account/store APIs; tests. Prerequisites: AUTH-02. Constraints: follow the approved React/Vite/TypeScript + Django/DRF + PostgreSQL architecture and existing API/data contracts; inspect the repository first; preserve existing working behavior; do not invent unresolved business rules—mark [DECISION REQUIRED]; do not modify unrelated files, add unnecessary dependencies, expose secrets, bypass authentication/store permissions, fabricate AI/ML results, or create autonomous actions. Out of scope for this task: Other modules, unrelated refactors, new dependencies, and unapproved features. Test requirement: Cross-store negative tests fail closed for every covered route. Run the narrow relevant checks and report exact commands and outcomes. Expected output: focused implementation, meaningful tests, and concise notes on files changed, decisions, risks, and next dependency. Code quality: small readable changes, type/validation/error handling appropriate to the existing project, no duplicated business formulas, and no generated or sensitive data committed.

Expected Codex output: A focused change for AUTH-03, relevant tests, a file-change summary, and exact commands/results. No unrelated implementation.

How to inspect: Review the diff for these boundaries: Centralize access checks; deny missing or unauthorized store context. Confirm only expected files changed, validation/permissions match the contract, and tests exercise the requirement.

How to understand: Explain in your own words how Object-level permissions; queryset filtering; least privilege. support this task; trace one normal case and one failure case through the code.

Run commands: Use verified environment commands from SETUP-07. Typical checks: backend: `python manage.py check` and the focused Django test module; frontend: `npm run lint`, focused test, and `npm run build`. Run only commands applicable to changed code and report exact outcomes.

Test steps / expected result: Cross-store negative tests fail closed for every covered route. Success means the target is present, tests pass, and failure behavior is understandable.

Common errors: If the DB is unavailable, verify PostgreSQL service, database name, credentials, and env loading. If imports/routes fail, check app registration and URL inclusion. If an API/UI mismatch appears, compare against docs/api-contract.md and correct the contract or implementation deliberately; do not patch around it.

Git milestone: After review and passing tests, commit only this task. Suggested: `git add <reviewed-files> && git commit -m "AUTH-03: add store-level permission enforcement"`. Use a feature branch only when it helps isolate a risky/long feature; no empty commits.

Viva questions: 1. What requirement does AUTH-03 satisfy? 2. Which data/API/UI boundary does it change? 3. How is invalid or unauthorized input handled? 4. What test proves it works? 5. What limitation remains?

Definition of Done: ☐ Scope met  ☐ Code understood  ☐ Focused tests pass  ☐ No unrelated changes  ☐ Evidence recorded  ☐ Commit created  ☐ Docs updated if affected  ☐ Viva explanation ready

## AUTH-04 — Add store isolation and permission test suite

Proposal lead / workstream assignment: Jointly assigned to Monira Islam and Rukaiya Akther Trisha — follows the proposal split; this is a planned role, not a contribution record.

Hands-on operator: Monira Islam (you) — you will carry out every task, including tasks assigned to the frontend/UI workstream.

Requirement: Authorization needs direct evidence, not assumptions.

Target: Tests cover unauthenticated, wrong role, wrong store, and allowed same-store access.

Why this task matters: Tests cover unauthenticated, wrong role, wrong store, and allowed same-store access. It isolates one change so the student can inspect, test, and explain it before moving on.

Prerequisites: AUTH-03

Concepts to understand: Negative testing; IDOR; authorization matrix.

Expected files/modules: backend/tests/security/test_store_isolation; CI test config.

Implementation scope: Create two-store fixtures and exercise API/object lookup paths.

Not in this task: Other modules, unrelated refactors, new dependencies, and unapproved features.

Ready-to-paste Codex prompt

You are implementing SellerOS, the SE-331 standalone social-commerce seller BI/decision-support capstone. Implement only AUTH-04 — Add store isolation and permission test suite. Requirement: Authorization needs direct evidence, not assumptions. Objective/acceptance target: Tests cover unauthenticated, wrong role, wrong store, and allowed same-store access. Scope allowed: Create two-store fixtures and exercise API/object lookup paths. Likely files/modules: backend/tests/security/test_store_isolation; CI test config. Prerequisites: AUTH-03. Constraints: follow the approved React/Vite/TypeScript + Django/DRF + PostgreSQL architecture and existing API/data contracts; inspect the repository first; preserve existing working behavior; do not invent unresolved business rules—mark [DECISION REQUIRED]; do not modify unrelated files, add unnecessary dependencies, expose secrets, bypass authentication/store permissions, fabricate AI/ML results, or create autonomous actions. Out of scope for this task: Other modules, unrelated refactors, new dependencies, and unapproved features. Test requirement: Cross-store reads/writes return safe denial and disclose no data. Run the narrow relevant checks and report exact commands and outcomes. Expected output: focused implementation, meaningful tests, and concise notes on files changed, decisions, risks, and next dependency. Code quality: small readable changes, type/validation/error handling appropriate to the existing project, no duplicated business formulas, and no generated or sensitive data committed.

Expected Codex output: A focused change for AUTH-04, relevant tests, a file-change summary, and exact commands/results. No unrelated implementation.

How to inspect: Review the diff for these boundaries: Create two-store fixtures and exercise API/object lookup paths. Confirm only expected files changed, validation/permissions match the contract, and tests exercise the requirement.

How to understand: Explain in your own words how Negative testing; IDOR; authorization matrix. support this task; trace one normal case and one failure case through the code.

Run commands: Use verified environment commands from SETUP-07. Typical checks: backend: `python manage.py check` and the focused Django test module; frontend: `npm run lint`, focused test, and `npm run build`. Run only commands applicable to changed code and report exact outcomes.

Test steps / expected result: Cross-store reads/writes return safe denial and disclose no data. Success means the target is present, tests pass, and failure behavior is understandable.

Common errors: If the DB is unavailable, verify PostgreSQL service, database name, credentials, and env loading. If imports/routes fail, check app registration and URL inclusion. If an API/UI mismatch appears, compare against docs/api-contract.md and correct the contract or implementation deliberately; do not patch around it.

Git milestone: After review and passing tests, commit only this task. Suggested: `git add <reviewed-files> && git commit -m "AUTH-04: add store isolation and permission test suite"`. Use a feature branch only when it helps isolate a risky/long feature; no empty commits.

Viva questions: 1. What requirement does AUTH-04 satisfy? 2. Which data/API/UI boundary does it change? 3. How is invalid or unauthorized input handled? 4. What test proves it works? 5. What limitation remains?

Definition of Done: ☐ Scope met  ☐ Code understood  ☐ Focused tests pass  ☐ No unrelated changes  ☐ Evidence recorded  ☐ Commit created  ☐ Docs updated if affected  ☐ Viva explanation ready

## AUTH-05 — Build frontend sign-in and session states

Proposal lead / workstream assignment: Rukaiya Akther Trisha — follows the proposal split; this is a planned role, not a contribution record.

Hands-on operator: Monira Islam (you) — you will carry out every task, including tasks assigned to the frontend/UI workstream.

Requirement: Seller needs to enter and leave authenticated workspace safely.

Target: Login/logout and expired-session states use the shared API client.

Why this task matters: Login/logout and expired-session states use the shared API client. It isolates one change so the student can inspect, test, and explain it before moving on.

Prerequisites: AUTH-04

Concepts to understand: Session lifecycle; protected routes; accessibility.

Expected files/modules: frontend/src/features/auth; route guards; tests.

Implementation scope: Follow API contract; avoid storing secrets or implementing custom crypto.

Not in this task: Other modules, unrelated refactors, new dependencies, and unapproved features.

Ready-to-paste Codex prompt

You are implementing SellerOS, the SE-331 standalone social-commerce seller BI/decision-support capstone. Implement only AUTH-05 — Build frontend sign-in and session states. Requirement: Seller needs to enter and leave authenticated workspace safely. Objective/acceptance target: Login/logout and expired-session states use the shared API client. Scope allowed: Follow API contract; avoid storing secrets or implementing custom crypto. Likely files/modules: frontend/src/features/auth; route guards; tests. Prerequisites: AUTH-04. Constraints: follow the approved React/Vite/TypeScript + Django/DRF + PostgreSQL architecture and existing API/data contracts; inspect the repository first; preserve existing working behavior; do not invent unresolved business rules—mark [DECISION REQUIRED]; do not modify unrelated files, add unnecessary dependencies, expose secrets, bypass authentication/store permissions, fabricate AI/ML results, or create autonomous actions. Out of scope for this task: Other modules, unrelated refactors, new dependencies, and unapproved features. Test requirement: Login, logout, expired session, loading, and errors are usable. Run the narrow relevant checks and report exact commands and outcomes. Expected output: focused implementation, meaningful tests, and concise notes on files changed, decisions, risks, and next dependency. Code quality: small readable changes, type/validation/error handling appropriate to the existing project, no duplicated business formulas, and no generated or sensitive data committed.

Expected Codex output: A focused change for AUTH-05, relevant tests, a file-change summary, and exact commands/results. No unrelated implementation.

How to inspect: Review the diff for these boundaries: Follow API contract; avoid storing secrets or implementing custom crypto. Confirm only expected files changed, validation/permissions match the contract, and tests exercise the requirement.

How to understand: Explain in your own words how Session lifecycle; protected routes; accessibility. support this task; trace one normal case and one failure case through the code.

Run commands: Use verified environment commands from SETUP-07. Typical checks: backend: `python manage.py check` and the focused Django test module; frontend: `npm run lint`, focused test, and `npm run build`. Run only commands applicable to changed code and report exact outcomes.

Test steps / expected result: Login, logout, expired session, loading, and errors are usable. Success means the target is present, tests pass, and failure behavior is understandable.

Common errors: If the DB is unavailable, verify PostgreSQL service, database name, credentials, and env loading. If imports/routes fail, check app registration and URL inclusion. If an API/UI mismatch appears, compare against docs/api-contract.md and correct the contract or implementation deliberately; do not patch around it.

Git milestone: After review and passing tests, commit only this task. Suggested: `git add <reviewed-files> && git commit -m "AUTH-05: build frontend sign-in and session states"`. Use a feature branch only when it helps isolate a risky/long feature; no empty commits.

Viva questions: 1. What requirement does AUTH-05 satisfy? 2. Which data/API/UI boundary does it change? 3. How is invalid or unauthorized input handled? 4. What test proves it works? 5. What limitation remains?

Definition of Done: ☐ Scope met  ☐ Code understood  ☐ Focused tests pass  ☐ No unrelated changes  ☐ Evidence recorded  ☐ Commit created  ☐ Docs updated if affected  ☐ Viva explanation ready

## AUTH-06 — Verify end-to-end authenticated store flow

Proposal lead / workstream assignment: Jointly assigned to Monira Islam and Rukaiya Akther Trisha — follows the proposal split; this is a planned role, not a contribution record.

Hands-on operator: Monira Islam (you) — you will carry out every task, including tasks assigned to the frontend/UI workstream.

Requirement: Core records should be built only after identity and scope work.

Target: A signed-in user reaches the correct store and cannot switch to another without permission.

Why this task matters: A signed-in user reaches the correct store and cannot switch to another without permission. It isolates one change so the student can inspect, test, and explain it before moving on.

Prerequisites: AUTH-05

Concepts to understand: End-to-end tests; authorization; environment setup.

Expected files/modules: frontend e2e; backend integration tests; docs/test-evidence.

Implementation scope: Run browser/API workflow against PostgreSQL test environment.

Not in this task: Other modules, unrelated refactors, new dependencies, and unapproved features.

Ready-to-paste Codex prompt

You are implementing SellerOS, the SE-331 standalone social-commerce seller BI/decision-support capstone. Implement only AUTH-06 — Verify end-to-end authenticated store flow. Requirement: Core records should be built only after identity and scope work. Objective/acceptance target: A signed-in user reaches the correct store and cannot switch to another without permission. Scope allowed: Run browser/API workflow against PostgreSQL test environment. Likely files/modules: frontend e2e; backend integration tests; docs/test-evidence. Prerequisites: AUTH-05. Constraints: follow the approved React/Vite/TypeScript + Django/DRF + PostgreSQL architecture and existing API/data contracts; inspect the repository first; preserve existing working behavior; do not invent unresolved business rules—mark [DECISION REQUIRED]; do not modify unrelated files, add unnecessary dependencies, expose secrets, bypass authentication/store permissions, fabricate AI/ML results, or create autonomous actions. Out of scope for this task: Other modules, unrelated refactors, new dependencies, and unapproved features. Test requirement: Checkpoint 02 passes with recorded evidence. Run the narrow relevant checks and report exact commands and outcomes. Expected output: focused implementation, meaningful tests, and concise notes on files changed, decisions, risks, and next dependency. Code quality: small readable changes, type/validation/error handling appropriate to the existing project, no duplicated business formulas, and no generated or sensitive data committed.

Expected Codex output: A focused change for AUTH-06, relevant tests, a file-change summary, and exact commands/results. No unrelated implementation.

How to inspect: Review the diff for these boundaries: Run browser/API workflow against PostgreSQL test environment. Confirm only expected files changed, validation/permissions match the contract, and tests exercise the requirement.

How to understand: Explain in your own words how End-to-end tests; authorization; environment setup. support this task; trace one normal case and one failure case through the code.

Run commands: Use verified environment commands from SETUP-07. Typical checks: backend: `python manage.py check` and the focused Django test module; frontend: `npm run lint`, focused test, and `npm run build`. Run only commands applicable to changed code and report exact outcomes.

Test steps / expected result: Checkpoint 02 passes with recorded evidence. Success means the target is present, tests pass, and failure behavior is understandable.

Common errors: If the DB is unavailable, verify PostgreSQL service, database name, credentials, and env loading. If imports/routes fail, check app registration and URL inclusion. If an API/UI mismatch appears, compare against docs/api-contract.md and correct the contract or implementation deliberately; do not patch around it.

Git milestone: After review and passing tests, commit only this task. Suggested: `git add <reviewed-files> && git commit -m "AUTH-06: verify end-to-end authenticated store flow"`. Use a feature branch only when it helps isolate a risky/long feature; no empty commits.

Viva questions: 1. What requirement does AUTH-06 satisfy? 2. Which data/API/UI boundary does it change? 3. How is invalid or unauthorized input handled? 4. What test proves it works? 5. What limitation remains?

Definition of Done: ☐ Scope met  ☐ Code understood  ☐ Focused tests pass  ☐ No unrelated changes  ☐ Evidence recorded  ☐ Commit created  ☐ Docs updated if affected  ☐ Viva explanation ready

# Phase 4 — Test-data policy and operational records

Build the structured, store-scoped data foundation that powers all analysis.

## DATA-01 — Create synthetic-data policy and seed strategy

Proposal lead / workstream assignment: Jointly assigned to Monira Islam and Rukaiya Akther Trisha — follows the proposal split; this is a planned role, not a contribution record.

Hands-on operator: Monira Islam (you) — you will carry out every task, including tasks assigned to the frontend/UI workstream.

Requirement: Evaluation must avoid unnecessary sensitive customer data.

Target: Policy states allowed test sources, synthetic-data labeling, reset strategy, and retention.

Why this task matters: Policy states allowed test sources, synthetic-data labeling, reset strategy, and retention. It isolates one change so the student can inspect, test, and explain it before moving on.

Prerequisites: None beyond repository inspection and the approved project baseline.

Concepts to understand: Data minimization; reproducibility; provenance.

Expected files/modules: docs/test-data-policy.md; backend seed command design.

Implementation scope: Document data provenance; prohibit production export in demo by default.

Not in this task: Other modules, unrelated refactors, new dependencies, and unapproved features.

Ready-to-paste Codex prompt

You are implementing SellerOS, the SE-331 standalone social-commerce seller BI/decision-support capstone. Implement only DATA-01 — Create synthetic-data policy and seed strategy. Requirement: Evaluation must avoid unnecessary sensitive customer data. Objective/acceptance target: Policy states allowed test sources, synthetic-data labeling, reset strategy, and retention. Scope allowed: Document data provenance; prohibit production export in demo by default. Likely files/modules: docs/test-data-policy.md; backend seed command design. Prerequisites: none beyond the approved project baseline. Constraints: follow the approved React/Vite/TypeScript + Django/DRF + PostgreSQL architecture and existing API/data contracts; inspect the repository first; preserve existing working behavior; do not invent unresolved business rules—mark [DECISION REQUIRED]; do not modify unrelated files, add unnecessary dependencies, expose secrets, bypass authentication/store permissions, fabricate AI/ML results, or create autonomous actions. Out of scope for this task: Other modules, unrelated refactors, new dependencies, and unapproved features. Test requirement: Policy reviewed before loading test records. Run the narrow relevant checks and report exact commands and outcomes. Expected output: focused implementation, meaningful tests, and concise notes on files changed, decisions, risks, and next dependency. Code quality: small readable changes, type/validation/error handling appropriate to the existing project, no duplicated business formulas, and no generated or sensitive data committed.

Expected Codex output: A focused change for DATA-01, relevant tests, a file-change summary, and exact commands/results. No unrelated implementation.

How to inspect: Review the diff for these boundaries: Document data provenance; prohibit production export in demo by default. Confirm only expected files changed, validation/permissions match the contract, and tests exercise the requirement.

How to understand: Explain in your own words how Data minimization; reproducibility; provenance. support this task; trace one normal case and one failure case through the code.

Run commands: Use verified environment commands from SETUP-07. Typical checks: backend: `python manage.py check` and the focused Django test module; frontend: `npm run lint`, focused test, and `npm run build`. Run only commands applicable to changed code and report exact outcomes.

Test steps / expected result: Policy reviewed before loading test records. Success means the target is present, tests pass, and failure behavior is understandable.

Common errors: If the DB is unavailable, verify PostgreSQL service, database name, credentials, and env loading. If imports/routes fail, check app registration and URL inclusion. If an API/UI mismatch appears, compare against docs/api-contract.md and correct the contract or implementation deliberately; do not patch around it.

Git milestone: After review and passing tests, commit only this task. Suggested: `git add <reviewed-files> && git commit -m "DATA-01: create synthetic-data policy and seed strategy"`. Use a feature branch only when it helps isolate a risky/long feature; no empty commits.

Viva questions: 1. What requirement does DATA-01 satisfy? 2. Which data/API/UI boundary does it change? 3. How is invalid or unauthorized input handled? 4. What test proves it works? 5. What limitation remains?

Definition of Done: ☐ Scope met  ☐ Code understood  ☐ Focused tests pass  ☐ No unrelated changes  ☐ Evidence recorded  ☐ Commit created  ☐ Docs updated if affected  ☐ Viva explanation ready

## DATA-02 — Create realistic synthetic product and customer records

Proposal lead / workstream assignment: Jointly assigned to Monira Islam and Rukaiya Akther Trisha — follows the proposal split; this is a planned role, not a contribution record.

Hands-on operator: Monira Islam (you) — you will carry out every task, including tasks assigned to the frontend/UI workstream.

Requirement: CRUD and segmentation need representative records.

Target: Repeatable seed set includes varied products, variants, and synthetic customer histories.

Why this task matters: Repeatable seed set includes varied products, variants, and synthetic customer histories. It isolates one change so the student can inspect, test, and explain it before moving on.

Prerequisites: DATA-01

Concepts to understand: Fixtures; referential integrity; representative sampling.

Expected files/modules: backend/seed; data/sample; tests.

Implementation scope: Use fictional identities, edge cases, and explicit synthetic labels.

Not in this task: Other modules, unrelated refactors, new dependencies, and unapproved features.

Ready-to-paste Codex prompt

You are implementing SellerOS, the SE-331 standalone social-commerce seller BI/decision-support capstone. Implement only DATA-02 — Create realistic synthetic product and customer records. Requirement: CRUD and segmentation need representative records. Objective/acceptance target: Repeatable seed set includes varied products, variants, and synthetic customer histories. Scope allowed: Use fictional identities, edge cases, and explicit synthetic labels. Likely files/modules: backend/seed; data/sample; tests. Prerequisites: DATA-01. Constraints: follow the approved React/Vite/TypeScript + Django/DRF + PostgreSQL architecture and existing API/data contracts; inspect the repository first; preserve existing working behavior; do not invent unresolved business rules—mark [DECISION REQUIRED]; do not modify unrelated files, add unnecessary dependencies, expose secrets, bypass authentication/store permissions, fabricate AI/ML results, or create autonomous actions. Out of scope for this task: Other modules, unrelated refactors, new dependencies, and unapproved features. Test requirement: Seed is repeatable and contains no real contact details. Run the narrow relevant checks and report exact commands and outcomes. Expected output: focused implementation, meaningful tests, and concise notes on files changed, decisions, risks, and next dependency. Code quality: small readable changes, type/validation/error handling appropriate to the existing project, no duplicated business formulas, and no generated or sensitive data committed.

Expected Codex output: A focused change for DATA-02, relevant tests, a file-change summary, and exact commands/results. No unrelated implementation.

How to inspect: Review the diff for these boundaries: Use fictional identities, edge cases, and explicit synthetic labels. Confirm only expected files changed, validation/permissions match the contract, and tests exercise the requirement.

How to understand: Explain in your own words how Fixtures; referential integrity; representative sampling. support this task; trace one normal case and one failure case through the code.

Run commands: Use verified environment commands from SETUP-07. Typical checks: backend: `python manage.py check` and the focused Django test module; frontend: `npm run lint`, focused test, and `npm run build`. Run only commands applicable to changed code and report exact outcomes.

Test steps / expected result: Seed is repeatable and contains no real contact details. Success means the target is present, tests pass, and failure behavior is understandable.

Common errors: If the DB is unavailable, verify PostgreSQL service, database name, credentials, and env loading. If imports/routes fail, check app registration and URL inclusion. If an API/UI mismatch appears, compare against docs/api-contract.md and correct the contract or implementation deliberately; do not patch around it.

Git milestone: After review and passing tests, commit only this task. Suggested: `git add <reviewed-files> && git commit -m "DATA-02: create realistic synthetic product and customer records"`. Use a feature branch only when it helps isolate a risky/long feature; no empty commits.

Viva questions: 1. What requirement does DATA-02 satisfy? 2. Which data/API/UI boundary does it change? 3. How is invalid or unauthorized input handled? 4. What test proves it works? 5. What limitation remains?

Definition of Done: ☐ Scope met  ☐ Code understood  ☐ Focused tests pass  ☐ No unrelated changes  ☐ Evidence recorded  ☐ Commit created  ☐ Docs updated if affected  ☐ Viva explanation ready

## DATA-03 — Create synthetic order, expense, and time-series records

Proposal lead / workstream assignment: Jointly assigned to Monira Islam and Rukaiya Akther Trisha — follows the proposal split; this is a planned role, not a contribution record.

Hands-on operator: Monira Islam (you) — you will carry out every task, including tasks assigned to the frontend/UI workstream.

Requirement: Analytics and forecasting need chronological, internally consistent records.

Target: Synthetic dataset includes normal, sparse, missing-cost, return/cancel cases after decisions.

Why this task matters: Synthetic dataset includes normal, sparse, missing-cost, return/cancel cases after decisions. It isolates one change so the student can inspect, test, and explain it before moving on.

Prerequisites: DATA-02

Concepts to understand: Time series; transactions; edge-case fixtures.

Expected files/modules: backend/seed; data/sample; docs/data.

Implementation scope: Generate only cases aligned to approved rules; preserve provenance.

Not in this task: Other modules, unrelated refactors, new dependencies, and unapproved features.

Ready-to-paste Codex prompt

You are implementing SellerOS, the SE-331 standalone social-commerce seller BI/decision-support capstone. Implement only DATA-03 — Create synthetic order, expense, and time-series records. Requirement: Analytics and forecasting need chronological, internally consistent records. Objective/acceptance target: Synthetic dataset includes normal, sparse, missing-cost, return/cancel cases after decisions. Scope allowed: Generate only cases aligned to approved rules; preserve provenance. Likely files/modules: backend/seed; data/sample; docs/data. Prerequisites: DATA-02. Constraints: follow the approved React/Vite/TypeScript + Django/DRF + PostgreSQL architecture and existing API/data contracts; inspect the repository first; preserve existing working behavior; do not invent unresolved business rules—mark [DECISION REQUIRED]; do not modify unrelated files, add unnecessary dependencies, expose secrets, bypass authentication/store permissions, fabricate AI/ML results, or create autonomous actions. Out of scope for this task: Other modules, unrelated refactors, new dependencies, and unapproved features. Test requirement: Totals reconcile to known expected values. Run the narrow relevant checks and report exact commands and outcomes. Expected output: focused implementation, meaningful tests, and concise notes on files changed, decisions, risks, and next dependency. Code quality: small readable changes, type/validation/error handling appropriate to the existing project, no duplicated business formulas, and no generated or sensitive data committed.

Expected Codex output: A focused change for DATA-03, relevant tests, a file-change summary, and exact commands/results. No unrelated implementation.

How to inspect: Review the diff for these boundaries: Generate only cases aligned to approved rules; preserve provenance. Confirm only expected files changed, validation/permissions match the contract, and tests exercise the requirement.

How to understand: Explain in your own words how Time series; transactions; edge-case fixtures. support this task; trace one normal case and one failure case through the code.

Run commands: Use verified environment commands from SETUP-07. Typical checks: backend: `python manage.py check` and the focused Django test module; frontend: `npm run lint`, focused test, and `npm run build`. Run only commands applicable to changed code and report exact outcomes.

Test steps / expected result: Totals reconcile to known expected values. Success means the target is present, tests pass, and failure behavior is understandable.

Common errors: If the DB is unavailable, verify PostgreSQL service, database name, credentials, and env loading. If imports/routes fail, check app registration and URL inclusion. If an API/UI mismatch appears, compare against docs/api-contract.md and correct the contract or implementation deliberately; do not patch around it.

Git milestone: After review and passing tests, commit only this task. Suggested: `git add <reviewed-files> && git commit -m "DATA-03: create synthetic order, expense, and time-series records"`. Use a feature branch only when it helps isolate a risky/long feature; no empty commits.

Viva questions: 1. What requirement does DATA-03 satisfy? 2. Which data/API/UI boundary does it change? 3. How is invalid or unauthorized input handled? 4. What test proves it works? 5. What limitation remains?

Definition of Done: ☐ Scope met  ☐ Code understood  ☐ Focused tests pass  ☐ No unrelated changes  ☐ Evidence recorded  ☐ Commit created  ☐ Docs updated if affected  ☐ Viva explanation ready

## DATA-04 — Create AI and evaluation case sets

Proposal lead / workstream assignment: Jointly assigned to Monira Islam and Rukaiya Akther Trisha — follows the proposal split; this is a planned role, not a contribution record.

Hands-on operator: Monira Islam (you) — you will carry out every task, including tasks assigned to the frontend/UI workstream.

Requirement: AI/ML quality must be checked with repeatable cases.

Target: Versioned cases cover supported requests, unsupported facts, insufficient data, injection, and expected evidence.

Why this task matters: Versioned cases cover supported requests, unsupported facts, insufficient data, injection, and expected evidence. It isolates one change so the student can inspect, test, and explain it before moving on.

Prerequisites: DATA-03

Concepts to understand: Test fixtures; rubric; prompt injection.

Expected files/modules: tests/ai_cases; docs/evaluation.

Implementation scope: Keep cases synthetic; include rubric and expected safe behavior.

Not in this task: Other modules, unrelated refactors, new dependencies, and unapproved features.

Ready-to-paste Codex prompt

You are implementing SellerOS, the SE-331 standalone social-commerce seller BI/decision-support capstone. Implement only DATA-04 — Create AI and evaluation case sets. Requirement: AI/ML quality must be checked with repeatable cases. Objective/acceptance target: Versioned cases cover supported requests, unsupported facts, insufficient data, injection, and expected evidence. Scope allowed: Keep cases synthetic; include rubric and expected safe behavior. Likely files/modules: tests/ai_cases; docs/evaluation. Prerequisites: DATA-03. Constraints: follow the approved React/Vite/TypeScript + Django/DRF + PostgreSQL architecture and existing API/data contracts; inspect the repository first; preserve existing working behavior; do not invent unresolved business rules—mark [DECISION REQUIRED]; do not modify unrelated files, add unnecessary dependencies, expose secrets, bypass authentication/store permissions, fabricate AI/ML results, or create autonomous actions. Out of scope for this task: Other modules, unrelated refactors, new dependencies, and unapproved features. Test requirement: Case set is deterministic and contains expected outcomes. Run the narrow relevant checks and report exact commands and outcomes. Expected output: focused implementation, meaningful tests, and concise notes on files changed, decisions, risks, and next dependency. Code quality: small readable changes, type/validation/error handling appropriate to the existing project, no duplicated business formulas, and no generated or sensitive data committed.

Expected Codex output: A focused change for DATA-04, relevant tests, a file-change summary, and exact commands/results. No unrelated implementation.

How to inspect: Review the diff for these boundaries: Keep cases synthetic; include rubric and expected safe behavior. Confirm only expected files changed, validation/permissions match the contract, and tests exercise the requirement.

How to understand: Explain in your own words how Test fixtures; rubric; prompt injection. support this task; trace one normal case and one failure case through the code.

Run commands: Use verified environment commands from SETUP-07. Typical checks: backend: `python manage.py check` and the focused Django test module; frontend: `npm run lint`, focused test, and `npm run build`. Run only commands applicable to changed code and report exact outcomes.

Test steps / expected result: Case set is deterministic and contains expected outcomes. Success means the target is present, tests pass, and failure behavior is understandable.

Common errors: If the DB is unavailable, verify PostgreSQL service, database name, credentials, and env loading. If imports/routes fail, check app registration and URL inclusion. If an API/UI mismatch appears, compare against docs/api-contract.md and correct the contract or implementation deliberately; do not patch around it.

Git milestone: After review and passing tests, commit only this task. Suggested: `git add <reviewed-files> && git commit -m "DATA-04: create ai and evaluation case sets"`. Use a feature branch only when it helps isolate a risky/long feature; no empty commits.

Viva questions: 1. What requirement does DATA-04 satisfy? 2. Which data/API/UI boundary does it change? 3. How is invalid or unauthorized input handled? 4. What test proves it works? 5. What limitation remains?

Definition of Done: ☐ Scope met  ☐ Code understood  ☐ Focused tests pass  ☐ No unrelated changes  ☐ Evidence recorded  ☐ Commit created  ☐ Docs updated if affected  ☐ Viva explanation ready

# Phase 5 — Product and inventory

Implement stock records and auditable updates before orders depend on them.

## PRODUCT-01 — Create product and variant models

Proposal lead / workstream assignment: Monira Islam — follows the proposal split; this is a planned role, not a contribution record.

Hands-on operator: Monira Islam (you) — you will carry out every task, including tasks assigned to the frontend/UI workstream.

Requirement: Products need seller/store ownership, price, cost, category, and optional variants.

Target: Product schema and migrations store approved catalogue data.

Why this task matters: Product schema and migrations store approved catalogue data. It isolates one change so the student can inspect, test, and explain it before moving on.

Prerequisites: None beyond repository inspection and the approved project baseline.

Concepts to understand: Django models; decimals; uniqueness; relationships.

Expected files/modules: backend/apps/catalog/models; migrations; tests.

Implementation scope: Use DB dictionary; decide variant representation before model coding.

Not in this task: Other modules, unrelated refactors, new dependencies, and unapproved features.

Ready-to-paste Codex prompt

You are implementing SellerOS, the SE-331 standalone social-commerce seller BI/decision-support capstone. Implement only PRODUCT-01 — Create product and variant models. Requirement: Products need seller/store ownership, price, cost, category, and optional variants. Objective/acceptance target: Product schema and migrations store approved catalogue data. Scope allowed: Use DB dictionary; decide variant representation before model coding. Likely files/modules: backend/apps/catalog/models; migrations; tests. Prerequisites: none beyond the approved project baseline. Constraints: follow the approved React/Vite/TypeScript + Django/DRF + PostgreSQL architecture and existing API/data contracts; inspect the repository first; preserve existing working behavior; do not invent unresolved business rules—mark [DECISION REQUIRED]; do not modify unrelated files, add unnecessary dependencies, expose secrets, bypass authentication/store permissions, fabricate AI/ML results, or create autonomous actions. Out of scope for this task: Other modules, unrelated refactors, new dependencies, and unapproved features. Test requirement: Model tests cover required fields, price/cost validation, store ownership. Run the narrow relevant checks and report exact commands and outcomes. Expected output: focused implementation, meaningful tests, and concise notes on files changed, decisions, risks, and next dependency. Code quality: small readable changes, type/validation/error handling appropriate to the existing project, no duplicated business formulas, and no generated or sensitive data committed.

Expected Codex output: A focused change for PRODUCT-01, relevant tests, a file-change summary, and exact commands/results. No unrelated implementation.

How to inspect: Review the diff for these boundaries: Use DB dictionary; decide variant representation before model coding. Confirm only expected files changed, validation/permissions match the contract, and tests exercise the requirement.

How to understand: Explain in your own words how Django models; decimals; uniqueness; relationships. support this task; trace one normal case and one failure case through the code.

Run commands: Use verified environment commands from SETUP-07. Typical checks: backend: `python manage.py check` and the focused Django test module; frontend: `npm run lint`, focused test, and `npm run build`. Run only commands applicable to changed code and report exact outcomes.

Test steps / expected result: Model tests cover required fields, price/cost validation, store ownership. Success means the target is present, tests pass, and failure behavior is understandable.

Common errors: If the DB is unavailable, verify PostgreSQL service, database name, credentials, and env loading. If imports/routes fail, check app registration and URL inclusion. If an API/UI mismatch appears, compare against docs/api-contract.md and correct the contract or implementation deliberately; do not patch around it.

Git milestone: After review and passing tests, commit only this task. Suggested: `git add <reviewed-files> && git commit -m "PRODUCT-01: create product and variant models"`. Use a feature branch only when it helps isolate a risky/long feature; no empty commits.

Viva questions: 1. What requirement does PRODUCT-01 satisfy? 2. Which data/API/UI boundary does it change? 3. How is invalid or unauthorized input handled? 4. What test proves it works? 5. What limitation remains?

Definition of Done: ☐ Scope met  ☐ Code understood  ☐ Focused tests pass  ☐ No unrelated changes  ☐ Evidence recorded  ☐ Commit created  ☐ Docs updated if affected  ☐ Viva explanation ready

## PRODUCT-02 — Add product and variant serializers

Proposal lead / workstream assignment: Monira Islam — follows the proposal split; this is a planned role, not a contribution record.

Hands-on operator: Monira Islam (you) — you will carry out every task, including tasks assigned to the frontend/UI workstream.

Requirement: API payloads need consistent validation.

Target: Serializer validation matches data dictionary and API contract.

Why this task matters: Serializer validation matches data dictionary and API contract. It isolates one change so the student can inspect, test, and explain it before moving on.

Prerequisites: PRODUCT-01

Concepts to understand: Serialization; validation; decimal precision.

Expected files/modules: backend/apps/catalog/serializers; tests.

Implementation scope: Validate decimals, names, categories, active state, and variant relationships.

Not in this task: Other modules, unrelated refactors, new dependencies, and unapproved features.

Ready-to-paste Codex prompt

You are implementing SellerOS, the SE-331 standalone social-commerce seller BI/decision-support capstone. Implement only PRODUCT-02 — Add product and variant serializers. Requirement: API payloads need consistent validation. Objective/acceptance target: Serializer validation matches data dictionary and API contract. Scope allowed: Validate decimals, names, categories, active state, and variant relationships. Likely files/modules: backend/apps/catalog/serializers; tests. Prerequisites: PRODUCT-01. Constraints: follow the approved React/Vite/TypeScript + Django/DRF + PostgreSQL architecture and existing API/data contracts; inspect the repository first; preserve existing working behavior; do not invent unresolved business rules—mark [DECISION REQUIRED]; do not modify unrelated files, add unnecessary dependencies, expose secrets, bypass authentication/store permissions, fabricate AI/ML results, or create autonomous actions. Out of scope for this task: Other modules, unrelated refactors, new dependencies, and unapproved features. Test requirement: Valid/invalid payload test matrix passes. Run the narrow relevant checks and report exact commands and outcomes. Expected output: focused implementation, meaningful tests, and concise notes on files changed, decisions, risks, and next dependency. Code quality: small readable changes, type/validation/error handling appropriate to the existing project, no duplicated business formulas, and no generated or sensitive data committed.

Expected Codex output: A focused change for PRODUCT-02, relevant tests, a file-change summary, and exact commands/results. No unrelated implementation.

How to inspect: Review the diff for these boundaries: Validate decimals, names, categories, active state, and variant relationships. Confirm only expected files changed, validation/permissions match the contract, and tests exercise the requirement.

How to understand: Explain in your own words how Serialization; validation; decimal precision. support this task; trace one normal case and one failure case through the code.

Run commands: Use verified environment commands from SETUP-07. Typical checks: backend: `python manage.py check` and the focused Django test module; frontend: `npm run lint`, focused test, and `npm run build`. Run only commands applicable to changed code and report exact outcomes.

Test steps / expected result: Valid/invalid payload test matrix passes. Success means the target is present, tests pass, and failure behavior is understandable.

Common errors: If the DB is unavailable, verify PostgreSQL service, database name, credentials, and env loading. If imports/routes fail, check app registration and URL inclusion. If an API/UI mismatch appears, compare against docs/api-contract.md and correct the contract or implementation deliberately; do not patch around it.

Git milestone: After review and passing tests, commit only this task. Suggested: `git add <reviewed-files> && git commit -m "PRODUCT-02: add product and variant serializers"`. Use a feature branch only when it helps isolate a risky/long feature; no empty commits.

Viva questions: 1. What requirement does PRODUCT-02 satisfy? 2. Which data/API/UI boundary does it change? 3. How is invalid or unauthorized input handled? 4. What test proves it works? 5. What limitation remains?

Definition of Done: ☐ Scope met  ☐ Code understood  ☐ Focused tests pass  ☐ No unrelated changes  ☐ Evidence recorded  ☐ Commit created  ☐ Docs updated if affected  ☐ Viva explanation ready

## PRODUCT-03 — Implement product list and detail APIs

Proposal lead / workstream assignment: Monira Islam — follows the proposal split; this is a planned role, not a contribution record.

Hands-on operator: Monira Islam (you) — you will carry out every task, including tasks assigned to the frontend/UI workstream.

Requirement: Seller must inspect catalogue records within their store.

Target: Filtered, paginated product list and detail reads honor store access.

Why this task matters: Filtered, paginated product list and detail reads honor store access. It isolates one change so the student can inspect, test, and explain it before moving on.

Prerequisites: PRODUCT-02

Concepts to understand: Querysets; pagination; filtering; object permissions.

Expected files/modules: backend/apps/catalog/views; URLs; tests.

Implementation scope: Implement read routes, ordering/filter rules, and error contract.

Not in this task: Other modules, unrelated refactors, new dependencies, and unapproved features.

Ready-to-paste Codex prompt

You are implementing SellerOS, the SE-331 standalone social-commerce seller BI/decision-support capstone. Implement only PRODUCT-03 — Implement product list and detail APIs. Requirement: Seller must inspect catalogue records within their store. Objective/acceptance target: Filtered, paginated product list and detail reads honor store access. Scope allowed: Implement read routes, ordering/filter rules, and error contract. Likely files/modules: backend/apps/catalog/views; URLs; tests. Prerequisites: PRODUCT-02. Constraints: follow the approved React/Vite/TypeScript + Django/DRF + PostgreSQL architecture and existing API/data contracts; inspect the repository first; preserve existing working behavior; do not invent unresolved business rules—mark [DECISION REQUIRED]; do not modify unrelated files, add unnecessary dependencies, expose secrets, bypass authentication/store permissions, fabricate AI/ML results, or create autonomous actions. Out of scope for this task: Other modules, unrelated refactors, new dependencies, and unapproved features. Test requirement: Same-store list/detail pass; cross-store IDs denied. Run the narrow relevant checks and report exact commands and outcomes. Expected output: focused implementation, meaningful tests, and concise notes on files changed, decisions, risks, and next dependency. Code quality: small readable changes, type/validation/error handling appropriate to the existing project, no duplicated business formulas, and no generated or sensitive data committed.

Expected Codex output: A focused change for PRODUCT-03, relevant tests, a file-change summary, and exact commands/results. No unrelated implementation.

How to inspect: Review the diff for these boundaries: Implement read routes, ordering/filter rules, and error contract. Confirm only expected files changed, validation/permissions match the contract, and tests exercise the requirement.

How to understand: Explain in your own words how Querysets; pagination; filtering; object permissions. support this task; trace one normal case and one failure case through the code.

Run commands: Use verified environment commands from SETUP-07. Typical checks: backend: `python manage.py check` and the focused Django test module; frontend: `npm run lint`, focused test, and `npm run build`. Run only commands applicable to changed code and report exact outcomes.

Test steps / expected result: Same-store list/detail pass; cross-store IDs denied. Success means the target is present, tests pass, and failure behavior is understandable.

Common errors: If the DB is unavailable, verify PostgreSQL service, database name, credentials, and env loading. If imports/routes fail, check app registration and URL inclusion. If an API/UI mismatch appears, compare against docs/api-contract.md and correct the contract or implementation deliberately; do not patch around it.

Git milestone: After review and passing tests, commit only this task. Suggested: `git add <reviewed-files> && git commit -m "PRODUCT-03: implement product list and detail apis"`. Use a feature branch only when it helps isolate a risky/long feature; no empty commits.

Viva questions: 1. What requirement does PRODUCT-03 satisfy? 2. Which data/API/UI boundary does it change? 3. How is invalid or unauthorized input handled? 4. What test proves it works? 5. What limitation remains?

Definition of Done: ☐ Scope met  ☐ Code understood  ☐ Focused tests pass  ☐ No unrelated changes  ☐ Evidence recorded  ☐ Commit created  ☐ Docs updated if affected  ☐ Viva explanation ready

## PRODUCT-04 — Implement product create and update APIs

Proposal lead / workstream assignment: Monira Islam — follows the proposal split; this is a planned role, not a contribution record.

Hands-on operator: Monira Islam (you) — you will carry out every task, including tasks assigned to the frontend/UI workstream.

Requirement: Seller must maintain catalogue data.

Target: Authorized seller can create/edit/deactivate product data under agreed rules.

Why this task matters: Authorized seller can create/edit/deactivate product data under agreed rules. It isolates one change so the student can inspect, test, and explain it before moving on.

Prerequisites: PRODUCT-03

Concepts to understand: HTTP methods; validation; referential integrity.

Expected files/modules: backend/apps/catalog/views; serializers; tests.

Implementation scope: Implement writes; avoid hard deletion when records are referenced unless decision allows.

Not in this task: Other modules, unrelated refactors, new dependencies, and unapproved features.

Ready-to-paste Codex prompt

You are implementing SellerOS, the SE-331 standalone social-commerce seller BI/decision-support capstone. Implement only PRODUCT-04 — Implement product create and update APIs. Requirement: Seller must maintain catalogue data. Objective/acceptance target: Authorized seller can create/edit/deactivate product data under agreed rules. Scope allowed: Implement writes; avoid hard deletion when records are referenced unless decision allows. Likely files/modules: backend/apps/catalog/views; serializers; tests. Prerequisites: PRODUCT-03. Constraints: follow the approved React/Vite/TypeScript + Django/DRF + PostgreSQL architecture and existing API/data contracts; inspect the repository first; preserve existing working behavior; do not invent unresolved business rules—mark [DECISION REQUIRED]; do not modify unrelated files, add unnecessary dependencies, expose secrets, bypass authentication/store permissions, fabricate AI/ML results, or create autonomous actions. Out of scope for this task: Other modules, unrelated refactors, new dependencies, and unapproved features. Test requirement: Create/update/deactivate tests include conflicts and invalid values. Run the narrow relevant checks and report exact commands and outcomes. Expected output: focused implementation, meaningful tests, and concise notes on files changed, decisions, risks, and next dependency. Code quality: small readable changes, type/validation/error handling appropriate to the existing project, no duplicated business formulas, and no generated or sensitive data committed.

Expected Codex output: A focused change for PRODUCT-04, relevant tests, a file-change summary, and exact commands/results. No unrelated implementation.

How to inspect: Review the diff for these boundaries: Implement writes; avoid hard deletion when records are referenced unless decision allows. Confirm only expected files changed, validation/permissions match the contract, and tests exercise the requirement.

How to understand: Explain in your own words how HTTP methods; validation; referential integrity. support this task; trace one normal case and one failure case through the code.

Run commands: Use verified environment commands from SETUP-07. Typical checks: backend: `python manage.py check` and the focused Django test module; frontend: `npm run lint`, focused test, and `npm run build`. Run only commands applicable to changed code and report exact outcomes.

Test steps / expected result: Create/update/deactivate tests include conflicts and invalid values. Success means the target is present, tests pass, and failure behavior is understandable.

Common errors: If the DB is unavailable, verify PostgreSQL service, database name, credentials, and env loading. If imports/routes fail, check app registration and URL inclusion. If an API/UI mismatch appears, compare against docs/api-contract.md and correct the contract or implementation deliberately; do not patch around it.

Git milestone: After review and passing tests, commit only this task. Suggested: `git add <reviewed-files> && git commit -m "PRODUCT-04: implement product create and update apis"`. Use a feature branch only when it helps isolate a risky/long feature; no empty commits.

Viva questions: 1. What requirement does PRODUCT-04 satisfy? 2. Which data/API/UI boundary does it change? 3. How is invalid or unauthorized input handled? 4. What test proves it works? 5. What limitation remains?

Definition of Done: ☐ Scope met  ☐ Code understood  ☐ Focused tests pass  ☐ No unrelated changes  ☐ Evidence recorded  ☐ Commit created  ☐ Docs updated if affected  ☐ Viva explanation ready

## PRODUCT-05 — Add product API validation and permission tests

Proposal lead / workstream assignment: Jointly assigned to Monira Islam and Rukaiya Akther Trisha — follows the proposal split; this is a planned role, not a contribution record.

Hands-on operator: Monira Islam (you) — you will carry out every task, including tasks assigned to the frontend/UI workstream.

Requirement: Catalogue rules must be executable and regression protected.

Target: Tests cover price/cost, variants, duplicate names/SKU, inactive items, and ownership.

Why this task matters: Tests cover price/cost, variants, duplicate names/SKU, inactive items, and ownership. It isolates one change so the student can inspect, test, and explain it before moving on.

Prerequisites: PRODUCT-04

Concepts to understand: Boundary testing; constraints; permission testing.

Expected files/modules: backend/apps/catalog/tests.

Implementation scope: Use approved rules; report unresolved duplicate semantics as decision.

Not in this task: Other modules, unrelated refactors, new dependencies, and unapproved features.

Ready-to-paste Codex prompt

You are implementing SellerOS, the SE-331 standalone social-commerce seller BI/decision-support capstone. Implement only PRODUCT-05 — Add product API validation and permission tests. Requirement: Catalogue rules must be executable and regression protected. Objective/acceptance target: Tests cover price/cost, variants, duplicate names/SKU, inactive items, and ownership. Scope allowed: Use approved rules; report unresolved duplicate semantics as decision. Likely files/modules: backend/apps/catalog/tests. Prerequisites: PRODUCT-04. Constraints: follow the approved React/Vite/TypeScript + Django/DRF + PostgreSQL architecture and existing API/data contracts; inspect the repository first; preserve existing working behavior; do not invent unresolved business rules—mark [DECISION REQUIRED]; do not modify unrelated files, add unnecessary dependencies, expose secrets, bypass authentication/store permissions, fabricate AI/ML results, or create autonomous actions. Out of scope for this task: Other modules, unrelated refactors, new dependencies, and unapproved features. Test requirement: All edge cases match documented behavior. Run the narrow relevant checks and report exact commands and outcomes. Expected output: focused implementation, meaningful tests, and concise notes on files changed, decisions, risks, and next dependency. Code quality: small readable changes, type/validation/error handling appropriate to the existing project, no duplicated business formulas, and no generated or sensitive data committed.

Expected Codex output: A focused change for PRODUCT-05, relevant tests, a file-change summary, and exact commands/results. No unrelated implementation.

How to inspect: Review the diff for these boundaries: Use approved rules; report unresolved duplicate semantics as decision. Confirm only expected files changed, validation/permissions match the contract, and tests exercise the requirement.

How to understand: Explain in your own words how Boundary testing; constraints; permission testing. support this task; trace one normal case and one failure case through the code.

Run commands: Use verified environment commands from SETUP-07. Typical checks: backend: `python manage.py check` and the focused Django test module; frontend: `npm run lint`, focused test, and `npm run build`. Run only commands applicable to changed code and report exact outcomes.

Test steps / expected result: All edge cases match documented behavior. Success means the target is present, tests pass, and failure behavior is understandable.

Common errors: If the DB is unavailable, verify PostgreSQL service, database name, credentials, and env loading. If imports/routes fail, check app registration and URL inclusion. If an API/UI mismatch appears, compare against docs/api-contract.md and correct the contract or implementation deliberately; do not patch around it.

Git milestone: After review and passing tests, commit only this task. Suggested: `git add <reviewed-files> && git commit -m "PRODUCT-05: add product api validation and permission tests"`. Use a feature branch only when it helps isolate a risky/long feature; no empty commits.

Viva questions: 1. What requirement does PRODUCT-05 satisfy? 2. Which data/API/UI boundary does it change? 3. How is invalid or unauthorized input handled? 4. What test proves it works? 5. What limitation remains?

Definition of Done: ☐ Scope met  ☐ Code understood  ☐ Focused tests pass  ☐ No unrelated changes  ☐ Evidence recorded  ☐ Commit created  ☐ Docs updated if affected  ☐ Viva explanation ready

## PRODUCT-06 — Build product list and form UI

Proposal lead / workstream assignment: Rukaiya Akther Trisha — follows the proposal split; this is a planned role, not a contribution record.

Hands-on operator: Monira Islam (you) — you will carry out every task, including tasks assigned to the frontend/UI workstream.

Requirement: Seller needs to manage catalogue through accessible screens.

Target: Product list, search/filter, create/edit form, and user feedback states exist.

Why this task matters: Product list, search/filter, create/edit form, and user feedback states exist. It isolates one change so the student can inspect, test, and explain it before moving on.

Prerequisites: PRODUCT-02; BACKEND-05; FRONTEND-03

Concepts to understand: Form validation; accessible tables; responsive layout.

Expected files/modules: frontend/src/features/products; tests.

Implementation scope: Use shared components and agreed field contract; no analytics widgets.

Not in this task: Other modules, unrelated refactors, new dependencies, and unapproved features.

Ready-to-paste Codex prompt

You are implementing SellerOS, the SE-331 standalone social-commerce seller BI/decision-support capstone. Implement only PRODUCT-06 — Build product list and form UI. Requirement: Seller needs to manage catalogue through accessible screens. Objective/acceptance target: Product list, search/filter, create/edit form, and user feedback states exist. Scope allowed: Use shared components and agreed field contract; no analytics widgets. Likely files/modules: frontend/src/features/products; tests. Prerequisites: PRODUCT-02; BACKEND-05; FRONTEND-03. Constraints: follow the approved React/Vite/TypeScript + Django/DRF + PostgreSQL architecture and existing API/data contracts; inspect the repository first; preserve existing working behavior; do not invent unresolved business rules—mark [DECISION REQUIRED]; do not modify unrelated files, add unnecessary dependencies, expose secrets, bypass authentication/store permissions, fabricate AI/ML results, or create autonomous actions. Out of scope for this task: Other modules, unrelated refactors, new dependencies, and unapproved features. Test requirement: UI tests cover empty/loading/error/validation/success. Run the narrow relevant checks and report exact commands and outcomes. Expected output: focused implementation, meaningful tests, and concise notes on files changed, decisions, risks, and next dependency. Code quality: small readable changes, type/validation/error handling appropriate to the existing project, no duplicated business formulas, and no generated or sensitive data committed.

Expected Codex output: A focused change for PRODUCT-06, relevant tests, a file-change summary, and exact commands/results. No unrelated implementation.

How to inspect: Review the diff for these boundaries: Use shared components and agreed field contract; no analytics widgets. Confirm only expected files changed, validation/permissions match the contract, and tests exercise the requirement.

How to understand: Explain in your own words how Form validation; accessible tables; responsive layout. support this task; trace one normal case and one failure case through the code.

Run commands: Use verified environment commands from SETUP-07. Typical checks: backend: `python manage.py check` and the focused Django test module; frontend: `npm run lint`, focused test, and `npm run build`. Run only commands applicable to changed code and report exact outcomes.

Test steps / expected result: UI tests cover empty/loading/error/validation/success. Success means the target is present, tests pass, and failure behavior is understandable.

Common errors: If the DB is unavailable, verify PostgreSQL service, database name, credentials, and env loading. If imports/routes fail, check app registration and URL inclusion. If an API/UI mismatch appears, compare against docs/api-contract.md and correct the contract or implementation deliberately; do not patch around it.

Git milestone: After review and passing tests, commit only this task. Suggested: `git add <reviewed-files> && git commit -m "PRODUCT-06: build product list and form ui"`. Use a feature branch only when it helps isolate a risky/long feature; no empty commits.

Viva questions: 1. What requirement does PRODUCT-06 satisfy? 2. Which data/API/UI boundary does it change? 3. How is invalid or unauthorized input handled? 4. What test proves it works? 5. What limitation remains?

Definition of Done: ☐ Scope met  ☐ Code understood  ☐ Focused tests pass  ☐ No unrelated changes  ☐ Evidence recorded  ☐ Commit created  ☐ Docs updated if affected  ☐ Viva explanation ready

## PRODUCT-07 — Connect product screens and verify workflow

Proposal lead / workstream assignment: Rukaiya Akther Trisha — follows the proposal split; this is a planned role, not a contribution record.

Hands-on operator: Monira Islam (you) — you will carry out every task, including tasks assigned to the frontend/UI workstream.

Requirement: Frontend and API need verified integration.

Target: Seller can create, view, edit, and deactivate products through real API.

Why this task matters: Seller can create, view, edit, and deactivate products through real API. It isolates one change so the student can inspect, test, and explain it before moving on.

Prerequisites: PRODUCT-06

Concepts to understand: TanStack Query cache; mutation invalidation; error mapping.

Expected files/modules: frontend product feature; e2e tests.

Implementation scope: Wire UI to documented contract; record integration issues and fix only within scope.

Not in this task: Other modules, unrelated refactors, new dependencies, and unapproved features.

Ready-to-paste Codex prompt

You are implementing SellerOS, the SE-331 standalone social-commerce seller BI/decision-support capstone. Implement only PRODUCT-07 — Connect product screens and verify workflow. Requirement: Frontend and API need verified integration. Objective/acceptance target: Seller can create, view, edit, and deactivate products through real API. Scope allowed: Wire UI to documented contract; record integration issues and fix only within scope. Likely files/modules: frontend product feature; e2e tests. Prerequisites: PRODUCT-06. Constraints: follow the approved React/Vite/TypeScript + Django/DRF + PostgreSQL architecture and existing API/data contracts; inspect the repository first; preserve existing working behavior; do not invent unresolved business rules—mark [DECISION REQUIRED]; do not modify unrelated files, add unnecessary dependencies, expose secrets, bypass authentication/store permissions, fabricate AI/ML results, or create autonomous actions. Out of scope for this task: Other modules, unrelated refactors, new dependencies, and unapproved features. Test requirement: End-to-end product flow passes. Run the narrow relevant checks and report exact commands and outcomes. Expected output: focused implementation, meaningful tests, and concise notes on files changed, decisions, risks, and next dependency. Code quality: small readable changes, type/validation/error handling appropriate to the existing project, no duplicated business formulas, and no generated or sensitive data committed.

Expected Codex output: A focused change for PRODUCT-07, relevant tests, a file-change summary, and exact commands/results. No unrelated implementation.

How to inspect: Review the diff for these boundaries: Wire UI to documented contract; record integration issues and fix only within scope. Confirm only expected files changed, validation/permissions match the contract, and tests exercise the requirement.

How to understand: Explain in your own words how TanStack Query cache; mutation invalidation; error mapping. support this task; trace one normal case and one failure case through the code.

Run commands: Use verified environment commands from SETUP-07. Typical checks: backend: `python manage.py check` and the focused Django test module; frontend: `npm run lint`, focused test, and `npm run build`. Run only commands applicable to changed code and report exact outcomes.

Test steps / expected result: End-to-end product flow passes. Success means the target is present, tests pass, and failure behavior is understandable.

Common errors: If the DB is unavailable, verify PostgreSQL service, database name, credentials, and env loading. If imports/routes fail, check app registration and URL inclusion. If an API/UI mismatch appears, compare against docs/api-contract.md and correct the contract or implementation deliberately; do not patch around it.

Git milestone: After review and passing tests, commit only this task. Suggested: `git add <reviewed-files> && git commit -m "PRODUCT-07: connect product screens and verify workflow"`. Use a feature branch only when it helps isolate a risky/long feature; no empty commits.

Viva questions: 1. What requirement does PRODUCT-07 satisfy? 2. Which data/API/UI boundary does it change? 3. How is invalid or unauthorized input handled? 4. What test proves it works? 5. What limitation remains?

Definition of Done: ☐ Scope met  ☐ Code understood  ☐ Focused tests pass  ☐ No unrelated changes  ☐ Evidence recorded  ☐ Commit created  ☐ Docs updated if affected  ☐ Viva explanation ready

# Phase 6 — Inventory

Make every quantity change traceable and transaction-safe.

## INV-01 — Create inventory movement model and low-stock rule

Proposal lead / workstream assignment: Monira Islam — follows the proposal split; this is a planned role, not a contribution record.

Hands-on operator: Monira Islam (you) — you will carry out every task, including tasks assigned to the frontend/UI workstream.

Requirement: Stock history and seller-defined reorder threshold are in scope.

Target: Movement ledger and threshold fields follow approved data model.

Why this task matters: Movement ledger and threshold fields follow approved data model. It isolates one change so the student can inspect, test, and explain it before moving on.

Prerequisites: None beyond repository inspection and the approved project baseline.

Concepts to understand: Ledger; aggregate state; constraints; decimal/integer units.

Expected files/modules: backend/apps/inventory/models; migrations; tests.

Implementation scope: Agree whether product quantity is derived or cached; document consistency rule.

Not in this task: Other modules, unrelated refactors, new dependencies, and unapproved features.

Ready-to-paste Codex prompt

You are implementing SellerOS, the SE-331 standalone social-commerce seller BI/decision-support capstone. Implement only INV-01 — Create inventory movement model and low-stock rule. Requirement: Stock history and seller-defined reorder threshold are in scope. Objective/acceptance target: Movement ledger and threshold fields follow approved data model. Scope allowed: Agree whether product quantity is derived or cached; document consistency rule. Likely files/modules: backend/apps/inventory/models; migrations; tests. Prerequisites: none beyond the approved project baseline. Constraints: follow the approved React/Vite/TypeScript + Django/DRF + PostgreSQL architecture and existing API/data contracts; inspect the repository first; preserve existing working behavior; do not invent unresolved business rules—mark [DECISION REQUIRED]; do not modify unrelated files, add unnecessary dependencies, expose secrets, bypass authentication/store permissions, fabricate AI/ML results, or create autonomous actions. Out of scope for this task: Other modules, unrelated refactors, new dependencies, and unapproved features. Test requirement: Model tests enforce valid movements and store ownership. Run the narrow relevant checks and report exact commands and outcomes. Expected output: focused implementation, meaningful tests, and concise notes on files changed, decisions, risks, and next dependency. Code quality: small readable changes, type/validation/error handling appropriate to the existing project, no duplicated business formulas, and no generated or sensitive data committed.

Expected Codex output: A focused change for INV-01, relevant tests, a file-change summary, and exact commands/results. No unrelated implementation.

How to inspect: Review the diff for these boundaries: Agree whether product quantity is derived or cached; document consistency rule. Confirm only expected files changed, validation/permissions match the contract, and tests exercise the requirement.

How to understand: Explain in your own words how Ledger; aggregate state; constraints; decimal/integer units. support this task; trace one normal case and one failure case through the code.

Run commands: Use verified environment commands from SETUP-07. Typical checks: backend: `python manage.py check` and the focused Django test module; frontend: `npm run lint`, focused test, and `npm run build`. Run only commands applicable to changed code and report exact outcomes.

Test steps / expected result: Model tests enforce valid movements and store ownership. Success means the target is present, tests pass, and failure behavior is understandable.

Common errors: If the DB is unavailable, verify PostgreSQL service, database name, credentials, and env loading. If imports/routes fail, check app registration and URL inclusion. If an API/UI mismatch appears, compare against docs/api-contract.md and correct the contract or implementation deliberately; do not patch around it.

Git milestone: After review and passing tests, commit only this task. Suggested: `git add <reviewed-files> && git commit -m "INV-01: create inventory movement model and low-stock rule"`. Use a feature branch only when it helps isolate a risky/long feature; no empty commits.

Viva questions: 1. What requirement does INV-01 satisfy? 2. Which data/API/UI boundary does it change? 3. How is invalid or unauthorized input handled? 4. What test proves it works? 5. What limitation remains?

Definition of Done: ☐ Scope met  ☐ Code understood  ☐ Focused tests pass  ☐ No unrelated changes  ☐ Evidence recorded  ☐ Commit created  ☐ Docs updated if affected  ☐ Viva explanation ready

## INV-02 — Implement atomic stock adjustment service

Proposal lead / workstream assignment: Monira Islam — follows the proposal split; this is a planned role, not a contribution record.

Hands-on operator: Monira Islam (you) — you will carry out every task, including tasks assigned to the frontend/UI workstream.

Requirement: Concurrent or failed updates must not corrupt quantities.

Target: Stock adjustments update quantity and movement history atomically.

Why this task matters: Stock adjustments update quantity and movement history atomically. It isolates one change so the student can inspect, test, and explain it before moving on.

Prerequisites: INV-01

Concepts to understand: Database transaction; locking; rollback; idempotency.

Expected files/modules: backend/apps/inventory/services; tests.

Implementation scope: Create service-layer transaction and reject invalid negative/overdraw states per decision.

Not in this task: Other modules, unrelated refactors, new dependencies, and unapproved features.

Ready-to-paste Codex prompt

You are implementing SellerOS, the SE-331 standalone social-commerce seller BI/decision-support capstone. Implement only INV-02 — Implement atomic stock adjustment service. Requirement: Concurrent or failed updates must not corrupt quantities. Objective/acceptance target: Stock adjustments update quantity and movement history atomically. Scope allowed: Create service-layer transaction and reject invalid negative/overdraw states per decision. Likely files/modules: backend/apps/inventory/services; tests. Prerequisites: INV-01. Constraints: follow the approved React/Vite/TypeScript + Django/DRF + PostgreSQL architecture and existing API/data contracts; inspect the repository first; preserve existing working behavior; do not invent unresolved business rules—mark [DECISION REQUIRED]; do not modify unrelated files, add unnecessary dependencies, expose secrets, bypass authentication/store permissions, fabricate AI/ML results, or create autonomous actions. Out of scope for this task: Other modules, unrelated refactors, new dependencies, and unapproved features. Test requirement: Success changes both records; failure changes neither. Run the narrow relevant checks and report exact commands and outcomes. Expected output: focused implementation, meaningful tests, and concise notes on files changed, decisions, risks, and next dependency. Code quality: small readable changes, type/validation/error handling appropriate to the existing project, no duplicated business formulas, and no generated or sensitive data committed.

Expected Codex output: A focused change for INV-02, relevant tests, a file-change summary, and exact commands/results. No unrelated implementation.

How to inspect: Review the diff for these boundaries: Create service-layer transaction and reject invalid negative/overdraw states per decision. Confirm only expected files changed, validation/permissions match the contract, and tests exercise the requirement.

How to understand: Explain in your own words how Database transaction; locking; rollback; idempotency. support this task; trace one normal case and one failure case through the code.

Run commands: Use verified environment commands from SETUP-07. Typical checks: backend: `python manage.py check` and the focused Django test module; frontend: `npm run lint`, focused test, and `npm run build`. Run only commands applicable to changed code and report exact outcomes.

Test steps / expected result: Success changes both records; failure changes neither. Success means the target is present, tests pass, and failure behavior is understandable.

Common errors: If the DB is unavailable, verify PostgreSQL service, database name, credentials, and env loading. If imports/routes fail, check app registration and URL inclusion. If an API/UI mismatch appears, compare against docs/api-contract.md and correct the contract or implementation deliberately; do not patch around it.

Git milestone: After review and passing tests, commit only this task. Suggested: `git add <reviewed-files> && git commit -m "INV-02: implement atomic stock adjustment service"`. Use a feature branch only when it helps isolate a risky/long feature; no empty commits.

Viva questions: 1. What requirement does INV-02 satisfy? 2. Which data/API/UI boundary does it change? 3. How is invalid or unauthorized input handled? 4. What test proves it works? 5. What limitation remains?

Definition of Done: ☐ Scope met  ☐ Code understood  ☐ Focused tests pass  ☐ No unrelated changes  ☐ Evidence recorded  ☐ Commit created  ☐ Docs updated if affected  ☐ Viva explanation ready

## INV-03 — Add inventory list and adjustment APIs

Proposal lead / workstream assignment: Monira Islam — follows the proposal split; this is a planned role, not a contribution record.

Hands-on operator: Monira Islam (you) — you will carry out every task, including tasks assigned to the frontend/UI workstream.

Requirement: Seller needs to view stock and record manual adjustment reasons.

Target: Store-scoped stock APIs expose current quantity, threshold, and movement history.

Why this task matters: Store-scoped stock APIs expose current quantity, threshold, and movement history. It isolates one change so the student can inspect, test, and explain it before moving on.

Prerequisites: INV-02

Concepts to understand: API design; permission checks; audit trail.

Expected files/modules: backend/apps/inventory/api; URLs; tests.

Implementation scope: Follow API contract and validation; do not alter stock outside service.

Not in this task: Other modules, unrelated refactors, new dependencies, and unapproved features.

Ready-to-paste Codex prompt

You are implementing SellerOS, the SE-331 standalone social-commerce seller BI/decision-support capstone. Implement only INV-03 — Add inventory list and adjustment APIs. Requirement: Seller needs to view stock and record manual adjustment reasons. Objective/acceptance target: Store-scoped stock APIs expose current quantity, threshold, and movement history. Scope allowed: Follow API contract and validation; do not alter stock outside service. Likely files/modules: backend/apps/inventory/api; URLs; tests. Prerequisites: INV-02. Constraints: follow the approved React/Vite/TypeScript + Django/DRF + PostgreSQL architecture and existing API/data contracts; inspect the repository first; preserve existing working behavior; do not invent unresolved business rules—mark [DECISION REQUIRED]; do not modify unrelated files, add unnecessary dependencies, expose secrets, bypass authentication/store permissions, fabricate AI/ML results, or create autonomous actions. Out of scope for this task: Other modules, unrelated refactors, new dependencies, and unapproved features. Test requirement: Read/adjust/history tests include cross-store denial. Run the narrow relevant checks and report exact commands and outcomes. Expected output: focused implementation, meaningful tests, and concise notes on files changed, decisions, risks, and next dependency. Code quality: small readable changes, type/validation/error handling appropriate to the existing project, no duplicated business formulas, and no generated or sensitive data committed.

Expected Codex output: A focused change for INV-03, relevant tests, a file-change summary, and exact commands/results. No unrelated implementation.

How to inspect: Review the diff for these boundaries: Follow API contract and validation; do not alter stock outside service. Confirm only expected files changed, validation/permissions match the contract, and tests exercise the requirement.

How to understand: Explain in your own words how API design; permission checks; audit trail. support this task; trace one normal case and one failure case through the code.

Run commands: Use verified environment commands from SETUP-07. Typical checks: backend: `python manage.py check` and the focused Django test module; frontend: `npm run lint`, focused test, and `npm run build`. Run only commands applicable to changed code and report exact outcomes.

Test steps / expected result: Read/adjust/history tests include cross-store denial. Success means the target is present, tests pass, and failure behavior is understandable.

Common errors: If the DB is unavailable, verify PostgreSQL service, database name, credentials, and env loading. If imports/routes fail, check app registration and URL inclusion. If an API/UI mismatch appears, compare against docs/api-contract.md and correct the contract or implementation deliberately; do not patch around it.

Git milestone: After review and passing tests, commit only this task. Suggested: `git add <reviewed-files> && git commit -m "INV-03: add inventory list and adjustment apis"`. Use a feature branch only when it helps isolate a risky/long feature; no empty commits.

Viva questions: 1. What requirement does INV-03 satisfy? 2. Which data/API/UI boundary does it change? 3. How is invalid or unauthorized input handled? 4. What test proves it works? 5. What limitation remains?

Definition of Done: ☐ Scope met  ☐ Code understood  ☐ Focused tests pass  ☐ No unrelated changes  ☐ Evidence recorded  ☐ Commit created  ☐ Docs updated if affected  ☐ Viva explanation ready

## INV-04 — Build inventory and low-stock UI

Proposal lead / workstream assignment: Rukaiya Akther Trisha — follows the proposal split; this is a planned role, not a contribution record.

Hands-on operator: Monira Islam (you) — you will carry out every task, including tasks assigned to the frontend/UI workstream.

Requirement: Seller must review stock and act on low-stock warnings.

Target: Inventory table, adjustment form, history, and threshold state are usable.

Why this task matters: Inventory table, adjustment form, history, and threshold state are usable. It isolates one change so the student can inspect, test, and explain it before moving on.

Prerequisites: INV-03; BACKEND-05; FRONTEND-03

Concepts to understand: Accessible data table; form; status indicators.

Expected files/modules: frontend/src/features/inventory; tests.

Implementation scope: Display exact units and confirmation; no automatic restock action.

Not in this task: Other modules, unrelated refactors, new dependencies, and unapproved features.

Ready-to-paste Codex prompt

You are implementing SellerOS, the SE-331 standalone social-commerce seller BI/decision-support capstone. Implement only INV-04 — Build inventory and low-stock UI. Requirement: Seller must review stock and act on low-stock warnings. Objective/acceptance target: Inventory table, adjustment form, history, and threshold state are usable. Scope allowed: Display exact units and confirmation; no automatic restock action. Likely files/modules: frontend/src/features/inventory; tests. Prerequisites: INV-03; BACKEND-05; FRONTEND-03. Constraints: follow the approved React/Vite/TypeScript + Django/DRF + PostgreSQL architecture and existing API/data contracts; inspect the repository first; preserve existing working behavior; do not invent unresolved business rules—mark [DECISION REQUIRED]; do not modify unrelated files, add unnecessary dependencies, expose secrets, bypass authentication/store permissions, fabricate AI/ML results, or create autonomous actions. Out of scope for this task: Other modules, unrelated refactors, new dependencies, and unapproved features. Test requirement: UI handles zero stock, low stock, empty, and API error. Run the narrow relevant checks and report exact commands and outcomes. Expected output: focused implementation, meaningful tests, and concise notes on files changed, decisions, risks, and next dependency. Code quality: small readable changes, type/validation/error handling appropriate to the existing project, no duplicated business formulas, and no generated or sensitive data committed.

Expected Codex output: A focused change for INV-04, relevant tests, a file-change summary, and exact commands/results. No unrelated implementation.

How to inspect: Review the diff for these boundaries: Display exact units and confirmation; no automatic restock action. Confirm only expected files changed, validation/permissions match the contract, and tests exercise the requirement.

How to understand: Explain in your own words how Accessible data table; form; status indicators. support this task; trace one normal case and one failure case through the code.

Run commands: Use verified environment commands from SETUP-07. Typical checks: backend: `python manage.py check` and the focused Django test module; frontend: `npm run lint`, focused test, and `npm run build`. Run only commands applicable to changed code and report exact outcomes.

Test steps / expected result: UI handles zero stock, low stock, empty, and API error. Success means the target is present, tests pass, and failure behavior is understandable.

Common errors: If the DB is unavailable, verify PostgreSQL service, database name, credentials, and env loading. If imports/routes fail, check app registration and URL inclusion. If an API/UI mismatch appears, compare against docs/api-contract.md and correct the contract or implementation deliberately; do not patch around it.

Git milestone: After review and passing tests, commit only this task. Suggested: `git add <reviewed-files> && git commit -m "INV-04: build inventory and low-stock ui"`. Use a feature branch only when it helps isolate a risky/long feature; no empty commits.

Viva questions: 1. What requirement does INV-04 satisfy? 2. Which data/API/UI boundary does it change? 3. How is invalid or unauthorized input handled? 4. What test proves it works? 5. What limitation remains?

Definition of Done: ☐ Scope met  ☐ Code understood  ☐ Focused tests pass  ☐ No unrelated changes  ☐ Evidence recorded  ☐ Commit created  ☐ Docs updated if affected  ☐ Viva explanation ready

## INV-05 — Verify product-to-inventory integration

Proposal lead / workstream assignment: Jointly assigned to Monira Islam and Rukaiya Akther Trisha — follows the proposal split; this is a planned role, not a contribution record.

Hands-on operator: Monira Islam (you) — you will carry out every task, including tasks assigned to the frontend/UI workstream.

Requirement: Product and inventory views must present consistent values.

Target: A product created/updated through catalogue appears correctly in inventory.

Why this task matters: A product created/updated through catalogue appears correctly in inventory. It isolates one change so the student can inspect, test, and explain it before moving on.

Prerequisites: INV-04

Concepts to understand: Cross-module contract; transactional invariants.

Expected files/modules: backend integration; frontend e2e.

Implementation scope: Test service/API/UI consistency and edge cases.

Not in this task: Other modules, unrelated refactors, new dependencies, and unapproved features.

Ready-to-paste Codex prompt

You are implementing SellerOS, the SE-331 standalone social-commerce seller BI/decision-support capstone. Implement only INV-05 — Verify product-to-inventory integration. Requirement: Product and inventory views must present consistent values. Objective/acceptance target: A product created/updated through catalogue appears correctly in inventory. Scope allowed: Test service/API/UI consistency and edge cases. Likely files/modules: backend integration; frontend e2e. Prerequisites: INV-04. Constraints: follow the approved React/Vite/TypeScript + Django/DRF + PostgreSQL architecture and existing API/data contracts; inspect the repository first; preserve existing working behavior; do not invent unresolved business rules—mark [DECISION REQUIRED]; do not modify unrelated files, add unnecessary dependencies, expose secrets, bypass authentication/store permissions, fabricate AI/ML results, or create autonomous actions. Out of scope for this task: Other modules, unrelated refactors, new dependencies, and unapproved features. Test requirement: Inventory checkpoint passes with movement history evidence. Run the narrow relevant checks and report exact commands and outcomes. Expected output: focused implementation, meaningful tests, and concise notes on files changed, decisions, risks, and next dependency. Code quality: small readable changes, type/validation/error handling appropriate to the existing project, no duplicated business formulas, and no generated or sensitive data committed.

Expected Codex output: A focused change for INV-05, relevant tests, a file-change summary, and exact commands/results. No unrelated implementation.

How to inspect: Review the diff for these boundaries: Test service/API/UI consistency and edge cases. Confirm only expected files changed, validation/permissions match the contract, and tests exercise the requirement.

How to understand: Explain in your own words how Cross-module contract; transactional invariants. support this task; trace one normal case and one failure case through the code.

Run commands: Use verified environment commands from SETUP-07. Typical checks: backend: `python manage.py check` and the focused Django test module; frontend: `npm run lint`, focused test, and `npm run build`. Run only commands applicable to changed code and report exact outcomes.

Test steps / expected result: Inventory checkpoint passes with movement history evidence. Success means the target is present, tests pass, and failure behavior is understandable.

Common errors: If the DB is unavailable, verify PostgreSQL service, database name, credentials, and env loading. If imports/routes fail, check app registration and URL inclusion. If an API/UI mismatch appears, compare against docs/api-contract.md and correct the contract or implementation deliberately; do not patch around it.

Git milestone: After review and passing tests, commit only this task. Suggested: `git add <reviewed-files> && git commit -m "INV-05: verify product-to-inventory integration"`. Use a feature branch only when it helps isolate a risky/long feature; no empty commits.

Viva questions: 1. What requirement does INV-05 satisfy? 2. Which data/API/UI boundary does it change? 3. How is invalid or unauthorized input handled? 4. What test proves it works? 5. What limitation remains?

Definition of Done: ☐ Scope met  ☐ Code understood  ☐ Focused tests pass  ☐ No unrelated changes  ☐ Evidence recorded  ☐ Commit created  ☐ Docs updated if affected  ☐ Viva explanation ready

## INV-06 — Test stock concurrency and rollback boundaries

Proposal lead / workstream assignment: Jointly assigned to Monira Islam and Rukaiya Akther Trisha — follows the proposal split; this is a planned role, not a contribution record.

Hands-on operator: Monira Islam (you) — you will carry out every task, including tasks assigned to the frontend/UI workstream.

Requirement: Order workflows will depend on reliable inventory updates.

Target: Concurrent adjustments and failed transactions leave a valid ledger and quantity.

Why this task matters: Concurrent adjustments and failed transactions leave a valid ledger and quantity. It isolates one change so the student can inspect, test, and explain it before moving on.

Prerequisites: INV-05

Concepts to understand: Concurrency; isolation; rollback.

Expected files/modules: backend/apps/inventory/tests.

Implementation scope: Use database transaction tests; document local test limits.

Not in this task: Other modules, unrelated refactors, new dependencies, and unapproved features.

Ready-to-paste Codex prompt

You are implementing SellerOS, the SE-331 standalone social-commerce seller BI/decision-support capstone. Implement only INV-06 — Test stock concurrency and rollback boundaries. Requirement: Order workflows will depend on reliable inventory updates. Objective/acceptance target: Concurrent adjustments and failed transactions leave a valid ledger and quantity. Scope allowed: Use database transaction tests; document local test limits. Likely files/modules: backend/apps/inventory/tests. Prerequisites: INV-05. Constraints: follow the approved React/Vite/TypeScript + Django/DRF + PostgreSQL architecture and existing API/data contracts; inspect the repository first; preserve existing working behavior; do not invent unresolved business rules—mark [DECISION REQUIRED]; do not modify unrelated files, add unnecessary dependencies, expose secrets, bypass authentication/store permissions, fabricate AI/ML results, or create autonomous actions. Out of scope for this task: Other modules, unrelated refactors, new dependencies, and unapproved features. Test requirement: No lost update or partial movement under covered scenarios. Run the narrow relevant checks and report exact commands and outcomes. Expected output: focused implementation, meaningful tests, and concise notes on files changed, decisions, risks, and next dependency. Code quality: small readable changes, type/validation/error handling appropriate to the existing project, no duplicated business formulas, and no generated or sensitive data committed.

Expected Codex output: A focused change for INV-06, relevant tests, a file-change summary, and exact commands/results. No unrelated implementation.

How to inspect: Review the diff for these boundaries: Use database transaction tests; document local test limits. Confirm only expected files changed, validation/permissions match the contract, and tests exercise the requirement.

How to understand: Explain in your own words how Concurrency; isolation; rollback. support this task; trace one normal case and one failure case through the code.

Run commands: Use verified environment commands from SETUP-07. Typical checks: backend: `python manage.py check` and the focused Django test module; frontend: `npm run lint`, focused test, and `npm run build`. Run only commands applicable to changed code and report exact outcomes.

Test steps / expected result: No lost update or partial movement under covered scenarios. Success means the target is present, tests pass, and failure behavior is understandable.

Common errors: If the DB is unavailable, verify PostgreSQL service, database name, credentials, and env loading. If imports/routes fail, check app registration and URL inclusion. If an API/UI mismatch appears, compare against docs/api-contract.md and correct the contract or implementation deliberately; do not patch around it.

Git milestone: After review and passing tests, commit only this task. Suggested: `git add <reviewed-files> && git commit -m "INV-06: test stock concurrency and rollback boundaries"`. Use a feature branch only when it helps isolate a risky/long feature; no empty commits.

Viva questions: 1. What requirement does INV-06 satisfy? 2. Which data/API/UI boundary does it change? 3. How is invalid or unauthorized input handled? 4. What test proves it works? 5. What limitation remains?

Definition of Done: ☐ Scope met  ☐ Code understood  ☐ Focused tests pass  ☐ No unrelated changes  ☐ Evidence recorded  ☐ Commit created  ☐ Docs updated if affected  ☐ Viva explanation ready

# Phase 7 — Customers and orders

Implement linked purchases and status transitions based on approved business rules.

## CUSTOMER-01 — Create customer model and store-scoped validation

Proposal lead / workstream assignment: Monira Islam — follows the proposal split; this is a planned role, not a contribution record.

Hands-on operator: Monira Islam (you) — you will carry out every task, including tasks assigned to the frontend/UI workstream.

Requirement: Customer profile and order history are in scope.

Target: Customer records store only necessary seller-entered data and store ownership.

Why this task matters: Customer records store only necessary seller-entered data and store ownership. It isolates one change so the student can inspect, test, and explain it before moving on.

Prerequisites: None beyond repository inspection and the approved project baseline.

Concepts to understand: PII minimization; nullable fields; tenant ownership.

Expected files/modules: backend/apps/customers/models; migration; tests.

Implementation scope: Finalize minimal fields and optional contact handling; avoid sensitive profiling.

Not in this task: Other modules, unrelated refactors, new dependencies, and unapproved features.

Ready-to-paste Codex prompt

You are implementing SellerOS, the SE-331 standalone social-commerce seller BI/decision-support capstone. Implement only CUSTOMER-01 — Create customer model and store-scoped validation. Requirement: Customer profile and order history are in scope. Objective/acceptance target: Customer records store only necessary seller-entered data and store ownership. Scope allowed: Finalize minimal fields and optional contact handling; avoid sensitive profiling. Likely files/modules: backend/apps/customers/models; migration; tests. Prerequisites: none beyond the approved project baseline. Constraints: follow the approved React/Vite/TypeScript + Django/DRF + PostgreSQL architecture and existing API/data contracts; inspect the repository first; preserve existing working behavior; do not invent unresolved business rules—mark [DECISION REQUIRED]; do not modify unrelated files, add unnecessary dependencies, expose secrets, bypass authentication/store permissions, fabricate AI/ML results, or create autonomous actions. Out of scope for this task: Other modules, unrelated refactors, new dependencies, and unapproved features. Test requirement: Model tests cover required data and store isolation. Run the narrow relevant checks and report exact commands and outcomes. Expected output: focused implementation, meaningful tests, and concise notes on files changed, decisions, risks, and next dependency. Code quality: small readable changes, type/validation/error handling appropriate to the existing project, no duplicated business formulas, and no generated or sensitive data committed.

Expected Codex output: A focused change for CUSTOMER-01, relevant tests, a file-change summary, and exact commands/results. No unrelated implementation.

How to inspect: Review the diff for these boundaries: Finalize minimal fields and optional contact handling; avoid sensitive profiling. Confirm only expected files changed, validation/permissions match the contract, and tests exercise the requirement.

How to understand: Explain in your own words how PII minimization; nullable fields; tenant ownership. support this task; trace one normal case and one failure case through the code.

Run commands: Use verified environment commands from SETUP-07. Typical checks: backend: `python manage.py check` and the focused Django test module; frontend: `npm run lint`, focused test, and `npm run build`. Run only commands applicable to changed code and report exact outcomes.

Test steps / expected result: Model tests cover required data and store isolation. Success means the target is present, tests pass, and failure behavior is understandable.

Common errors: If the DB is unavailable, verify PostgreSQL service, database name, credentials, and env loading. If imports/routes fail, check app registration and URL inclusion. If an API/UI mismatch appears, compare against docs/api-contract.md and correct the contract or implementation deliberately; do not patch around it.

Git milestone: After review and passing tests, commit only this task. Suggested: `git add <reviewed-files> && git commit -m "CUSTOMER-01: create customer model and store-scoped validation"`. Use a feature branch only when it helps isolate a risky/long feature; no empty commits.

Viva questions: 1. What requirement does CUSTOMER-01 satisfy? 2. Which data/API/UI boundary does it change? 3. How is invalid or unauthorized input handled? 4. What test proves it works? 5. What limitation remains?

Definition of Done: ☐ Scope met  ☐ Code understood  ☐ Focused tests pass  ☐ No unrelated changes  ☐ Evidence recorded  ☐ Commit created  ☐ Docs updated if affected  ☐ Viva explanation ready

## CUSTOMER-02 — Implement customer list, detail, create, and update APIs

Proposal lead / workstream assignment: Monira Islam — follows the proposal split; this is a planned role, not a contribution record.

Hands-on operator: Monira Islam (you) — you will carry out every task, including tasks assigned to the frontend/UI workstream.

Requirement: Seller needs to maintain customer records.

Target: Customer CRUD API follows shared filters, errors, and permissions.

Why this task matters: Customer CRUD API follows shared filters, errors, and permissions. It isolates one change so the student can inspect, test, and explain it before moving on.

Prerequisites: CUSTOMER-01

Concepts to understand: CRUD; validation; pagination; permission.

Expected files/modules: backend/apps/customers/api; serializers; tests.

Implementation scope: Add duplicate/contact rules only if approved; paginate list.

Not in this task: Other modules, unrelated refactors, new dependencies, and unapproved features.

Ready-to-paste Codex prompt

You are implementing SellerOS, the SE-331 standalone social-commerce seller BI/decision-support capstone. Implement only CUSTOMER-02 — Implement customer list, detail, create, and update APIs. Requirement: Seller needs to maintain customer records. Objective/acceptance target: Customer CRUD API follows shared filters, errors, and permissions. Scope allowed: Add duplicate/contact rules only if approved; paginate list. Likely files/modules: backend/apps/customers/api; serializers; tests. Prerequisites: CUSTOMER-01. Constraints: follow the approved React/Vite/TypeScript + Django/DRF + PostgreSQL architecture and existing API/data contracts; inspect the repository first; preserve existing working behavior; do not invent unresolved business rules—mark [DECISION REQUIRED]; do not modify unrelated files, add unnecessary dependencies, expose secrets, bypass authentication/store permissions, fabricate AI/ML results, or create autonomous actions. Out of scope for this task: Other modules, unrelated refactors, new dependencies, and unapproved features. Test requirement: API test matrix passes for each method. Run the narrow relevant checks and report exact commands and outcomes. Expected output: focused implementation, meaningful tests, and concise notes on files changed, decisions, risks, and next dependency. Code quality: small readable changes, type/validation/error handling appropriate to the existing project, no duplicated business formulas, and no generated or sensitive data committed.

Expected Codex output: A focused change for CUSTOMER-02, relevant tests, a file-change summary, and exact commands/results. No unrelated implementation.

How to inspect: Review the diff for these boundaries: Add duplicate/contact rules only if approved; paginate list. Confirm only expected files changed, validation/permissions match the contract, and tests exercise the requirement.

How to understand: Explain in your own words how CRUD; validation; pagination; permission. support this task; trace one normal case and one failure case through the code.

Run commands: Use verified environment commands from SETUP-07. Typical checks: backend: `python manage.py check` and the focused Django test module; frontend: `npm run lint`, focused test, and `npm run build`. Run only commands applicable to changed code and report exact outcomes.

Test steps / expected result: API test matrix passes for each method. Success means the target is present, tests pass, and failure behavior is understandable.

Common errors: If the DB is unavailable, verify PostgreSQL service, database name, credentials, and env loading. If imports/routes fail, check app registration and URL inclusion. If an API/UI mismatch appears, compare against docs/api-contract.md and correct the contract or implementation deliberately; do not patch around it.

Git milestone: After review and passing tests, commit only this task. Suggested: `git add <reviewed-files> && git commit -m "CUSTOMER-02: implement customer list, detail, create, and update apis"`. Use a feature branch only when it helps isolate a risky/long feature; no empty commits.

Viva questions: 1. What requirement does CUSTOMER-02 satisfy? 2. Which data/API/UI boundary does it change? 3. How is invalid or unauthorized input handled? 4. What test proves it works? 5. What limitation remains?

Definition of Done: ☐ Scope met  ☐ Code understood  ☐ Focused tests pass  ☐ No unrelated changes  ☐ Evidence recorded  ☐ Commit created  ☐ Docs updated if affected  ☐ Viva explanation ready

## CUSTOMER-03 — Implement order-derived purchase history

Proposal lead / workstream assignment: Monira Islam — follows the proposal split; this is a planned role, not a contribution record.

Hands-on operator: Monira Islam (you) — you will carry out every task, including tasks assigned to the frontend/UI workstream.

Requirement: Customer summary should reflect recorded orders, not duplicated manual facts.

Target: Purchase count, last purchase, and totals are computed from eligible orders per approved status rules.

Why this task matters: Purchase count, last purchase, and totals are computed from eligible orders per approved status rules. It isolates one change so the student can inspect, test, and explain it before moving on.

Prerequisites: CUSTOMER-02

Concepts to understand: Aggregation; query performance; source of truth.

Expected files/modules: backend/apps/customers/services; query tests.

Implementation scope: Use a service/query; do not store values unless justified and kept consistent.

Not in this task: Other modules, unrelated refactors, new dependencies, and unapproved features.

Ready-to-paste Codex prompt

You are implementing SellerOS, the SE-331 standalone social-commerce seller BI/decision-support capstone. Implement only CUSTOMER-03 — Implement order-derived purchase history. Requirement: Customer summary should reflect recorded orders, not duplicated manual facts. Objective/acceptance target: Purchase count, last purchase, and totals are computed from eligible orders per approved status rules. Scope allowed: Use a service/query; do not store values unless justified and kept consistent. Likely files/modules: backend/apps/customers/services; query tests. Prerequisites: CUSTOMER-02. Constraints: follow the approved React/Vite/TypeScript + Django/DRF + PostgreSQL architecture and existing API/data contracts; inspect the repository first; preserve existing working behavior; do not invent unresolved business rules—mark [DECISION REQUIRED]; do not modify unrelated files, add unnecessary dependencies, expose secrets, bypass authentication/store permissions, fabricate AI/ML results, or create autonomous actions. Out of scope for this task: Other modules, unrelated refactors, new dependencies, and unapproved features. Test requirement: Hand-calculated customer histories match service results. Run the narrow relevant checks and report exact commands and outcomes. Expected output: focused implementation, meaningful tests, and concise notes on files changed, decisions, risks, and next dependency. Code quality: small readable changes, type/validation/error handling appropriate to the existing project, no duplicated business formulas, and no generated or sensitive data committed.

Expected Codex output: A focused change for CUSTOMER-03, relevant tests, a file-change summary, and exact commands/results. No unrelated implementation.

How to inspect: Review the diff for these boundaries: Use a service/query; do not store values unless justified and kept consistent. Confirm only expected files changed, validation/permissions match the contract, and tests exercise the requirement.

How to understand: Explain in your own words how Aggregation; query performance; source of truth. support this task; trace one normal case and one failure case through the code.

Run commands: Use verified environment commands from SETUP-07. Typical checks: backend: `python manage.py check` and the focused Django test module; frontend: `npm run lint`, focused test, and `npm run build`. Run only commands applicable to changed code and report exact outcomes.

Test steps / expected result: Hand-calculated customer histories match service results. Success means the target is present, tests pass, and failure behavior is understandable.

Common errors: If the DB is unavailable, verify PostgreSQL service, database name, credentials, and env loading. If imports/routes fail, check app registration and URL inclusion. If an API/UI mismatch appears, compare against docs/api-contract.md and correct the contract or implementation deliberately; do not patch around it.

Git milestone: After review and passing tests, commit only this task. Suggested: `git add <reviewed-files> && git commit -m "CUSTOMER-03: implement order-derived purchase history"`. Use a feature branch only when it helps isolate a risky/long feature; no empty commits.

Viva questions: 1. What requirement does CUSTOMER-03 satisfy? 2. Which data/API/UI boundary does it change? 3. How is invalid or unauthorized input handled? 4. What test proves it works? 5. What limitation remains?

Definition of Done: ☐ Scope met  ☐ Code understood  ☐ Focused tests pass  ☐ No unrelated changes  ☐ Evidence recorded  ☐ Commit created  ☐ Docs updated if affected  ☐ Viva explanation ready

## CUSTOMER-04 — Build customer list and profile UI

Proposal lead / workstream assignment: Rukaiya Akther Trisha — follows the proposal split; this is a planned role, not a contribution record.

Hands-on operator: Monira Islam (you) — you will carry out every task, including tasks assigned to the frontend/UI workstream.

Requirement: Seller needs to inspect customers and purchase history.

Target: Customer screens show approved fields and linked order history.

Why this task matters: Customer screens show approved fields and linked order history. It isolates one change so the student can inspect, test, and explain it before moving on.

Prerequisites: CUSTOMER-02; FRONTEND-03

Concepts to understand: Accessible forms/tables; derived data display.

Expected files/modules: frontend/src/features/customers; tests.

Implementation scope: Avoid sensitive labels and unapproved segments.

Not in this task: Other modules, unrelated refactors, new dependencies, and unapproved features.

Ready-to-paste Codex prompt

You are implementing SellerOS, the SE-331 standalone social-commerce seller BI/decision-support capstone. Implement only CUSTOMER-04 — Build customer list and profile UI. Requirement: Seller needs to inspect customers and purchase history. Objective/acceptance target: Customer screens show approved fields and linked order history. Scope allowed: Avoid sensitive labels and unapproved segments. Likely files/modules: frontend/src/features/customers; tests. Prerequisites: CUSTOMER-02; FRONTEND-03. Constraints: follow the approved React/Vite/TypeScript + Django/DRF + PostgreSQL architecture and existing API/data contracts; inspect the repository first; preserve existing working behavior; do not invent unresolved business rules—mark [DECISION REQUIRED]; do not modify unrelated files, add unnecessary dependencies, expose secrets, bypass authentication/store permissions, fabricate AI/ML results, or create autonomous actions. Out of scope for this task: Other modules, unrelated refactors, new dependencies, and unapproved features. Test requirement: UI states and CRUD flow tested. Run the narrow relevant checks and report exact commands and outcomes. Expected output: focused implementation, meaningful tests, and concise notes on files changed, decisions, risks, and next dependency. Code quality: small readable changes, type/validation/error handling appropriate to the existing project, no duplicated business formulas, and no generated or sensitive data committed.

Expected Codex output: A focused change for CUSTOMER-04, relevant tests, a file-change summary, and exact commands/results. No unrelated implementation.

How to inspect: Review the diff for these boundaries: Avoid sensitive labels and unapproved segments. Confirm only expected files changed, validation/permissions match the contract, and tests exercise the requirement.

How to understand: Explain in your own words how Accessible forms/tables; derived data display. support this task; trace one normal case and one failure case through the code.

Run commands: Use verified environment commands from SETUP-07. Typical checks: backend: `python manage.py check` and the focused Django test module; frontend: `npm run lint`, focused test, and `npm run build`. Run only commands applicable to changed code and report exact outcomes.

Test steps / expected result: UI states and CRUD flow tested. Success means the target is present, tests pass, and failure behavior is understandable.

Common errors: If the DB is unavailable, verify PostgreSQL service, database name, credentials, and env loading. If imports/routes fail, check app registration and URL inclusion. If an API/UI mismatch appears, compare against docs/api-contract.md and correct the contract or implementation deliberately; do not patch around it.

Git milestone: After review and passing tests, commit only this task. Suggested: `git add <reviewed-files> && git commit -m "CUSTOMER-04: build customer list and profile ui"`. Use a feature branch only when it helps isolate a risky/long feature; no empty commits.

Viva questions: 1. What requirement does CUSTOMER-04 satisfy? 2. Which data/API/UI boundary does it change? 3. How is invalid or unauthorized input handled? 4. What test proves it works? 5. What limitation remains?

Definition of Done: ☐ Scope met  ☐ Code understood  ☐ Focused tests pass  ☐ No unrelated changes  ☐ Evidence recorded  ☐ Commit created  ☐ Docs updated if affected  ☐ Viva explanation ready

## CUSTOMER-05 — Verify customer and order relationship

Proposal lead / workstream assignment: Jointly assigned to Monira Islam and Rukaiya Akther Trisha — follows the proposal split; this is a planned role, not a contribution record.

Hands-on operator: Monira Islam (you) — you will carry out every task, including tasks assigned to the frontend/UI workstream.

Requirement: Customer history depends on order integrity.

Target: Creating eligible orders updates displayed history without stale or duplicate totals.

Why this task matters: Creating eligible orders updates displayed history without stale or duplicate totals. It isolates one change so the student can inspect, test, and explain it before moving on.

Prerequisites: CUSTOMER-04

Concepts to understand: Derived state; query invalidation; referential integrity.

Expected files/modules: backend integration; frontend e2e.

Implementation scope: Use seed cases and real API.

Not in this task: Other modules, unrelated refactors, new dependencies, and unapproved features.

Ready-to-paste Codex prompt

You are implementing SellerOS, the SE-331 standalone social-commerce seller BI/decision-support capstone. Implement only CUSTOMER-05 — Verify customer and order relationship. Requirement: Customer history depends on order integrity. Objective/acceptance target: Creating eligible orders updates displayed history without stale or duplicate totals. Scope allowed: Use seed cases and real API. Likely files/modules: backend integration; frontend e2e. Prerequisites: CUSTOMER-04. Constraints: follow the approved React/Vite/TypeScript + Django/DRF + PostgreSQL architecture and existing API/data contracts; inspect the repository first; preserve existing working behavior; do not invent unresolved business rules—mark [DECISION REQUIRED]; do not modify unrelated files, add unnecessary dependencies, expose secrets, bypass authentication/store permissions, fabricate AI/ML results, or create autonomous actions. Out of scope for this task: Other modules, unrelated refactors, new dependencies, and unapproved features. Test requirement: History matches hand-computed test cases. Run the narrow relevant checks and report exact commands and outcomes. Expected output: focused implementation, meaningful tests, and concise notes on files changed, decisions, risks, and next dependency. Code quality: small readable changes, type/validation/error handling appropriate to the existing project, no duplicated business formulas, and no generated or sensitive data committed.

Expected Codex output: A focused change for CUSTOMER-05, relevant tests, a file-change summary, and exact commands/results. No unrelated implementation.

How to inspect: Review the diff for these boundaries: Use seed cases and real API. Confirm only expected files changed, validation/permissions match the contract, and tests exercise the requirement.

How to understand: Explain in your own words how Derived state; query invalidation; referential integrity. support this task; trace one normal case and one failure case through the code.

Run commands: Use verified environment commands from SETUP-07. Typical checks: backend: `python manage.py check` and the focused Django test module; frontend: `npm run lint`, focused test, and `npm run build`. Run only commands applicable to changed code and report exact outcomes.

Test steps / expected result: History matches hand-computed test cases. Success means the target is present, tests pass, and failure behavior is understandable.

Common errors: If the DB is unavailable, verify PostgreSQL service, database name, credentials, and env loading. If imports/routes fail, check app registration and URL inclusion. If an API/UI mismatch appears, compare against docs/api-contract.md and correct the contract or implementation deliberately; do not patch around it.

Git milestone: After review and passing tests, commit only this task. Suggested: `git add <reviewed-files> && git commit -m "CUSTOMER-05: verify customer and order relationship"`. Use a feature branch only when it helps isolate a risky/long feature; no empty commits.

Viva questions: 1. What requirement does CUSTOMER-05 satisfy? 2. Which data/API/UI boundary does it change? 3. How is invalid or unauthorized input handled? 4. What test proves it works? 5. What limitation remains?

Definition of Done: ☐ Scope met  ☐ Code understood  ☐ Focused tests pass  ☐ No unrelated changes  ☐ Evidence recorded  ☐ Commit created  ☐ Docs updated if affected  ☐ Viva explanation ready

## ORDER-01 — Implement order and order-item models

Proposal lead / workstream assignment: Monira Islam — follows the proposal split; this is a planned role, not a contribution record.

Hands-on operator: Monira Islam (you) — you will carry out every task, including tasks assigned to the frontend/UI workstream.

Requirement: Orders connect customers, product snapshots, quantity, revenue inputs, and status.

Target: Order schema preserves transaction-time item values and approved status fields.

Why this task matters: Order schema preserves transaction-time item values and approved status fields. It isolates one change so the student can inspect, test, and explain it before moving on.

Prerequisites: CUSTOMER-05

Concepts to understand: Order line; snapshot; Decimal; foreign keys.

Expected files/modules: backend/apps/orders/models; migrations; tests.

Implementation scope: Use PLAN-03 rules; store historical item price/cost where approved; no unapproved refund model.

Not in this task: Other modules, unrelated refactors, new dependencies, and unapproved features.

Ready-to-paste Codex prompt

You are implementing SellerOS, the SE-331 standalone social-commerce seller BI/decision-support capstone. Implement only ORDER-01 — Implement order and order-item models. Requirement: Orders connect customers, product snapshots, quantity, revenue inputs, and status. Objective/acceptance target: Order schema preserves transaction-time item values and approved status fields. Scope allowed: Use PLAN-03 rules; store historical item price/cost where approved; no unapproved refund model. Likely files/modules: backend/apps/orders/models; migrations; tests. Prerequisites: CUSTOMER-05. Constraints: follow the approved React/Vite/TypeScript + Django/DRF + PostgreSQL architecture and existing API/data contracts; inspect the repository first; preserve existing working behavior; do not invent unresolved business rules—mark [DECISION REQUIRED]; do not modify unrelated files, add unnecessary dependencies, expose secrets, bypass authentication/store permissions, fabricate AI/ML results, or create autonomous actions. Out of scope for this task: Other modules, unrelated refactors, new dependencies, and unapproved features. Test requirement: Models preserve history and validate relationships. Run the narrow relevant checks and report exact commands and outcomes. Expected output: focused implementation, meaningful tests, and concise notes on files changed, decisions, risks, and next dependency. Code quality: small readable changes, type/validation/error handling appropriate to the existing project, no duplicated business formulas, and no generated or sensitive data committed.

Expected Codex output: A focused change for ORDER-01, relevant tests, a file-change summary, and exact commands/results. No unrelated implementation.

How to inspect: Review the diff for these boundaries: Use PLAN-03 rules; store historical item price/cost where approved; no unapproved refund model. Confirm only expected files changed, validation/permissions match the contract, and tests exercise the requirement.

How to understand: Explain in your own words how Order line; snapshot; Decimal; foreign keys. support this task; trace one normal case and one failure case through the code.

Run commands: Use verified environment commands from SETUP-07. Typical checks: backend: `python manage.py check` and the focused Django test module; frontend: `npm run lint`, focused test, and `npm run build`. Run only commands applicable to changed code and report exact outcomes.

Test steps / expected result: Models preserve history and validate relationships. Success means the target is present, tests pass, and failure behavior is understandable.

Common errors: If the DB is unavailable, verify PostgreSQL service, database name, credentials, and env loading. If imports/routes fail, check app registration and URL inclusion. If an API/UI mismatch appears, compare against docs/api-contract.md and correct the contract or implementation deliberately; do not patch around it.

Git milestone: After review and passing tests, commit only this task. Suggested: `git add <reviewed-files> && git commit -m "ORDER-01: implement order and order-item models"`. Use a feature branch only when it helps isolate a risky/long feature; no empty commits.

Viva questions: 1. What requirement does ORDER-01 satisfy? 2. Which data/API/UI boundary does it change? 3. How is invalid or unauthorized input handled? 4. What test proves it works? 5. What limitation remains?

Definition of Done: ☐ Scope met  ☐ Code understood  ☐ Focused tests pass  ☐ No unrelated changes  ☐ Evidence recorded  ☐ Commit created  ☐ Docs updated if affected  ☐ Viva explanation ready

## ORDER-02 — Implement order creation validation and serializers

Proposal lead / workstream assignment: Monira Islam — follows the proposal split; this is a planned role, not a contribution record.

Hands-on operator: Monira Islam (you) — you will carry out every task, including tasks assigned to the frontend/UI workstream.

Requirement: Orders need validated input and consistent error messages.

Target: Create serializer validates customer, product, quantity, prices, discount, delivery fields per contract.

Why this task matters: Create serializer validates customer, product, quantity, prices, discount, delivery fields per contract. It isolates one change so the student can inspect, test, and explain it before moving on.

Prerequisites: ORDER-01

Concepts to understand: Nested serializers; validation; trust boundaries.

Expected files/modules: backend/apps/orders/serializers; tests.

Implementation scope: Enforce store membership and server-side pricing policy decided by team.

Not in this task: Other modules, unrelated refactors, new dependencies, and unapproved features.

Ready-to-paste Codex prompt

You are implementing SellerOS, the SE-331 standalone social-commerce seller BI/decision-support capstone. Implement only ORDER-02 — Implement order creation validation and serializers. Requirement: Orders need validated input and consistent error messages. Objective/acceptance target: Create serializer validates customer, product, quantity, prices, discount, delivery fields per contract. Scope allowed: Enforce store membership and server-side pricing policy decided by team. Likely files/modules: backend/apps/orders/serializers; tests. Prerequisites: ORDER-01. Constraints: follow the approved React/Vite/TypeScript + Django/DRF + PostgreSQL architecture and existing API/data contracts; inspect the repository first; preserve existing working behavior; do not invent unresolved business rules—mark [DECISION REQUIRED]; do not modify unrelated files, add unnecessary dependencies, expose secrets, bypass authentication/store permissions, fabricate AI/ML results, or create autonomous actions. Out of scope for this task: Other modules, unrelated refactors, new dependencies, and unapproved features. Test requirement: Valid payload accepted; malformed/foreign IDs rejected. Run the narrow relevant checks and report exact commands and outcomes. Expected output: focused implementation, meaningful tests, and concise notes on files changed, decisions, risks, and next dependency. Code quality: small readable changes, type/validation/error handling appropriate to the existing project, no duplicated business formulas, and no generated or sensitive data committed.

Expected Codex output: A focused change for ORDER-02, relevant tests, a file-change summary, and exact commands/results. No unrelated implementation.

How to inspect: Review the diff for these boundaries: Enforce store membership and server-side pricing policy decided by team. Confirm only expected files changed, validation/permissions match the contract, and tests exercise the requirement.

How to understand: Explain in your own words how Nested serializers; validation; trust boundaries. support this task; trace one normal case and one failure case through the code.

Run commands: Use verified environment commands from SETUP-07. Typical checks: backend: `python manage.py check` and the focused Django test module; frontend: `npm run lint`, focused test, and `npm run build`. Run only commands applicable to changed code and report exact outcomes.

Test steps / expected result: Valid payload accepted; malformed/foreign IDs rejected. Success means the target is present, tests pass, and failure behavior is understandable.

Common errors: If the DB is unavailable, verify PostgreSQL service, database name, credentials, and env loading. If imports/routes fail, check app registration and URL inclusion. If an API/UI mismatch appears, compare against docs/api-contract.md and correct the contract or implementation deliberately; do not patch around it.

Git milestone: After review and passing tests, commit only this task. Suggested: `git add <reviewed-files> && git commit -m "ORDER-02: implement order creation validation and serializers"`. Use a feature branch only when it helps isolate a risky/long feature; no empty commits.

Viva questions: 1. What requirement does ORDER-02 satisfy? 2. Which data/API/UI boundary does it change? 3. How is invalid or unauthorized input handled? 4. What test proves it works? 5. What limitation remains?

Definition of Done: ☐ Scope met  ☐ Code understood  ☐ Focused tests pass  ☐ No unrelated changes  ☐ Evidence recorded  ☐ Commit created  ☐ Docs updated if affected  ☐ Viva explanation ready

## ORDER-03 — Implement atomic order creation with stock reservation/deduction

Proposal lead / workstream assignment: Monira Islam — follows the proposal split; this is a planned role, not a contribution record.

Hands-on operator: Monira Islam (you) — you will carry out every task, including tasks assigned to the frontend/UI workstream.

Requirement: Order creation and stock must remain consistent.

Target: A valid order and inventory effect commit together or roll back together.

Why this task matters: A valid order and inventory effect commit together or roll back together. It isolates one change so the student can inspect, test, and explain it before moving on.

Prerequisites: ORDER-02

Concepts to understand: Transactions; service boundaries; idempotency.

Expected files/modules: backend/apps/orders/services; inventory service; tests.

Implementation scope: Implement agreed timing and quantities; ensure movement references order.

Not in this task: Other modules, unrelated refactors, new dependencies, and unapproved features.

Ready-to-paste Codex prompt

You are implementing SellerOS, the SE-331 standalone social-commerce seller BI/decision-support capstone. Implement only ORDER-03 — Implement atomic order creation with stock reservation/deduction. Requirement: Order creation and stock must remain consistent. Objective/acceptance target: A valid order and inventory effect commit together or roll back together. Scope allowed: Implement agreed timing and quantities; ensure movement references order. Likely files/modules: backend/apps/orders/services; inventory service; tests. Prerequisites: ORDER-02. Constraints: follow the approved React/Vite/TypeScript + Django/DRF + PostgreSQL architecture and existing API/data contracts; inspect the repository first; preserve existing working behavior; do not invent unresolved business rules—mark [DECISION REQUIRED]; do not modify unrelated files, add unnecessary dependencies, expose secrets, bypass authentication/store permissions, fabricate AI/ML results, or create autonomous actions. Out of scope for this task: Other modules, unrelated refactors, new dependencies, and unapproved features. Test requirement: Failure injection proves no partial order or stock update. Run the narrow relevant checks and report exact commands and outcomes. Expected output: focused implementation, meaningful tests, and concise notes on files changed, decisions, risks, and next dependency. Code quality: small readable changes, type/validation/error handling appropriate to the existing project, no duplicated business formulas, and no generated or sensitive data committed.

Expected Codex output: A focused change for ORDER-03, relevant tests, a file-change summary, and exact commands/results. No unrelated implementation.

How to inspect: Review the diff for these boundaries: Implement agreed timing and quantities; ensure movement references order. Confirm only expected files changed, validation/permissions match the contract, and tests exercise the requirement.

How to understand: Explain in your own words how Transactions; service boundaries; idempotency. support this task; trace one normal case and one failure case through the code.

Run commands: Use verified environment commands from SETUP-07. Typical checks: backend: `python manage.py check` and the focused Django test module; frontend: `npm run lint`, focused test, and `npm run build`. Run only commands applicable to changed code and report exact outcomes.

Test steps / expected result: Failure injection proves no partial order or stock update. Success means the target is present, tests pass, and failure behavior is understandable.

Common errors: If the DB is unavailable, verify PostgreSQL service, database name, credentials, and env loading. If imports/routes fail, check app registration and URL inclusion. If an API/UI mismatch appears, compare against docs/api-contract.md and correct the contract or implementation deliberately; do not patch around it.

Git milestone: After review and passing tests, commit only this task. Suggested: `git add <reviewed-files> && git commit -m "ORDER-03: implement atomic order creation with stock reservation/deduction"`. Use a feature branch only when it helps isolate a risky/long feature; no empty commits.

Viva questions: 1. What requirement does ORDER-03 satisfy? 2. Which data/API/UI boundary does it change? 3. How is invalid or unauthorized input handled? 4. What test proves it works? 5. What limitation remains?

Definition of Done: ☐ Scope met  ☐ Code understood  ☐ Focused tests pass  ☐ No unrelated changes  ☐ Evidence recorded  ☐ Commit created  ☐ Docs updated if affected  ☐ Viva explanation ready

## ORDER-04 — Implement allowed order status transitions

Proposal lead / workstream assignment: Monira Islam — follows the proposal split; this is a planned role, not a contribution record.

Hands-on operator: Monira Islam (you) — you will carry out every task, including tasks assigned to the frontend/UI workstream.

Requirement: Order workflow requires defined states and transition rules.

Target: API rejects invalid or unauthorized state transitions.

Why this task matters: API rejects invalid or unauthorized state transitions. It isolates one change so the student can inspect, test, and explain it before moving on.

Prerequisites: ORDER-03

Concepts to understand: State machine; audit events; validation.

Expected files/modules: backend/apps/orders/services; tests; docs.

Implementation scope: Use approved state machine; cancellations/refunds remain gated by PLAN-03.

Not in this task: Other modules, unrelated refactors, new dependencies, and unapproved features.

Ready-to-paste Codex prompt

You are implementing SellerOS, the SE-331 standalone social-commerce seller BI/decision-support capstone. Implement only ORDER-04 — Implement allowed order status transitions. Requirement: Order workflow requires defined states and transition rules. Objective/acceptance target: API rejects invalid or unauthorized state transitions. Scope allowed: Use approved state machine; cancellations/refunds remain gated by PLAN-03. Likely files/modules: backend/apps/orders/services; tests; docs. Prerequisites: ORDER-03. Constraints: follow the approved React/Vite/TypeScript + Django/DRF + PostgreSQL architecture and existing API/data contracts; inspect the repository first; preserve existing working behavior; do not invent unresolved business rules—mark [DECISION REQUIRED]; do not modify unrelated files, add unnecessary dependencies, expose secrets, bypass authentication/store permissions, fabricate AI/ML results, or create autonomous actions. Out of scope for this task: Other modules, unrelated refactors, new dependencies, and unapproved features. Test requirement: Allowed and forbidden transition table passes tests. Run the narrow relevant checks and report exact commands and outcomes. Expected output: focused implementation, meaningful tests, and concise notes on files changed, decisions, risks, and next dependency. Code quality: small readable changes, type/validation/error handling appropriate to the existing project, no duplicated business formulas, and no generated or sensitive data committed.

Expected Codex output: A focused change for ORDER-04, relevant tests, a file-change summary, and exact commands/results. No unrelated implementation.

How to inspect: Review the diff for these boundaries: Use approved state machine; cancellations/refunds remain gated by PLAN-03. Confirm only expected files changed, validation/permissions match the contract, and tests exercise the requirement.

How to understand: Explain in your own words how State machine; audit events; validation. support this task; trace one normal case and one failure case through the code.

Run commands: Use verified environment commands from SETUP-07. Typical checks: backend: `python manage.py check` and the focused Django test module; frontend: `npm run lint`, focused test, and `npm run build`. Run only commands applicable to changed code and report exact outcomes.

Test steps / expected result: Allowed and forbidden transition table passes tests. Success means the target is present, tests pass, and failure behavior is understandable.

Common errors: If the DB is unavailable, verify PostgreSQL service, database name, credentials, and env loading. If imports/routes fail, check app registration and URL inclusion. If an API/UI mismatch appears, compare against docs/api-contract.md and correct the contract or implementation deliberately; do not patch around it.

Git milestone: After review and passing tests, commit only this task. Suggested: `git add <reviewed-files> && git commit -m "ORDER-04: implement allowed order status transitions"`. Use a feature branch only when it helps isolate a risky/long feature; no empty commits.

Viva questions: 1. What requirement does ORDER-04 satisfy? 2. Which data/API/UI boundary does it change? 3. How is invalid or unauthorized input handled? 4. What test proves it works? 5. What limitation remains?

Definition of Done: ☐ Scope met  ☐ Code understood  ☐ Focused tests pass  ☐ No unrelated changes  ☐ Evidence recorded  ☐ Commit created  ☐ Docs updated if affected  ☐ Viva explanation ready

## ORDER-05 — Implement order list and detail APIs

Proposal lead / workstream assignment: Monira Islam — follows the proposal split; this is a planned role, not a contribution record.

Hands-on operator: Monira Islam (you) — you will carry out every task, including tasks assigned to the frontend/UI workstream.

Requirement: Seller must find and review orders.

Target: Store-scoped list/detail endpoints support approved date/status filters and pagination.

Why this task matters: Store-scoped list/detail endpoints support approved date/status filters and pagination. It isolates one change so the student can inspect, test, and explain it before moving on.

Prerequisites: ORDER-04

Concepts to understand: Query filters; pagination; object access.

Expected files/modules: backend/apps/orders/api; URLs; tests.

Implementation scope: No analytics calculations in this task.

Not in this task: Other modules, unrelated refactors, new dependencies, and unapproved features.

Ready-to-paste Codex prompt

You are implementing SellerOS, the SE-331 standalone social-commerce seller BI/decision-support capstone. Implement only ORDER-05 — Implement order list and detail APIs. Requirement: Seller must find and review orders. Objective/acceptance target: Store-scoped list/detail endpoints support approved date/status filters and pagination. Scope allowed: No analytics calculations in this task. Likely files/modules: backend/apps/orders/api; URLs; tests. Prerequisites: ORDER-04. Constraints: follow the approved React/Vite/TypeScript + Django/DRF + PostgreSQL architecture and existing API/data contracts; inspect the repository first; preserve existing working behavior; do not invent unresolved business rules—mark [DECISION REQUIRED]; do not modify unrelated files, add unnecessary dependencies, expose secrets, bypass authentication/store permissions, fabricate AI/ML results, or create autonomous actions. Out of scope for this task: Other modules, unrelated refactors, new dependencies, and unapproved features. Test requirement: Correct result set, validation, and isolation verified. Run the narrow relevant checks and report exact commands and outcomes. Expected output: focused implementation, meaningful tests, and concise notes on files changed, decisions, risks, and next dependency. Code quality: small readable changes, type/validation/error handling appropriate to the existing project, no duplicated business formulas, and no generated or sensitive data committed.

Expected Codex output: A focused change for ORDER-05, relevant tests, a file-change summary, and exact commands/results. No unrelated implementation.

How to inspect: Review the diff for these boundaries: No analytics calculations in this task. Confirm only expected files changed, validation/permissions match the contract, and tests exercise the requirement.

How to understand: Explain in your own words how Query filters; pagination; object access. support this task; trace one normal case and one failure case through the code.

Run commands: Use verified environment commands from SETUP-07. Typical checks: backend: `python manage.py check` and the focused Django test module; frontend: `npm run lint`, focused test, and `npm run build`. Run only commands applicable to changed code and report exact outcomes.

Test steps / expected result: Correct result set, validation, and isolation verified. Success means the target is present, tests pass, and failure behavior is understandable.

Common errors: If the DB is unavailable, verify PostgreSQL service, database name, credentials, and env loading. If imports/routes fail, check app registration and URL inclusion. If an API/UI mismatch appears, compare against docs/api-contract.md and correct the contract or implementation deliberately; do not patch around it.

Git milestone: After review and passing tests, commit only this task. Suggested: `git add <reviewed-files> && git commit -m "ORDER-05: implement order list and detail apis"`. Use a feature branch only when it helps isolate a risky/long feature; no empty commits.

Viva questions: 1. What requirement does ORDER-05 satisfy? 2. Which data/API/UI boundary does it change? 3. How is invalid or unauthorized input handled? 4. What test proves it works? 5. What limitation remains?

Definition of Done: ☐ Scope met  ☐ Code understood  ☐ Focused tests pass  ☐ No unrelated changes  ☐ Evidence recorded  ☐ Commit created  ☐ Docs updated if affected  ☐ Viva explanation ready

## ORDER-06 — Implement order status update API and audit record

Proposal lead / workstream assignment: Monira Islam — follows the proposal split; this is a planned role, not a contribution record.

Hands-on operator: Monira Islam (you) — you will carry out every task, including tasks assigned to the frontend/UI workstream.

Requirement: Status changes should be traceable and consistent.

Target: Authorized status updates persist transition evidence and return stable API response.

Why this task matters: Authorized status updates persist transition evidence and return stable API response. It isolates one change so the student can inspect, test, and explain it before moving on.

Prerequisites: ORDER-05

Concepts to understand: PATCH semantics; audit trail; transaction.

Expected files/modules: backend/apps/orders/api; transition service; tests.

Implementation scope: Only status update and audit; no automatic external messages.

Not in this task: Other modules, unrelated refactors, new dependencies, and unapproved features.

Ready-to-paste Codex prompt

You are implementing SellerOS, the SE-331 standalone social-commerce seller BI/decision-support capstone. Implement only ORDER-06 — Implement order status update API and audit record. Requirement: Status changes should be traceable and consistent. Objective/acceptance target: Authorized status updates persist transition evidence and return stable API response. Scope allowed: Only status update and audit; no automatic external messages. Likely files/modules: backend/apps/orders/api; transition service; tests. Prerequisites: ORDER-05. Constraints: follow the approved React/Vite/TypeScript + Django/DRF + PostgreSQL architecture and existing API/data contracts; inspect the repository first; preserve existing working behavior; do not invent unresolved business rules—mark [DECISION REQUIRED]; do not modify unrelated files, add unnecessary dependencies, expose secrets, bypass authentication/store permissions, fabricate AI/ML results, or create autonomous actions. Out of scope for this task: Other modules, unrelated refactors, new dependencies, and unapproved features. Test requirement: Status history matches accepted/rejected actions. Run the narrow relevant checks and report exact commands and outcomes. Expected output: focused implementation, meaningful tests, and concise notes on files changed, decisions, risks, and next dependency. Code quality: small readable changes, type/validation/error handling appropriate to the existing project, no duplicated business formulas, and no generated or sensitive data committed.

Expected Codex output: A focused change for ORDER-06, relevant tests, a file-change summary, and exact commands/results. No unrelated implementation.

How to inspect: Review the diff for these boundaries: Only status update and audit; no automatic external messages. Confirm only expected files changed, validation/permissions match the contract, and tests exercise the requirement.

How to understand: Explain in your own words how PATCH semantics; audit trail; transaction. support this task; trace one normal case and one failure case through the code.

Run commands: Use verified environment commands from SETUP-07. Typical checks: backend: `python manage.py check` and the focused Django test module; frontend: `npm run lint`, focused test, and `npm run build`. Run only commands applicable to changed code and report exact outcomes.

Test steps / expected result: Status history matches accepted/rejected actions. Success means the target is present, tests pass, and failure behavior is understandable.

Common errors: If the DB is unavailable, verify PostgreSQL service, database name, credentials, and env loading. If imports/routes fail, check app registration and URL inclusion. If an API/UI mismatch appears, compare against docs/api-contract.md and correct the contract or implementation deliberately; do not patch around it.

Git milestone: After review and passing tests, commit only this task. Suggested: `git add <reviewed-files> && git commit -m "ORDER-06: implement order status update api and audit record"`. Use a feature branch only when it helps isolate a risky/long feature; no empty commits.

Viva questions: 1. What requirement does ORDER-06 satisfy? 2. Which data/API/UI boundary does it change? 3. How is invalid or unauthorized input handled? 4. What test proves it works? 5. What limitation remains?

Definition of Done: ☐ Scope met  ☐ Code understood  ☐ Focused tests pass  ☐ No unrelated changes  ☐ Evidence recorded  ☐ Commit created  ☐ Docs updated if affected  ☐ Viva explanation ready

## ORDER-07 — Build order create and detail UI

Proposal lead / workstream assignment: Rukaiya Akther Trisha — follows the proposal split; this is a planned role, not a contribution record.

Hands-on operator: Monira Islam (you) — you will carry out every task, including tasks assigned to the frontend/UI workstream.

Requirement: Seller needs to enter orders linked to customers and products.

Target: Accessible order form and detail view follow the agreed payload contract.

Why this task matters: Accessible order form and detail view follow the agreed payload contract. It isolates one change so the student can inspect, test, and explain it before moving on.

Prerequisites: ORDER-02; PRODUCT-03; CUSTOMER-02; BACKEND-05; FRONTEND-03

Concepts to understand: Dependent selects; form state; server validation.

Expected files/modules: frontend/src/features/orders; tests.

Implementation scope: No frontend-side authority over price/stock; show server validation errors.

Not in this task: Other modules, unrelated refactors, new dependencies, and unapproved features.

Ready-to-paste Codex prompt

You are implementing SellerOS, the SE-331 standalone social-commerce seller BI/decision-support capstone. Implement only ORDER-07 — Build order create and detail UI. Requirement: Seller needs to enter orders linked to customers and products. Objective/acceptance target: Accessible order form and detail view follow the agreed payload contract. Scope allowed: No frontend-side authority over price/stock; show server validation errors. Likely files/modules: frontend/src/features/orders; tests. Prerequisites: ORDER-02; PRODUCT-03; CUSTOMER-02; BACKEND-05; FRONTEND-03. Constraints: follow the approved React/Vite/TypeScript + Django/DRF + PostgreSQL architecture and existing API/data contracts; inspect the repository first; preserve existing working behavior; do not invent unresolved business rules—mark [DECISION REQUIRED]; do not modify unrelated files, add unnecessary dependencies, expose secrets, bypass authentication/store permissions, fabricate AI/ML results, or create autonomous actions. Out of scope for this task: Other modules, unrelated refactors, new dependencies, and unapproved features. Test requirement: Create flow covers stock errors and empty lookup states. Run the narrow relevant checks and report exact commands and outcomes. Expected output: focused implementation, meaningful tests, and concise notes on files changed, decisions, risks, and next dependency. Code quality: small readable changes, type/validation/error handling appropriate to the existing project, no duplicated business formulas, and no generated or sensitive data committed.

Expected Codex output: A focused change for ORDER-07, relevant tests, a file-change summary, and exact commands/results. No unrelated implementation.

How to inspect: Review the diff for these boundaries: No frontend-side authority over price/stock; show server validation errors. Confirm only expected files changed, validation/permissions match the contract, and tests exercise the requirement.

How to understand: Explain in your own words how Dependent selects; form state; server validation. support this task; trace one normal case and one failure case through the code.

Run commands: Use verified environment commands from SETUP-07. Typical checks: backend: `python manage.py check` and the focused Django test module; frontend: `npm run lint`, focused test, and `npm run build`. Run only commands applicable to changed code and report exact outcomes.

Test steps / expected result: Create flow covers stock errors and empty lookup states. Success means the target is present, tests pass, and failure behavior is understandable.

Common errors: If the DB is unavailable, verify PostgreSQL service, database name, credentials, and env loading. If imports/routes fail, check app registration and URL inclusion. If an API/UI mismatch appears, compare against docs/api-contract.md and correct the contract or implementation deliberately; do not patch around it.

Git milestone: After review and passing tests, commit only this task. Suggested: `git add <reviewed-files> && git commit -m "ORDER-07: build order create and detail ui"`. Use a feature branch only when it helps isolate a risky/long feature; no empty commits.

Viva questions: 1. What requirement does ORDER-07 satisfy? 2. Which data/API/UI boundary does it change? 3. How is invalid or unauthorized input handled? 4. What test proves it works? 5. What limitation remains?

Definition of Done: ☐ Scope met  ☐ Code understood  ☐ Focused tests pass  ☐ No unrelated changes  ☐ Evidence recorded  ☐ Commit created  ☐ Docs updated if affected  ☐ Viva explanation ready

## ORDER-08 — Build order list and status workflow UI

Proposal lead / workstream assignment: Rukaiya Akther Trisha — follows the proposal split; this is a planned role, not a contribution record.

Hands-on operator: Monira Islam (you) — you will carry out every task, including tasks assigned to the frontend/UI workstream.

Requirement: Seller needs to review and update order stages.

Target: Order list filters and permitted status actions reflect backend rules.

Why this task matters: Order list filters and permitted status actions reflect backend rules. It isolates one change so the student can inspect, test, and explain it before moving on.

Prerequisites: ORDER-05; ORDER-06; FRONTEND-03

Concepts to understand: Workflow UI; optimistic updates; confirmation.

Expected files/modules: frontend/src/features/orders; e2e tests.

Implementation scope: Do not offer forbidden transitions or automatic sending.

Not in this task: Other modules, unrelated refactors, new dependencies, and unapproved features.

Ready-to-paste Codex prompt

You are implementing SellerOS, the SE-331 standalone social-commerce seller BI/decision-support capstone. Implement only ORDER-08 — Build order list and status workflow UI. Requirement: Seller needs to review and update order stages. Objective/acceptance target: Order list filters and permitted status actions reflect backend rules. Scope allowed: Do not offer forbidden transitions or automatic sending. Likely files/modules: frontend/src/features/orders; e2e tests. Prerequisites: ORDER-05; ORDER-06; FRONTEND-03. Constraints: follow the approved React/Vite/TypeScript + Django/DRF + PostgreSQL architecture and existing API/data contracts; inspect the repository first; preserve existing working behavior; do not invent unresolved business rules—mark [DECISION REQUIRED]; do not modify unrelated files, add unnecessary dependencies, expose secrets, bypass authentication/store permissions, fabricate AI/ML results, or create autonomous actions. Out of scope for this task: Other modules, unrelated refactors, new dependencies, and unapproved features. Test requirement: Status UI remains accurate after success and failure. Run the narrow relevant checks and report exact commands and outcomes. Expected output: focused implementation, meaningful tests, and concise notes on files changed, decisions, risks, and next dependency. Code quality: small readable changes, type/validation/error handling appropriate to the existing project, no duplicated business formulas, and no generated or sensitive data committed.

Expected Codex output: A focused change for ORDER-08, relevant tests, a file-change summary, and exact commands/results. No unrelated implementation.

How to inspect: Review the diff for these boundaries: Do not offer forbidden transitions or automatic sending. Confirm only expected files changed, validation/permissions match the contract, and tests exercise the requirement.

How to understand: Explain in your own words how Workflow UI; optimistic updates; confirmation. support this task; trace one normal case and one failure case through the code.

Run commands: Use verified environment commands from SETUP-07. Typical checks: backend: `python manage.py check` and the focused Django test module; frontend: `npm run lint`, focused test, and `npm run build`. Run only commands applicable to changed code and report exact outcomes.

Test steps / expected result: Status UI remains accurate after success and failure. Success means the target is present, tests pass, and failure behavior is understandable.

Common errors: If the DB is unavailable, verify PostgreSQL service, database name, credentials, and env loading. If imports/routes fail, check app registration and URL inclusion. If an API/UI mismatch appears, compare against docs/api-contract.md and correct the contract or implementation deliberately; do not patch around it.

Git milestone: After review and passing tests, commit only this task. Suggested: `git add <reviewed-files> && git commit -m "ORDER-08: build order list and status workflow ui"`. Use a feature branch only when it helps isolate a risky/long feature; no empty commits.

Viva questions: 1. What requirement does ORDER-08 satisfy? 2. Which data/API/UI boundary does it change? 3. How is invalid or unauthorized input handled? 4. What test proves it works? 5. What limitation remains?

Definition of Done: ☐ Scope met  ☐ Code understood  ☐ Focused tests pass  ☐ No unrelated changes  ☐ Evidence recorded  ☐ Commit created  ☐ Docs updated if affected  ☐ Viva explanation ready

# Phase 8 — Expenses and synthetic demo data

Record costs transparently and make demo data reproducible.

## EXPENSE-01 — Create expense model and validation

Proposal lead / workstream assignment: Monira Islam — follows the proposal split; this is a planned role, not a contribution record.

Hands-on operator: Monira Islam (you) — you will carry out every task, including tasks assigned to the frontend/UI workstream.

Requirement: Profit analysis includes other entered expenses.

Target: Store-scoped expense records have amount, category, date, and description rules.

Why this task matters: Store-scoped expense records have amount, category, date, and description rules. It isolates one change so the student can inspect, test, and explain it before moving on.

Prerequisites: None beyond repository inspection and the approved project baseline.

Concepts to understand: Money precision; categories; date/time.

Expected files/modules: backend/apps/expenses/models; migrations; tests.

Implementation scope: Use currency and period decisions; no formal accounting/tax features.

Not in this task: Other modules, unrelated refactors, new dependencies, and unapproved features.

Ready-to-paste Codex prompt

You are implementing SellerOS, the SE-331 standalone social-commerce seller BI/decision-support capstone. Implement only EXPENSE-01 — Create expense model and validation. Requirement: Profit analysis includes other entered expenses. Objective/acceptance target: Store-scoped expense records have amount, category, date, and description rules. Scope allowed: Use currency and period decisions; no formal accounting/tax features. Likely files/modules: backend/apps/expenses/models; migrations; tests. Prerequisites: none beyond the approved project baseline. Constraints: follow the approved React/Vite/TypeScript + Django/DRF + PostgreSQL architecture and existing API/data contracts; inspect the repository first; preserve existing working behavior; do not invent unresolved business rules—mark [DECISION REQUIRED]; do not modify unrelated files, add unnecessary dependencies, expose secrets, bypass authentication/store permissions, fabricate AI/ML results, or create autonomous actions. Out of scope for this task: Other modules, unrelated refactors, new dependencies, and unapproved features. Test requirement: Model and validation boundary tests pass. Run the narrow relevant checks and report exact commands and outcomes. Expected output: focused implementation, meaningful tests, and concise notes on files changed, decisions, risks, and next dependency. Code quality: small readable changes, type/validation/error handling appropriate to the existing project, no duplicated business formulas, and no generated or sensitive data committed.

Expected Codex output: A focused change for EXPENSE-01, relevant tests, a file-change summary, and exact commands/results. No unrelated implementation.

How to inspect: Review the diff for these boundaries: Use currency and period decisions; no formal accounting/tax features. Confirm only expected files changed, validation/permissions match the contract, and tests exercise the requirement.

How to understand: Explain in your own words how Money precision; categories; date/time. support this task; trace one normal case and one failure case through the code.

Run commands: Use verified environment commands from SETUP-07. Typical checks: backend: `python manage.py check` and the focused Django test module; frontend: `npm run lint`, focused test, and `npm run build`. Run only commands applicable to changed code and report exact outcomes.

Test steps / expected result: Model and validation boundary tests pass. Success means the target is present, tests pass, and failure behavior is understandable.

Common errors: If the DB is unavailable, verify PostgreSQL service, database name, credentials, and env loading. If imports/routes fail, check app registration and URL inclusion. If an API/UI mismatch appears, compare against docs/api-contract.md and correct the contract or implementation deliberately; do not patch around it.

Git milestone: After review and passing tests, commit only this task. Suggested: `git add <reviewed-files> && git commit -m "EXPENSE-01: create expense model and validation"`. Use a feature branch only when it helps isolate a risky/long feature; no empty commits.

Viva questions: 1. What requirement does EXPENSE-01 satisfy? 2. Which data/API/UI boundary does it change? 3. How is invalid or unauthorized input handled? 4. What test proves it works? 5. What limitation remains?

Definition of Done: ☐ Scope met  ☐ Code understood  ☐ Focused tests pass  ☐ No unrelated changes  ☐ Evidence recorded  ☐ Commit created  ☐ Docs updated if affected  ☐ Viva explanation ready

## EXPENSE-02 — Implement expense list/create/update APIs

Proposal lead / workstream assignment: Monira Islam — follows the proposal split; this is a planned role, not a contribution record.

Hands-on operator: Monira Islam (you) — you will carry out every task, including tasks assigned to the frontend/UI workstream.

Requirement: Seller needs controlled expense maintenance.

Target: Expense APIs support permitted operations, filters, and store isolation.

Why this task matters: Expense APIs support permitted operations, filters, and store isolation. It isolates one change so the student can inspect, test, and explain it before moving on.

Prerequisites: EXPENSE-01

Concepts to understand: REST; validation; authorization.

Expected files/modules: backend/apps/expenses/api; tests.

Implementation scope: Follow API contract; handle linked/closed periods only if decided.

Not in this task: Other modules, unrelated refactors, new dependencies, and unapproved features.

Ready-to-paste Codex prompt

You are implementing SellerOS, the SE-331 standalone social-commerce seller BI/decision-support capstone. Implement only EXPENSE-02 — Implement expense list/create/update APIs. Requirement: Seller needs controlled expense maintenance. Objective/acceptance target: Expense APIs support permitted operations, filters, and store isolation. Scope allowed: Follow API contract; handle linked/closed periods only if decided. Likely files/modules: backend/apps/expenses/api; tests. Prerequisites: EXPENSE-01. Constraints: follow the approved React/Vite/TypeScript + Django/DRF + PostgreSQL architecture and existing API/data contracts; inspect the repository first; preserve existing working behavior; do not invent unresolved business rules—mark [DECISION REQUIRED]; do not modify unrelated files, add unnecessary dependencies, expose secrets, bypass authentication/store permissions, fabricate AI/ML results, or create autonomous actions. Out of scope for this task: Other modules, unrelated refactors, new dependencies, and unapproved features. Test requirement: API tests cover CRUD, filters, and cross-store access. Run the narrow relevant checks and report exact commands and outcomes. Expected output: focused implementation, meaningful tests, and concise notes on files changed, decisions, risks, and next dependency. Code quality: small readable changes, type/validation/error handling appropriate to the existing project, no duplicated business formulas, and no generated or sensitive data committed.

Expected Codex output: A focused change for EXPENSE-02, relevant tests, a file-change summary, and exact commands/results. No unrelated implementation.

How to inspect: Review the diff for these boundaries: Follow API contract; handle linked/closed periods only if decided. Confirm only expected files changed, validation/permissions match the contract, and tests exercise the requirement.

How to understand: Explain in your own words how REST; validation; authorization. support this task; trace one normal case and one failure case through the code.

Run commands: Use verified environment commands from SETUP-07. Typical checks: backend: `python manage.py check` and the focused Django test module; frontend: `npm run lint`, focused test, and `npm run build`. Run only commands applicable to changed code and report exact outcomes.

Test steps / expected result: API tests cover CRUD, filters, and cross-store access. Success means the target is present, tests pass, and failure behavior is understandable.

Common errors: If the DB is unavailable, verify PostgreSQL service, database name, credentials, and env loading. If imports/routes fail, check app registration and URL inclusion. If an API/UI mismatch appears, compare against docs/api-contract.md and correct the contract or implementation deliberately; do not patch around it.

Git milestone: After review and passing tests, commit only this task. Suggested: `git add <reviewed-files> && git commit -m "EXPENSE-02: implement expense list/create/update apis"`. Use a feature branch only when it helps isolate a risky/long feature; no empty commits.

Viva questions: 1. What requirement does EXPENSE-02 satisfy? 2. Which data/API/UI boundary does it change? 3. How is invalid or unauthorized input handled? 4. What test proves it works? 5. What limitation remains?

Definition of Done: ☐ Scope met  ☐ Code understood  ☐ Focused tests pass  ☐ No unrelated changes  ☐ Evidence recorded  ☐ Commit created  ☐ Docs updated if affected  ☐ Viva explanation ready

## EXPENSE-03 — Build expense UI

Proposal lead / workstream assignment: Rukaiya Akther Trisha — follows the proposal split; this is a planned role, not a contribution record.

Hands-on operator: Monira Islam (you) — you will carry out every task, including tasks assigned to the frontend/UI workstream.

Requirement: Seller must enter and review non-product costs.

Target: Expense table/form display amounts and dates clearly.

Why this task matters: Expense table/form display amounts and dates clearly. It isolates one change so the student can inspect, test, and explain it before moving on.

Prerequisites: EXPENSE-02; FRONTEND-03

Concepts to understand: Accessible currency form; date validation.

Expected files/modules: frontend/src/features/expenses; tests.

Implementation scope: No charts or financial statements in this task.

Not in this task: Other modules, unrelated refactors, new dependencies, and unapproved features.

Ready-to-paste Codex prompt

You are implementing SellerOS, the SE-331 standalone social-commerce seller BI/decision-support capstone. Implement only EXPENSE-03 — Build expense UI. Requirement: Seller must enter and review non-product costs. Objective/acceptance target: Expense table/form display amounts and dates clearly. Scope allowed: No charts or financial statements in this task. Likely files/modules: frontend/src/features/expenses; tests. Prerequisites: EXPENSE-02; FRONTEND-03. Constraints: follow the approved React/Vite/TypeScript + Django/DRF + PostgreSQL architecture and existing API/data contracts; inspect the repository first; preserve existing working behavior; do not invent unresolved business rules—mark [DECISION REQUIRED]; do not modify unrelated files, add unnecessary dependencies, expose secrets, bypass authentication/store permissions, fabricate AI/ML results, or create autonomous actions. Out of scope for this task: Other modules, unrelated refactors, new dependencies, and unapproved features. Test requirement: CRUD and loading/error/empty states pass. Run the narrow relevant checks and report exact commands and outcomes. Expected output: focused implementation, meaningful tests, and concise notes on files changed, decisions, risks, and next dependency. Code quality: small readable changes, type/validation/error handling appropriate to the existing project, no duplicated business formulas, and no generated or sensitive data committed.

Expected Codex output: A focused change for EXPENSE-03, relevant tests, a file-change summary, and exact commands/results. No unrelated implementation.

How to inspect: Review the diff for these boundaries: No charts or financial statements in this task. Confirm only expected files changed, validation/permissions match the contract, and tests exercise the requirement.

How to understand: Explain in your own words how Accessible currency form; date validation. support this task; trace one normal case and one failure case through the code.

Run commands: Use verified environment commands from SETUP-07. Typical checks: backend: `python manage.py check` and the focused Django test module; frontend: `npm run lint`, focused test, and `npm run build`. Run only commands applicable to changed code and report exact outcomes.

Test steps / expected result: CRUD and loading/error/empty states pass. Success means the target is present, tests pass, and failure behavior is understandable.

Common errors: If the DB is unavailable, verify PostgreSQL service, database name, credentials, and env loading. If imports/routes fail, check app registration and URL inclusion. If an API/UI mismatch appears, compare against docs/api-contract.md and correct the contract or implementation deliberately; do not patch around it.

Git milestone: After review and passing tests, commit only this task. Suggested: `git add <reviewed-files> && git commit -m "EXPENSE-03: build expense ui"`. Use a feature branch only when it helps isolate a risky/long feature; no empty commits.

Viva questions: 1. What requirement does EXPENSE-03 satisfy? 2. Which data/API/UI boundary does it change? 3. How is invalid or unauthorized input handled? 4. What test proves it works? 5. What limitation remains?

Definition of Done: ☐ Scope met  ☐ Code understood  ☐ Focused tests pass  ☐ No unrelated changes  ☐ Evidence recorded  ☐ Commit created  ☐ Docs updated if affected  ☐ Viva explanation ready

## EXPENSE-04 — Verify seeded demo records and reset command

Proposal lead / workstream assignment: Jointly assigned to Monira Islam and Rukaiya Akther Trisha — follows the proposal split; this is a planned role, not a contribution record.

Hands-on operator: Monira Islam (you) — you will carry out every task, including tasks assigned to the frontend/UI workstream.

Requirement: A repeatable demo needs predictable data without PII.

Target: Documented seed/reset commands generate approved product, customer, order, and expense scenarios.

Why this task matters: Documented seed/reset commands generate approved product, customer, order, and expense scenarios. It isolates one change so the student can inspect, test, and explain it before moving on.

Prerequisites: EXPENSE-03

Concepts to understand: Environment guards; fixture idempotency.

Expected files/modules: backend/management/commands; docs/demo-data; tests.

Implementation scope: Prevent accidental destructive reset against non-test environments.

Not in this task: Other modules, unrelated refactors, new dependencies, and unapproved features.

Ready-to-paste Codex prompt

You are implementing SellerOS, the SE-331 standalone social-commerce seller BI/decision-support capstone. Implement only EXPENSE-04 — Verify seeded demo records and reset command. Requirement: A repeatable demo needs predictable data without PII. Objective/acceptance target: Documented seed/reset commands generate approved product, customer, order, and expense scenarios. Scope allowed: Prevent accidental destructive reset against non-test environments. Likely files/modules: backend/management/commands; docs/demo-data; tests. Prerequisites: EXPENSE-03. Constraints: follow the approved React/Vite/TypeScript + Django/DRF + PostgreSQL architecture and existing API/data contracts; inspect the repository first; preserve existing working behavior; do not invent unresolved business rules—mark [DECISION REQUIRED]; do not modify unrelated files, add unnecessary dependencies, expose secrets, bypass authentication/store permissions, fabricate AI/ML results, or create autonomous actions. Out of scope for this task: Other modules, unrelated refactors, new dependencies, and unapproved features. Test requirement: Repeated run gives same expected metrics; production guard blocks. Run the narrow relevant checks and report exact commands and outcomes. Expected output: focused implementation, meaningful tests, and concise notes on files changed, decisions, risks, and next dependency. Code quality: small readable changes, type/validation/error handling appropriate to the existing project, no duplicated business formulas, and no generated or sensitive data committed.

Expected Codex output: A focused change for EXPENSE-04, relevant tests, a file-change summary, and exact commands/results. No unrelated implementation.

How to inspect: Review the diff for these boundaries: Prevent accidental destructive reset against non-test environments. Confirm only expected files changed, validation/permissions match the contract, and tests exercise the requirement.

How to understand: Explain in your own words how Environment guards; fixture idempotency. support this task; trace one normal case and one failure case through the code.

Run commands: Use verified environment commands from SETUP-07. Typical checks: backend: `python manage.py check` and the focused Django test module; frontend: `npm run lint`, focused test, and `npm run build`. Run only commands applicable to changed code and report exact outcomes.

Test steps / expected result: Repeated run gives same expected metrics; production guard blocks. Success means the target is present, tests pass, and failure behavior is understandable.

Common errors: If the DB is unavailable, verify PostgreSQL service, database name, credentials, and env loading. If imports/routes fail, check app registration and URL inclusion. If an API/UI mismatch appears, compare against docs/api-contract.md and correct the contract or implementation deliberately; do not patch around it.

Git milestone: After review and passing tests, commit only this task. Suggested: `git add <reviewed-files> && git commit -m "EXPENSE-04: verify seeded demo records and reset command"`. Use a feature branch only when it helps isolate a risky/long feature; no empty commits.

Viva questions: 1. What requirement does EXPENSE-04 satisfy? 2. Which data/API/UI boundary does it change? 3. How is invalid or unauthorized input handled? 4. What test proves it works? 5. What limitation remains?

Definition of Done: ☐ Scope met  ☐ Code understood  ☐ Focused tests pass  ☐ No unrelated changes  ☐ Evidence recorded  ☐ Commit created  ☐ Docs updated if affected  ☐ Viva explanation ready

# Phase 9 — Sales analytics, profit intelligence, and dashboard

Calculate explainable measures from verified transactions before asking AI to describe them.

## ANALYTICS-01 — Define sales metric contract and eligible records

Proposal lead / workstream assignment: Jointly assigned to Monira Islam and Rukaiya Akther Trisha — follows the proposal split; this is a planned role, not a contribution record.

Hands-on operator: Monira Islam (you) — you will carry out every task, including tasks assigned to the frontend/UI workstream.

Requirement: Dashboard metrics must be based on explicit definitions.

Target: Metric definitions cover date basis, statuses, returns, time zone, and empty periods.

Why this task matters: Metric definitions cover date basis, statuses, returns, time zone, and empty periods. It isolates one change so the student can inspect, test, and explain it before moving on.

Prerequisites: None beyond repository inspection and the approved project baseline.

Concepts to understand: Aggregation; business calendars; source records.

Expected files/modules: docs/metrics.md; backend analytics tests.

Implementation scope: Use PLAN-03 and mark missing choices [DECISION REQUIRED].

Not in this task: Other modules, unrelated refactors, new dependencies, and unapproved features.

Ready-to-paste Codex prompt

You are implementing SellerOS, the SE-331 standalone social-commerce seller BI/decision-support capstone. Implement only ANALYTICS-01 — Define sales metric contract and eligible records. Requirement: Dashboard metrics must be based on explicit definitions. Objective/acceptance target: Metric definitions cover date basis, statuses, returns, time zone, and empty periods. Scope allowed: Use PLAN-03 and mark missing choices [DECISION REQUIRED]. Likely files/modules: docs/metrics.md; backend analytics tests. Prerequisites: none beyond the approved project baseline. Constraints: follow the approved React/Vite/TypeScript + Django/DRF + PostgreSQL architecture and existing API/data contracts; inspect the repository first; preserve existing working behavior; do not invent unresolved business rules—mark [DECISION REQUIRED]; do not modify unrelated files, add unnecessary dependencies, expose secrets, bypass authentication/store permissions, fabricate AI/ML results, or create autonomous actions. Out of scope for this task: Other modules, unrelated refactors, new dependencies, and unapproved features. Test requirement: Metric examples are hand-calculable. Run the narrow relevant checks and report exact commands and outcomes. Expected output: focused implementation, meaningful tests, and concise notes on files changed, decisions, risks, and next dependency. Code quality: small readable changes, type/validation/error handling appropriate to the existing project, no duplicated business formulas, and no generated or sensitive data committed.

Expected Codex output: A focused change for ANALYTICS-01, relevant tests, a file-change summary, and exact commands/results. No unrelated implementation.

How to inspect: Review the diff for these boundaries: Use PLAN-03 and mark missing choices [DECISION REQUIRED]. Confirm only expected files changed, validation/permissions match the contract, and tests exercise the requirement.

How to understand: Explain in your own words how Aggregation; business calendars; source records. support this task; trace one normal case and one failure case through the code.

Run commands: Use verified environment commands from SETUP-07. Typical checks: backend: `python manage.py check` and the focused Django test module; frontend: `npm run lint`, focused test, and `npm run build`. Run only commands applicable to changed code and report exact outcomes.

Test steps / expected result: Metric examples are hand-calculable. Success means the target is present, tests pass, and failure behavior is understandable.

Common errors: If the DB is unavailable, verify PostgreSQL service, database name, credentials, and env loading. If imports/routes fail, check app registration and URL inclusion. If an API/UI mismatch appears, compare against docs/api-contract.md and correct the contract or implementation deliberately; do not patch around it.

Git milestone: After review and passing tests, commit only this task. Suggested: `git add <reviewed-files> && git commit -m "ANALYTICS-01: define sales metric contract and eligible records"`. Use a feature branch only when it helps isolate a risky/long feature; no empty commits.

Viva questions: 1. What requirement does ANALYTICS-01 satisfy? 2. Which data/API/UI boundary does it change? 3. How is invalid or unauthorized input handled? 4. What test proves it works? 5. What limitation remains?

Definition of Done: ☐ Scope met  ☐ Code understood  ☐ Focused tests pass  ☐ No unrelated changes  ☐ Evidence recorded  ☐ Commit created  ☐ Docs updated if affected  ☐ Viva explanation ready

## ANALYTICS-02 — Implement sales aggregation service

Proposal lead / workstream assignment: Monira Islam — follows the proposal split; this is a planned role, not a contribution record.

Hands-on operator: Monira Islam (you) — you will carry out every task, including tasks assigned to the frontend/UI workstream.

Requirement: Seller needs sales summaries by period and product.

Target: Backend returns agreed counts and revenue totals from eligible order lines.

Why this task matters: Backend returns agreed counts and revenue totals from eligible order lines. It isolates one change so the student can inspect, test, and explain it before moving on.

Prerequisites: ANALYTICS-01

Concepts to understand: Database aggregation; Decimal; query efficiency.

Expected files/modules: backend/apps/analytics/services/sales.py; tests.

Implementation scope: Deterministic queries only; no LLM arithmetic.

Not in this task: Other modules, unrelated refactors, new dependencies, and unapproved features.

Ready-to-paste Codex prompt

You are implementing SellerOS, the SE-331 standalone social-commerce seller BI/decision-support capstone. Implement only ANALYTICS-02 — Implement sales aggregation service. Requirement: Seller needs sales summaries by period and product. Objective/acceptance target: Backend returns agreed counts and revenue totals from eligible order lines. Scope allowed: Deterministic queries only; no LLM arithmetic. Likely files/modules: backend/apps/analytics/services/sales.py; tests. Prerequisites: ANALYTICS-01. Constraints: follow the approved React/Vite/TypeScript + Django/DRF + PostgreSQL architecture and existing API/data contracts; inspect the repository first; preserve existing working behavior; do not invent unresolved business rules—mark [DECISION REQUIRED]; do not modify unrelated files, add unnecessary dependencies, expose secrets, bypass authentication/store permissions, fabricate AI/ML results, or create autonomous actions. Out of scope for this task: Other modules, unrelated refactors, new dependencies, and unapproved features. Test requirement: Results match hand calculations across statuses and dates. Run the narrow relevant checks and report exact commands and outcomes. Expected output: focused implementation, meaningful tests, and concise notes on files changed, decisions, risks, and next dependency. Code quality: small readable changes, type/validation/error handling appropriate to the existing project, no duplicated business formulas, and no generated or sensitive data committed.

Expected Codex output: A focused change for ANALYTICS-02, relevant tests, a file-change summary, and exact commands/results. No unrelated implementation.

How to inspect: Review the diff for these boundaries: Deterministic queries only; no LLM arithmetic. Confirm only expected files changed, validation/permissions match the contract, and tests exercise the requirement.

How to understand: Explain in your own words how Database aggregation; Decimal; query efficiency. support this task; trace one normal case and one failure case through the code.

Run commands: Use verified environment commands from SETUP-07. Typical checks: backend: `python manage.py check` and the focused Django test module; frontend: `npm run lint`, focused test, and `npm run build`. Run only commands applicable to changed code and report exact outcomes.

Test steps / expected result: Results match hand calculations across statuses and dates. Success means the target is present, tests pass, and failure behavior is understandable.

Common errors: If the DB is unavailable, verify PostgreSQL service, database name, credentials, and env loading. If imports/routes fail, check app registration and URL inclusion. If an API/UI mismatch appears, compare against docs/api-contract.md and correct the contract or implementation deliberately; do not patch around it.

Git milestone: After review and passing tests, commit only this task. Suggested: `git add <reviewed-files> && git commit -m "ANALYTICS-02: implement sales aggregation service"`. Use a feature branch only when it helps isolate a risky/long feature; no empty commits.

Viva questions: 1. What requirement does ANALYTICS-02 satisfy? 2. Which data/API/UI boundary does it change? 3. How is invalid or unauthorized input handled? 4. What test proves it works? 5. What limitation remains?

Definition of Done: ☐ Scope met  ☐ Code understood  ☐ Focused tests pass  ☐ No unrelated changes  ☐ Evidence recorded  ☐ Commit created  ☐ Docs updated if affected  ☐ Viva explanation ready

## ANALYTICS-03 — Implement sales summary API

Proposal lead / workstream assignment: Monira Islam — follows the proposal split; this is a planned role, not a contribution record.

Hands-on operator: Monira Islam (you) — you will carry out every task, including tasks assigned to the frontend/UI workstream.

Requirement: Frontend needs a stable analytics endpoint.

Target: Store-scoped API exposes documented periods, filters, totals, and empty-data states.

Why this task matters: Store-scoped API exposes documented periods, filters, totals, and empty-data states. It isolates one change so the student can inspect, test, and explain it before moving on.

Prerequisites: ANALYTICS-02

Concepts to understand: API contract; date filtering; authorization.

Expected files/modules: backend/apps/analytics/api; tests; API docs.

Implementation scope: Validate date ranges and reuse metric service.

Not in this task: Other modules, unrelated refactors, new dependencies, and unapproved features.

Ready-to-paste Codex prompt

You are implementing SellerOS, the SE-331 standalone social-commerce seller BI/decision-support capstone. Implement only ANALYTICS-03 — Implement sales summary API. Requirement: Frontend needs a stable analytics endpoint. Objective/acceptance target: Store-scoped API exposes documented periods, filters, totals, and empty-data states. Scope allowed: Validate date ranges and reuse metric service. Likely files/modules: backend/apps/analytics/api; tests; API docs. Prerequisites: ANALYTICS-02. Constraints: follow the approved React/Vite/TypeScript + Django/DRF + PostgreSQL architecture and existing API/data contracts; inspect the repository first; preserve existing working behavior; do not invent unresolved business rules—mark [DECISION REQUIRED]; do not modify unrelated files, add unnecessary dependencies, expose secrets, bypass authentication/store permissions, fabricate AI/ML results, or create autonomous actions. Out of scope for this task: Other modules, unrelated refactors, new dependencies, and unapproved features. Test requirement: Request/response and failure cases tested. Run the narrow relevant checks and report exact commands and outcomes. Expected output: focused implementation, meaningful tests, and concise notes on files changed, decisions, risks, and next dependency. Code quality: small readable changes, type/validation/error handling appropriate to the existing project, no duplicated business formulas, and no generated or sensitive data committed.

Expected Codex output: A focused change for ANALYTICS-03, relevant tests, a file-change summary, and exact commands/results. No unrelated implementation.

How to inspect: Review the diff for these boundaries: Validate date ranges and reuse metric service. Confirm only expected files changed, validation/permissions match the contract, and tests exercise the requirement.

How to understand: Explain in your own words how API contract; date filtering; authorization. support this task; trace one normal case and one failure case through the code.

Run commands: Use verified environment commands from SETUP-07. Typical checks: backend: `python manage.py check` and the focused Django test module; frontend: `npm run lint`, focused test, and `npm run build`. Run only commands applicable to changed code and report exact outcomes.

Test steps / expected result: Request/response and failure cases tested. Success means the target is present, tests pass, and failure behavior is understandable.

Common errors: If the DB is unavailable, verify PostgreSQL service, database name, credentials, and env loading. If imports/routes fail, check app registration and URL inclusion. If an API/UI mismatch appears, compare against docs/api-contract.md and correct the contract or implementation deliberately; do not patch around it.

Git milestone: After review and passing tests, commit only this task. Suggested: `git add <reviewed-files> && git commit -m "ANALYTICS-03: implement sales summary api"`. Use a feature branch only when it helps isolate a risky/long feature; no empty commits.

Viva questions: 1. What requirement does ANALYTICS-03 satisfy? 2. Which data/API/UI boundary does it change? 3. How is invalid or unauthorized input handled? 4. What test proves it works? 5. What limitation remains?

Definition of Done: ☐ Scope met  ☐ Code understood  ☐ Focused tests pass  ☐ No unrelated changes  ☐ Evidence recorded  ☐ Commit created  ☐ Docs updated if affected  ☐ Viva explanation ready

## ANALYTICS-04 — Implement product performance breakdown

Proposal lead / workstream assignment: Monira Islam — follows the proposal split; this is a planned role, not a contribution record.

Hands-on operator: Monira Islam (you) — you will carry out every task, including tasks assigned to the frontend/UI workstream.

Requirement: Seller needs to compare product sales from recorded data.

Target: Service/API reports product quantities and revenue for selected period.

Why this task matters: Service/API reports product quantities and revenue for selected period. It isolates one change so the student can inspect, test, and explain it before moving on.

Prerequisites: ANALYTICS-03

Concepts to understand: Grouping; joins; null/inactive products.

Expected files/modules: backend/apps/analytics/services/products.py; tests.

Implementation scope: No unsupported profitability ranking here.

Not in this task: Other modules, unrelated refactors, new dependencies, and unapproved features.

Ready-to-paste Codex prompt

You are implementing SellerOS, the SE-331 standalone social-commerce seller BI/decision-support capstone. Implement only ANALYTICS-04 — Implement product performance breakdown. Requirement: Seller needs to compare product sales from recorded data. Objective/acceptance target: Service/API reports product quantities and revenue for selected period. Scope allowed: No unsupported profitability ranking here. Likely files/modules: backend/apps/analytics/services/products.py; tests. Prerequisites: ANALYTICS-03. Constraints: follow the approved React/Vite/TypeScript + Django/DRF + PostgreSQL architecture and existing API/data contracts; inspect the repository first; preserve existing working behavior; do not invent unresolved business rules—mark [DECISION REQUIRED]; do not modify unrelated files, add unnecessary dependencies, expose secrets, bypass authentication/store permissions, fabricate AI/ML results, or create autonomous actions. Out of scope for this task: Other modules, unrelated refactors, new dependencies, and unapproved features. Test requirement: Product totals reconcile to order line facts. Run the narrow relevant checks and report exact commands and outcomes. Expected output: focused implementation, meaningful tests, and concise notes on files changed, decisions, risks, and next dependency. Code quality: small readable changes, type/validation/error handling appropriate to the existing project, no duplicated business formulas, and no generated or sensitive data committed.

Expected Codex output: A focused change for ANALYTICS-04, relevant tests, a file-change summary, and exact commands/results. No unrelated implementation.

How to inspect: Review the diff for these boundaries: No unsupported profitability ranking here. Confirm only expected files changed, validation/permissions match the contract, and tests exercise the requirement.

How to understand: Explain in your own words how Grouping; joins; null/inactive products. support this task; trace one normal case and one failure case through the code.

Run commands: Use verified environment commands from SETUP-07. Typical checks: backend: `python manage.py check` and the focused Django test module; frontend: `npm run lint`, focused test, and `npm run build`. Run only commands applicable to changed code and report exact outcomes.

Test steps / expected result: Product totals reconcile to order line facts. Success means the target is present, tests pass, and failure behavior is understandable.

Common errors: If the DB is unavailable, verify PostgreSQL service, database name, credentials, and env loading. If imports/routes fail, check app registration and URL inclusion. If an API/UI mismatch appears, compare against docs/api-contract.md and correct the contract or implementation deliberately; do not patch around it.

Git milestone: After review and passing tests, commit only this task. Suggested: `git add <reviewed-files> && git commit -m "ANALYTICS-04: implement product performance breakdown"`. Use a feature branch only when it helps isolate a risky/long feature; no empty commits.

Viva questions: 1. What requirement does ANALYTICS-04 satisfy? 2. Which data/API/UI boundary does it change? 3. How is invalid or unauthorized input handled? 4. What test proves it works? 5. What limitation remains?

Definition of Done: ☐ Scope met  ☐ Code understood  ☐ Focused tests pass  ☐ No unrelated changes  ☐ Evidence recorded  ☐ Commit created  ☐ Docs updated if affected  ☐ Viva explanation ready

## ANALYTICS-05 — Add analytics API tests and query budget baseline

Proposal lead / workstream assignment: Jointly assigned to Monira Islam and Rukaiya Akther Trisha — follows the proposal split; this is a planned role, not a contribution record.

Hands-on operator: Monira Islam (you) — you will carry out every task, including tasks assigned to the frontend/UI workstream.

Requirement: Analytics correctness and basic performance need evidence.

Target: Edge-case tests and a repeatable query timing method exist.

Why this task matters: Edge-case tests and a repeatable query timing method exist. It isolates one change so the student can inspect, test, and explain it before moving on.

Prerequisites: ANALYTICS-04

Concepts to understand: Fixture coverage; query count; measured vs estimated.

Expected files/modules: backend/apps/analytics/tests; docs/performance-baseline.md.

Implementation scope: Record measurements only after running under named data/environment.

Not in this task: Other modules, unrelated refactors, new dependencies, and unapproved features.

Ready-to-paste Codex prompt

You are implementing SellerOS, the SE-331 standalone social-commerce seller BI/decision-support capstone. Implement only ANALYTICS-05 — Add analytics API tests and query budget baseline. Requirement: Analytics correctness and basic performance need evidence. Objective/acceptance target: Edge-case tests and a repeatable query timing method exist. Scope allowed: Record measurements only after running under named data/environment. Likely files/modules: backend/apps/analytics/tests; docs/performance-baseline.md. Prerequisites: ANALYTICS-04. Constraints: follow the approved React/Vite/TypeScript + Django/DRF + PostgreSQL architecture and existing API/data contracts; inspect the repository first; preserve existing working behavior; do not invent unresolved business rules—mark [DECISION REQUIRED]; do not modify unrelated files, add unnecessary dependencies, expose secrets, bypass authentication/store permissions, fabricate AI/ML results, or create autonomous actions. Out of scope for this task: Other modules, unrelated refactors, new dependencies, and unapproved features. Test requirement: Tests pass; baseline includes method and environment. Run the narrow relevant checks and report exact commands and outcomes. Expected output: focused implementation, meaningful tests, and concise notes on files changed, decisions, risks, and next dependency. Code quality: small readable changes, type/validation/error handling appropriate to the existing project, no duplicated business formulas, and no generated or sensitive data committed.

Expected Codex output: A focused change for ANALYTICS-05, relevant tests, a file-change summary, and exact commands/results. No unrelated implementation.

How to inspect: Review the diff for these boundaries: Record measurements only after running under named data/environment. Confirm only expected files changed, validation/permissions match the contract, and tests exercise the requirement.

How to understand: Explain in your own words how Fixture coverage; query count; measured vs estimated. support this task; trace one normal case and one failure case through the code.

Run commands: Use verified environment commands from SETUP-07. Typical checks: backend: `python manage.py check` and the focused Django test module; frontend: `npm run lint`, focused test, and `npm run build`. Run only commands applicable to changed code and report exact outcomes.

Test steps / expected result: Tests pass; baseline includes method and environment. Success means the target is present, tests pass, and failure behavior is understandable.

Common errors: If the DB is unavailable, verify PostgreSQL service, database name, credentials, and env loading. If imports/routes fail, check app registration and URL inclusion. If an API/UI mismatch appears, compare against docs/api-contract.md and correct the contract or implementation deliberately; do not patch around it.

Git milestone: After review and passing tests, commit only this task. Suggested: `git add <reviewed-files> && git commit -m "ANALYTICS-05: add analytics api tests and query budget baseline"`. Use a feature branch only when it helps isolate a risky/long feature; no empty commits.

Viva questions: 1. What requirement does ANALYTICS-05 satisfy? 2. Which data/API/UI boundary does it change? 3. How is invalid or unauthorized input handled? 4. What test proves it works? 5. What limitation remains?

Definition of Done: ☐ Scope met  ☐ Code understood  ☐ Focused tests pass  ☐ No unrelated changes  ☐ Evidence recorded  ☐ Commit created  ☐ Docs updated if affected  ☐ Viva explanation ready

## PROFIT-01 — Approve estimated-profit formula and cost treatment

Proposal lead / workstream assignment: Jointly assigned to Monira Islam and Rukaiya Akther Trisha — follows the proposal split; this is a planned role, not a contribution record.

Hands-on operator: Monira Islam (you) — you will carry out every task, including tasks assigned to the frontend/UI workstream.

Requirement: Profit intelligence must be hand-checkable and deterministic.

Target: Formula defines revenue, product cost, discounts, delivery, other expense allocation, missing fields, period, and rounding.

Why this task matters: Formula defines revenue, product cost, discounts, delivery, other expense allocation, missing fields, period, and rounding. It isolates one change so the student can inspect, test, and explain it before moving on.

Prerequisites: ANALYTICS-05

Concepts to understand: Revenue vs margin; cost allocation; precision.

Expected files/modules: docs/profit-formula.md; examples.

Implementation scope: Do not choose unspecified accounting semantics silently; mark [DECISION REQUIRED].

Not in this task: Other modules, unrelated refactors, new dependencies, and unapproved features.

Ready-to-paste Codex prompt

You are implementing SellerOS, the SE-331 standalone social-commerce seller BI/decision-support capstone. Implement only PROFIT-01 — Approve estimated-profit formula and cost treatment. Requirement: Profit intelligence must be hand-checkable and deterministic. Objective/acceptance target: Formula defines revenue, product cost, discounts, delivery, other expense allocation, missing fields, period, and rounding. Scope allowed: Do not choose unspecified accounting semantics silently; mark [DECISION REQUIRED]. Likely files/modules: docs/profit-formula.md; examples. Prerequisites: ANALYTICS-05. Constraints: follow the approved React/Vite/TypeScript + Django/DRF + PostgreSQL architecture and existing API/data contracts; inspect the repository first; preserve existing working behavior; do not invent unresolved business rules—mark [DECISION REQUIRED]; do not modify unrelated files, add unnecessary dependencies, expose secrets, bypass authentication/store permissions, fabricate AI/ML results, or create autonomous actions. Out of scope for this task: Other modules, unrelated refactors, new dependencies, and unapproved features. Test requirement: Worked examples are approved before implementation. Run the narrow relevant checks and report exact commands and outcomes. Expected output: focused implementation, meaningful tests, and concise notes on files changed, decisions, risks, and next dependency. Code quality: small readable changes, type/validation/error handling appropriate to the existing project, no duplicated business formulas, and no generated or sensitive data committed.

Expected Codex output: A focused change for PROFIT-01, relevant tests, a file-change summary, and exact commands/results. No unrelated implementation.

How to inspect: Review the diff for these boundaries: Do not choose unspecified accounting semantics silently; mark [DECISION REQUIRED]. Confirm only expected files changed, validation/permissions match the contract, and tests exercise the requirement.

How to understand: Explain in your own words how Revenue vs margin; cost allocation; precision. support this task; trace one normal case and one failure case through the code.

Run commands: Use verified environment commands from SETUP-07. Typical checks: backend: `python manage.py check` and the focused Django test module; frontend: `npm run lint`, focused test, and `npm run build`. Run only commands applicable to changed code and report exact outcomes.

Test steps / expected result: Worked examples are approved before implementation. Success means the target is present, tests pass, and failure behavior is understandable.

Common errors: If the DB is unavailable, verify PostgreSQL service, database name, credentials, and env loading. If imports/routes fail, check app registration and URL inclusion. If an API/UI mismatch appears, compare against docs/api-contract.md and correct the contract or implementation deliberately; do not patch around it.

Git milestone: After review and passing tests, commit only this task. Suggested: `git add <reviewed-files> && git commit -m "PROFIT-01: approve estimated-profit formula and cost treatment"`. Use a feature branch only when it helps isolate a risky/long feature; no empty commits.

Viva questions: 1. What requirement does PROFIT-01 satisfy? 2. Which data/API/UI boundary does it change? 3. How is invalid or unauthorized input handled? 4. What test proves it works? 5. What limitation remains?

Definition of Done: ☐ Scope met  ☐ Code understood  ☐ Focused tests pass  ☐ No unrelated changes  ☐ Evidence recorded  ☐ Commit created  ☐ Docs updated if affected  ☐ Viva explanation ready

## PROFIT-02 — Implement order-level profit calculation service

Proposal lead / workstream assignment: Monira Islam — follows the proposal split; this is a planned role, not a contribution record.

Hands-on operator: Monira Islam (you) — you will carry out every task, including tasks assigned to the frontend/UI workstream.

Requirement: Seller needs estimated profit from recorded transaction costs.

Target: Service computes order/item contribution using approved formula and completeness flags.

Why this task matters: Service computes order/item contribution using approved formula and completeness flags. It isolates one change so the student can inspect, test, and explain it before moving on.

Prerequisites: PROFIT-01

Concepts to understand: Pure functions; Decimal; missing data.

Expected files/modules: backend/apps/profit/services/order_profit.py; tests.

Implementation scope: Pure deterministic code; do not use LLM for arithmetic.

Not in this task: Other modules, unrelated refactors, new dependencies, and unapproved features.

Ready-to-paste Codex prompt

You are implementing SellerOS, the SE-331 standalone social-commerce seller BI/decision-support capstone. Implement only PROFIT-02 — Implement order-level profit calculation service. Requirement: Seller needs estimated profit from recorded transaction costs. Objective/acceptance target: Service computes order/item contribution using approved formula and completeness flags. Scope allowed: Pure deterministic code; do not use LLM for arithmetic. Likely files/modules: backend/apps/profit/services/order_profit.py; tests. Prerequisites: PROFIT-01. Constraints: follow the approved React/Vite/TypeScript + Django/DRF + PostgreSQL architecture and existing API/data contracts; inspect the repository first; preserve existing working behavior; do not invent unresolved business rules—mark [DECISION REQUIRED]; do not modify unrelated files, add unnecessary dependencies, expose secrets, bypass authentication/store permissions, fabricate AI/ML results, or create autonomous actions. Out of scope for this task: Other modules, unrelated refactors, new dependencies, and unapproved features. Test requirement: Unit tests match hand calculations and missing-cost behavior. Run the narrow relevant checks and report exact commands and outcomes. Expected output: focused implementation, meaningful tests, and concise notes on files changed, decisions, risks, and next dependency. Code quality: small readable changes, type/validation/error handling appropriate to the existing project, no duplicated business formulas, and no generated or sensitive data committed.

Expected Codex output: A focused change for PROFIT-02, relevant tests, a file-change summary, and exact commands/results. No unrelated implementation.

How to inspect: Review the diff for these boundaries: Pure deterministic code; do not use LLM for arithmetic. Confirm only expected files changed, validation/permissions match the contract, and tests exercise the requirement.

How to understand: Explain in your own words how Pure functions; Decimal; missing data. support this task; trace one normal case and one failure case through the code.

Run commands: Use verified environment commands from SETUP-07. Typical checks: backend: `python manage.py check` and the focused Django test module; frontend: `npm run lint`, focused test, and `npm run build`. Run only commands applicable to changed code and report exact outcomes.

Test steps / expected result: Unit tests match hand calculations and missing-cost behavior. Success means the target is present, tests pass, and failure behavior is understandable.

Common errors: If the DB is unavailable, verify PostgreSQL service, database name, credentials, and env loading. If imports/routes fail, check app registration and URL inclusion. If an API/UI mismatch appears, compare against docs/api-contract.md and correct the contract or implementation deliberately; do not patch around it.

Git milestone: After review and passing tests, commit only this task. Suggested: `git add <reviewed-files> && git commit -m "PROFIT-02: implement order-level profit calculation service"`. Use a feature branch only when it helps isolate a risky/long feature; no empty commits.

Viva questions: 1. What requirement does PROFIT-02 satisfy? 2. Which data/API/UI boundary does it change? 3. How is invalid or unauthorized input handled? 4. What test proves it works? 5. What limitation remains?

Definition of Done: ☐ Scope met  ☐ Code understood  ☐ Focused tests pass  ☐ No unrelated changes  ☐ Evidence recorded  ☐ Commit created  ☐ Docs updated if affected  ☐ Viva explanation ready

## PROFIT-03 — Implement period-level profit aggregation

Proposal lead / workstream assignment: Monira Islam — follows the proposal split; this is a planned role, not a contribution record.

Hands-on operator: Monira Islam (you) — you will carry out every task, including tasks assigned to the frontend/UI workstream.

Requirement: Seller needs period totals that reconcile to orders and expenses.

Target: Service combines eligible order profit and approved expense treatment.

Why this task matters: Service combines eligible order profit and approved expense treatment. It isolates one change so the student can inspect, test, and explain it before moving on.

Prerequisites: PROFIT-02

Concepts to understand: Aggregation; expense assignment; incomplete data.

Expected files/modules: backend/apps/profit/services/period_profit.py; tests.

Implementation scope: No formal accounting output or tax statements.

Not in this task: Other modules, unrelated refactors, new dependencies, and unapproved features.

Ready-to-paste Codex prompt

You are implementing SellerOS, the SE-331 standalone social-commerce seller BI/decision-support capstone. Implement only PROFIT-03 — Implement period-level profit aggregation. Requirement: Seller needs period totals that reconcile to orders and expenses. Objective/acceptance target: Service combines eligible order profit and approved expense treatment. Scope allowed: No formal accounting output or tax statements. Likely files/modules: backend/apps/profit/services/period_profit.py; tests. Prerequisites: PROFIT-02. Constraints: follow the approved React/Vite/TypeScript + Django/DRF + PostgreSQL architecture and existing API/data contracts; inspect the repository first; preserve existing working behavior; do not invent unresolved business rules—mark [DECISION REQUIRED]; do not modify unrelated files, add unnecessary dependencies, expose secrets, bypass authentication/store permissions, fabricate AI/ML results, or create autonomous actions. Out of scope for this task: Other modules, unrelated refactors, new dependencies, and unapproved features. Test requirement: Totals reconcile to row-level computations. Run the narrow relevant checks and report exact commands and outcomes. Expected output: focused implementation, meaningful tests, and concise notes on files changed, decisions, risks, and next dependency. Code quality: small readable changes, type/validation/error handling appropriate to the existing project, no duplicated business formulas, and no generated or sensitive data committed.

Expected Codex output: A focused change for PROFIT-03, relevant tests, a file-change summary, and exact commands/results. No unrelated implementation.

How to inspect: Review the diff for these boundaries: No formal accounting output or tax statements. Confirm only expected files changed, validation/permissions match the contract, and tests exercise the requirement.

How to understand: Explain in your own words how Aggregation; expense assignment; incomplete data. support this task; trace one normal case and one failure case through the code.

Run commands: Use verified environment commands from SETUP-07. Typical checks: backend: `python manage.py check` and the focused Django test module; frontend: `npm run lint`, focused test, and `npm run build`. Run only commands applicable to changed code and report exact outcomes.

Test steps / expected result: Totals reconcile to row-level computations. Success means the target is present, tests pass, and failure behavior is understandable.

Common errors: If the DB is unavailable, verify PostgreSQL service, database name, credentials, and env loading. If imports/routes fail, check app registration and URL inclusion. If an API/UI mismatch appears, compare against docs/api-contract.md and correct the contract or implementation deliberately; do not patch around it.

Git milestone: After review and passing tests, commit only this task. Suggested: `git add <reviewed-files> && git commit -m "PROFIT-03: implement period-level profit aggregation"`. Use a feature branch only when it helps isolate a risky/long feature; no empty commits.

Viva questions: 1. What requirement does PROFIT-03 satisfy? 2. Which data/API/UI boundary does it change? 3. How is invalid or unauthorized input handled? 4. What test proves it works? 5. What limitation remains?

Definition of Done: ☐ Scope met  ☐ Code understood  ☐ Focused tests pass  ☐ No unrelated changes  ☐ Evidence recorded  ☐ Commit created  ☐ Docs updated if affected  ☐ Viva explanation ready

## PROFIT-04 — Implement profit API with calculation basis

Proposal lead / workstream assignment: Monira Islam — follows the proposal split; this is a planned role, not a contribution record.

Hands-on operator: Monira Islam (you) — you will carry out every task, including tasks assigned to the frontend/UI workstream.

Requirement: UI/advisor need both values and explanations of the calculation basis.

Target: API returns estimated metric, period, included records, completeness, and warnings.

Why this task matters: API returns estimated metric, period, included records, completeness, and warnings. It isolates one change so the student can inspect, test, and explain it before moving on.

Prerequisites: PROFIT-03

Concepts to understand: Response schemas; provenance; warnings.

Expected files/modules: backend/apps/profit/api; tests; API docs.

Implementation scope: Expose no unsupported certainty; maintain store isolation.

Not in this task: Other modules, unrelated refactors, new dependencies, and unapproved features.

Ready-to-paste Codex prompt

You are implementing SellerOS, the SE-331 standalone social-commerce seller BI/decision-support capstone. Implement only PROFIT-04 — Implement profit API with calculation basis. Requirement: UI/advisor need both values and explanations of the calculation basis. Objective/acceptance target: API returns estimated metric, period, included records, completeness, and warnings. Scope allowed: Expose no unsupported certainty; maintain store isolation. Likely files/modules: backend/apps/profit/api; tests; API docs. Prerequisites: PROFIT-03. Constraints: follow the approved React/Vite/TypeScript + Django/DRF + PostgreSQL architecture and existing API/data contracts; inspect the repository first; preserve existing working behavior; do not invent unresolved business rules—mark [DECISION REQUIRED]; do not modify unrelated files, add unnecessary dependencies, expose secrets, bypass authentication/store permissions, fabricate AI/ML results, or create autonomous actions. Out of scope for this task: Other modules, unrelated refactors, new dependencies, and unapproved features. Test requirement: Contract tests verify totals and basis metadata. Run the narrow relevant checks and report exact commands and outcomes. Expected output: focused implementation, meaningful tests, and concise notes on files changed, decisions, risks, and next dependency. Code quality: small readable changes, type/validation/error handling appropriate to the existing project, no duplicated business formulas, and no generated or sensitive data committed.

Expected Codex output: A focused change for PROFIT-04, relevant tests, a file-change summary, and exact commands/results. No unrelated implementation.

How to inspect: Review the diff for these boundaries: Expose no unsupported certainty; maintain store isolation. Confirm only expected files changed, validation/permissions match the contract, and tests exercise the requirement.

How to understand: Explain in your own words how Response schemas; provenance; warnings. support this task; trace one normal case and one failure case through the code.

Run commands: Use verified environment commands from SETUP-07. Typical checks: backend: `python manage.py check` and the focused Django test module; frontend: `npm run lint`, focused test, and `npm run build`. Run only commands applicable to changed code and report exact outcomes.

Test steps / expected result: Contract tests verify totals and basis metadata. Success means the target is present, tests pass, and failure behavior is understandable.

Common errors: If the DB is unavailable, verify PostgreSQL service, database name, credentials, and env loading. If imports/routes fail, check app registration and URL inclusion. If an API/UI mismatch appears, compare against docs/api-contract.md and correct the contract or implementation deliberately; do not patch around it.

Git milestone: After review and passing tests, commit only this task. Suggested: `git add <reviewed-files> && git commit -m "PROFIT-04: implement profit api with calculation basis"`. Use a feature branch only when it helps isolate a risky/long feature; no empty commits.

Viva questions: 1. What requirement does PROFIT-04 satisfy? 2. Which data/API/UI boundary does it change? 3. How is invalid or unauthorized input handled? 4. What test proves it works? 5. What limitation remains?

Definition of Done: ☐ Scope met  ☐ Code understood  ☐ Focused tests pass  ☐ No unrelated changes  ☐ Evidence recorded  ☐ Commit created  ☐ Docs updated if affected  ☐ Viva explanation ready

## PROFIT-05 — Build profit table and visualization UI

Proposal lead / workstream assignment: Rukaiya Akther Trisha — follows the proposal split; this is a planned role, not a contribution record.

Hands-on operator: Monira Islam (you) — you will carry out every task, including tasks assigned to the frontend/UI workstream.

Requirement: Seller should see revenue and estimated profit separately.

Target: UI shows calculated values, contributing costs, assumptions, and incomplete-data state.

Why this task matters: UI shows calculated values, contributing costs, assumptions, and incomplete-data state. It isolates one change so the student can inspect, test, and explain it before moving on.

Prerequisites: PROFIT-04

Concepts to understand: Data visualization; labeling; chart accessibility.

Expected files/modules: frontend/src/features/profit; tests.

Implementation scope: Avoid representing estimate as audited profit.

Not in this task: Other modules, unrelated refactors, new dependencies, and unapproved features.

Ready-to-paste Codex prompt

You are implementing SellerOS, the SE-331 standalone social-commerce seller BI/decision-support capstone. Implement only PROFIT-05 — Build profit table and visualization UI. Requirement: Seller should see revenue and estimated profit separately. Objective/acceptance target: UI shows calculated values, contributing costs, assumptions, and incomplete-data state. Scope allowed: Avoid representing estimate as audited profit. Likely files/modules: frontend/src/features/profit; tests. Prerequisites: PROFIT-04. Constraints: follow the approved React/Vite/TypeScript + Django/DRF + PostgreSQL architecture and existing API/data contracts; inspect the repository first; preserve existing working behavior; do not invent unresolved business rules—mark [DECISION REQUIRED]; do not modify unrelated files, add unnecessary dependencies, expose secrets, bypass authentication/store permissions, fabricate AI/ML results, or create autonomous actions. Out of scope for this task: Other modules, unrelated refactors, new dependencies, and unapproved features. Test requirement: UI labels estimate and handles missing input transparently. Run the narrow relevant checks and report exact commands and outcomes. Expected output: focused implementation, meaningful tests, and concise notes on files changed, decisions, risks, and next dependency. Code quality: small readable changes, type/validation/error handling appropriate to the existing project, no duplicated business formulas, and no generated or sensitive data committed.

Expected Codex output: A focused change for PROFIT-05, relevant tests, a file-change summary, and exact commands/results. No unrelated implementation.

How to inspect: Review the diff for these boundaries: Avoid representing estimate as audited profit. Confirm only expected files changed, validation/permissions match the contract, and tests exercise the requirement.

How to understand: Explain in your own words how Data visualization; labeling; chart accessibility. support this task; trace one normal case and one failure case through the code.

Run commands: Use verified environment commands from SETUP-07. Typical checks: backend: `python manage.py check` and the focused Django test module; frontend: `npm run lint`, focused test, and `npm run build`. Run only commands applicable to changed code and report exact outcomes.

Test steps / expected result: UI labels estimate and handles missing input transparently. Success means the target is present, tests pass, and failure behavior is understandable.

Common errors: If the DB is unavailable, verify PostgreSQL service, database name, credentials, and env loading. If imports/routes fail, check app registration and URL inclusion. If an API/UI mismatch appears, compare against docs/api-contract.md and correct the contract or implementation deliberately; do not patch around it.

Git milestone: After review and passing tests, commit only this task. Suggested: `git add <reviewed-files> && git commit -m "PROFIT-05: build profit table and visualization ui"`. Use a feature branch only when it helps isolate a risky/long feature; no empty commits.

Viva questions: 1. What requirement does PROFIT-05 satisfy? 2. Which data/API/UI boundary does it change? 3. How is invalid or unauthorized input handled? 4. What test proves it works? 5. What limitation remains?

Definition of Done: ☐ Scope met  ☐ Code understood  ☐ Focused tests pass  ☐ No unrelated changes  ☐ Evidence recorded  ☐ Commit created  ☐ Docs updated if affected  ☐ Viva explanation ready

## PROFIT-06 — Audit profit examples and regression cases

Proposal lead / workstream assignment: Jointly assigned to Monira Islam and Rukaiya Akther Trisha — follows the proposal split; this is a planned role, not a contribution record.

Hands-on operator: Monira Islam (you) — you will carry out every task, including tasks assigned to the frontend/UI workstream.

Requirement: Financial calculations need reproducible verification.

Target: Versioned examples and tests cover discounts, delivery, missing cost, expense, and zero sales.

Why this task matters: Versioned examples and tests cover discounts, delivery, missing cost, expense, and zero sales. It isolates one change so the student can inspect, test, and explain it before moving on.

Prerequisites: PROFIT-05

Concepts to understand: Boundary cases; regression tests.

Expected files/modules: tests/analytics/profit_cases; docs/evaluation.

Implementation scope: Use formulas and accepted business rules only.

Not in this task: Other modules, unrelated refactors, new dependencies, and unapproved features.

Ready-to-paste Codex prompt

You are implementing SellerOS, the SE-331 standalone social-commerce seller BI/decision-support capstone. Implement only PROFIT-06 — Audit profit examples and regression cases. Requirement: Financial calculations need reproducible verification. Objective/acceptance target: Versioned examples and tests cover discounts, delivery, missing cost, expense, and zero sales. Scope allowed: Use formulas and accepted business rules only. Likely files/modules: tests/analytics/profit_cases; docs/evaluation. Prerequisites: PROFIT-05. Constraints: follow the approved React/Vite/TypeScript + Django/DRF + PostgreSQL architecture and existing API/data contracts; inspect the repository first; preserve existing working behavior; do not invent unresolved business rules—mark [DECISION REQUIRED]; do not modify unrelated files, add unnecessary dependencies, expose secrets, bypass authentication/store permissions, fabricate AI/ML results, or create autonomous actions. Out of scope for this task: Other modules, unrelated refactors, new dependencies, and unapproved features. Test requirement: Independent hand calculation agrees with API output. Run the narrow relevant checks and report exact commands and outcomes. Expected output: focused implementation, meaningful tests, and concise notes on files changed, decisions, risks, and next dependency. Code quality: small readable changes, type/validation/error handling appropriate to the existing project, no duplicated business formulas, and no generated or sensitive data committed.

Expected Codex output: A focused change for PROFIT-06, relevant tests, a file-change summary, and exact commands/results. No unrelated implementation.

How to inspect: Review the diff for these boundaries: Use formulas and accepted business rules only. Confirm only expected files changed, validation/permissions match the contract, and tests exercise the requirement.

How to understand: Explain in your own words how Boundary cases; regression tests. support this task; trace one normal case and one failure case through the code.

Run commands: Use verified environment commands from SETUP-07. Typical checks: backend: `python manage.py check` and the focused Django test module; frontend: `npm run lint`, focused test, and `npm run build`. Run only commands applicable to changed code and report exact outcomes.

Test steps / expected result: Independent hand calculation agrees with API output. Success means the target is present, tests pass, and failure behavior is understandable.

Common errors: If the DB is unavailable, verify PostgreSQL service, database name, credentials, and env loading. If imports/routes fail, check app registration and URL inclusion. If an API/UI mismatch appears, compare against docs/api-contract.md and correct the contract or implementation deliberately; do not patch around it.

Git milestone: After review and passing tests, commit only this task. Suggested: `git add <reviewed-files> && git commit -m "PROFIT-06: audit profit examples and regression cases"`. Use a feature branch only when it helps isolate a risky/long feature; no empty commits.

Viva questions: 1. What requirement does PROFIT-06 satisfy? 2. Which data/API/UI boundary does it change? 3. How is invalid or unauthorized input handled? 4. What test proves it works? 5. What limitation remains?

Definition of Done: ☐ Scope met  ☐ Code understood  ☐ Focused tests pass  ☐ No unrelated changes  ☐ Evidence recorded  ☐ Commit created  ☐ Docs updated if affected  ☐ Viva explanation ready

# Phase 10 — Dashboard

Present the approved indicators clearly and provide empty/error states.

## DASH-01 — Define dashboard layout and data contract

Proposal lead / workstream assignment: Jointly assigned to Monira Islam and Rukaiya Akther Trisha — follows the proposal split; this is a planned role, not a contribution record.

Hands-on operator: Monira Islam (you) — you will carry out every task, including tasks assigned to the frontend/UI workstream.

Requirement: Dashboard cards and charts need approved metrics and filters.

Target: Wireframe maps each visual to an endpoint, metric, and period filter.

Why this task matters: Wireframe maps each visual to an endpoint, metric, and period filter. It isolates one change so the student can inspect, test, and explain it before moving on.

Prerequisites: None beyond repository inspection and the approved project baseline.

Concepts to understand: Information hierarchy; chart semantics; contract design.

Expected files/modules: docs/ui/dashboard-contract.md; frontend types.

Implementation scope: Keep scope to proposal dashboards; no invented KPIs.

Not in this task: Other modules, unrelated refactors, new dependencies, and unapproved features.

Ready-to-paste Codex prompt

You are implementing SellerOS, the SE-331 standalone social-commerce seller BI/decision-support capstone. Implement only DASH-01 — Define dashboard layout and data contract. Requirement: Dashboard cards and charts need approved metrics and filters. Objective/acceptance target: Wireframe maps each visual to an endpoint, metric, and period filter. Scope allowed: Keep scope to proposal dashboards; no invented KPIs. Likely files/modules: docs/ui/dashboard-contract.md; frontend types. Prerequisites: none beyond the approved project baseline. Constraints: follow the approved React/Vite/TypeScript + Django/DRF + PostgreSQL architecture and existing API/data contracts; inspect the repository first; preserve existing working behavior; do not invent unresolved business rules—mark [DECISION REQUIRED]; do not modify unrelated files, add unnecessary dependencies, expose secrets, bypass authentication/store permissions, fabricate AI/ML results, or create autonomous actions. Out of scope for this task: Other modules, unrelated refactors, new dependencies, and unapproved features. Test requirement: Every widget has source, unit, and empty-state behavior. Run the narrow relevant checks and report exact commands and outcomes. Expected output: focused implementation, meaningful tests, and concise notes on files changed, decisions, risks, and next dependency. Code quality: small readable changes, type/validation/error handling appropriate to the existing project, no duplicated business formulas, and no generated or sensitive data committed.

Expected Codex output: A focused change for DASH-01, relevant tests, a file-change summary, and exact commands/results. No unrelated implementation.

How to inspect: Review the diff for these boundaries: Keep scope to proposal dashboards; no invented KPIs. Confirm only expected files changed, validation/permissions match the contract, and tests exercise the requirement.

How to understand: Explain in your own words how Information hierarchy; chart semantics; contract design. support this task; trace one normal case and one failure case through the code.

Run commands: Use verified environment commands from SETUP-07. Typical checks: backend: `python manage.py check` and the focused Django test module; frontend: `npm run lint`, focused test, and `npm run build`. Run only commands applicable to changed code and report exact outcomes.

Test steps / expected result: Every widget has source, unit, and empty-state behavior. Success means the target is present, tests pass, and failure behavior is understandable.

Common errors: If the DB is unavailable, verify PostgreSQL service, database name, credentials, and env loading. If imports/routes fail, check app registration and URL inclusion. If an API/UI mismatch appears, compare against docs/api-contract.md and correct the contract or implementation deliberately; do not patch around it.

Git milestone: After review and passing tests, commit only this task. Suggested: `git add <reviewed-files> && git commit -m "DASH-01: define dashboard layout and data contract"`. Use a feature branch only when it helps isolate a risky/long feature; no empty commits.

Viva questions: 1. What requirement does DASH-01 satisfy? 2. Which data/API/UI boundary does it change? 3. How is invalid or unauthorized input handled? 4. What test proves it works? 5. What limitation remains?

Definition of Done: ☐ Scope met  ☐ Code understood  ☐ Focused tests pass  ☐ No unrelated changes  ☐ Evidence recorded  ☐ Commit created  ☐ Docs updated if affected  ☐ Viva explanation ready

## DASH-02 — Implement dashboard summary API composition

Proposal lead / workstream assignment: Monira Islam — follows the proposal split; this is a planned role, not a contribution record.

Hands-on operator: Monira Islam (you) — you will carry out every task, including tasks assigned to the frontend/UI workstream.

Requirement: Dashboard needs a coherent response without duplicating formulas.

Target: API composes tested sales, product, inventory, and profit services.

Why this task matters: API composes tested sales, product, inventory, and profit services. It isolates one change so the student can inspect, test, and explain it before moving on.

Prerequisites: DASH-01

Concepts to understand: Service orchestration; query reuse; latency.

Expected files/modules: backend/apps/analytics/api/dashboard; tests.

Implementation scope: Do not reimplement calculations in view or frontend.

Not in this task: Other modules, unrelated refactors, new dependencies, and unapproved features.

Ready-to-paste Codex prompt

You are implementing SellerOS, the SE-331 standalone social-commerce seller BI/decision-support capstone. Implement only DASH-02 — Implement dashboard summary API composition. Requirement: Dashboard needs a coherent response without duplicating formulas. Objective/acceptance target: API composes tested sales, product, inventory, and profit services. Scope allowed: Do not reimplement calculations in view or frontend. Likely files/modules: backend/apps/analytics/api/dashboard; tests. Prerequisites: DASH-01. Constraints: follow the approved React/Vite/TypeScript + Django/DRF + PostgreSQL architecture and existing API/data contracts; inspect the repository first; preserve existing working behavior; do not invent unresolved business rules—mark [DECISION REQUIRED]; do not modify unrelated files, add unnecessary dependencies, expose secrets, bypass authentication/store permissions, fabricate AI/ML results, or create autonomous actions. Out of scope for this task: Other modules, unrelated refactors, new dependencies, and unapproved features. Test requirement: Composed values match component service values. Run the narrow relevant checks and report exact commands and outcomes. Expected output: focused implementation, meaningful tests, and concise notes on files changed, decisions, risks, and next dependency. Code quality: small readable changes, type/validation/error handling appropriate to the existing project, no duplicated business formulas, and no generated or sensitive data committed.

Expected Codex output: A focused change for DASH-02, relevant tests, a file-change summary, and exact commands/results. No unrelated implementation.

How to inspect: Review the diff for these boundaries: Do not reimplement calculations in view or frontend. Confirm only expected files changed, validation/permissions match the contract, and tests exercise the requirement.

How to understand: Explain in your own words how Service orchestration; query reuse; latency. support this task; trace one normal case and one failure case through the code.

Run commands: Use verified environment commands from SETUP-07. Typical checks: backend: `python manage.py check` and the focused Django test module; frontend: `npm run lint`, focused test, and `npm run build`. Run only commands applicable to changed code and report exact outcomes.

Test steps / expected result: Composed values match component service values. Success means the target is present, tests pass, and failure behavior is understandable.

Common errors: If the DB is unavailable, verify PostgreSQL service, database name, credentials, and env loading. If imports/routes fail, check app registration and URL inclusion. If an API/UI mismatch appears, compare against docs/api-contract.md and correct the contract or implementation deliberately; do not patch around it.

Git milestone: After review and passing tests, commit only this task. Suggested: `git add <reviewed-files> && git commit -m "DASH-02: implement dashboard summary api composition"`. Use a feature branch only when it helps isolate a risky/long feature; no empty commits.

Viva questions: 1. What requirement does DASH-02 satisfy? 2. Which data/API/UI boundary does it change? 3. How is invalid or unauthorized input handled? 4. What test proves it works? 5. What limitation remains?

Definition of Done: ☐ Scope met  ☐ Code understood  ☐ Focused tests pass  ☐ No unrelated changes  ☐ Evidence recorded  ☐ Commit created  ☐ Docs updated if affected  ☐ Viva explanation ready

## DASH-03 — Build responsive dashboard charts and cards

Proposal lead / workstream assignment: Rukaiya Akther Trisha — follows the proposal split; this is a planned role, not a contribution record.

Hands-on operator: Monira Islam (you) — you will carry out every task, including tasks assigned to the frontend/UI workstream.

Requirement: Seller needs readable sales and performance summaries.

Target: Dashboard visualizes the documented measures with accessible labels and period controls.

Why this task matters: Dashboard visualizes the documented measures with accessible labels and period controls. It isolates one change so the student can inspect, test, and explain it before moving on.

Prerequisites: DASH-01; DASH-02; FRONTEND-03

Concepts to understand: Recharts; responsive layout; accessible chart alternatives.

Expected files/modules: frontend/src/features/dashboard; tests.

Implementation scope: No fabricated data; sample data must be explicitly identified.

Not in this task: Other modules, unrelated refactors, new dependencies, and unapproved features.

Ready-to-paste Codex prompt

You are implementing SellerOS, the SE-331 standalone social-commerce seller BI/decision-support capstone. Implement only DASH-03 — Build responsive dashboard charts and cards. Requirement: Seller needs readable sales and performance summaries. Objective/acceptance target: Dashboard visualizes the documented measures with accessible labels and period controls. Scope allowed: No fabricated data; sample data must be explicitly identified. Likely files/modules: frontend/src/features/dashboard; tests. Prerequisites: DASH-01; DASH-02; FRONTEND-03. Constraints: follow the approved React/Vite/TypeScript + Django/DRF + PostgreSQL architecture and existing API/data contracts; inspect the repository first; preserve existing working behavior; do not invent unresolved business rules—mark [DECISION REQUIRED]; do not modify unrelated files, add unnecessary dependencies, expose secrets, bypass authentication/store permissions, fabricate AI/ML results, or create autonomous actions. Out of scope for this task: Other modules, unrelated refactors, new dependencies, and unapproved features. Test requirement: Visual states work at desktop/mobile widths. Run the narrow relevant checks and report exact commands and outcomes. Expected output: focused implementation, meaningful tests, and concise notes on files changed, decisions, risks, and next dependency. Code quality: small readable changes, type/validation/error handling appropriate to the existing project, no duplicated business formulas, and no generated or sensitive data committed.

Expected Codex output: A focused change for DASH-03, relevant tests, a file-change summary, and exact commands/results. No unrelated implementation.

How to inspect: Review the diff for these boundaries: No fabricated data; sample data must be explicitly identified. Confirm only expected files changed, validation/permissions match the contract, and tests exercise the requirement.

How to understand: Explain in your own words how Recharts; responsive layout; accessible chart alternatives. support this task; trace one normal case and one failure case through the code.

Run commands: Use verified environment commands from SETUP-07. Typical checks: backend: `python manage.py check` and the focused Django test module; frontend: `npm run lint`, focused test, and `npm run build`. Run only commands applicable to changed code and report exact outcomes.

Test steps / expected result: Visual states work at desktop/mobile widths. Success means the target is present, tests pass, and failure behavior is understandable.

Common errors: If the DB is unavailable, verify PostgreSQL service, database name, credentials, and env loading. If imports/routes fail, check app registration and URL inclusion. If an API/UI mismatch appears, compare against docs/api-contract.md and correct the contract or implementation deliberately; do not patch around it.

Git milestone: After review and passing tests, commit only this task. Suggested: `git add <reviewed-files> && git commit -m "DASH-03: build responsive dashboard charts and cards"`. Use a feature branch only when it helps isolate a risky/long feature; no empty commits.

Viva questions: 1. What requirement does DASH-03 satisfy? 2. Which data/API/UI boundary does it change? 3. How is invalid or unauthorized input handled? 4. What test proves it works? 5. What limitation remains?

Definition of Done: ☐ Scope met  ☐ Code understood  ☐ Focused tests pass  ☐ No unrelated changes  ☐ Evidence recorded  ☐ Commit created  ☐ Docs updated if affected  ☐ Viva explanation ready

## DASH-04 — Verify dashboard end-to-end with synthetic records

Proposal lead / workstream assignment: Jointly assigned to Monira Islam and Rukaiya Akther Trisha — follows the proposal split; this is a planned role, not a contribution record.

Hands-on operator: Monira Islam (you) — you will carry out every task, including tasks assigned to the frontend/UI workstream.

Requirement: Displayed values must be traceable to stored records.

Target: Dashboard totals match seed-set expected values across filters.

Why this task matters: Dashboard totals match seed-set expected values across filters. It isolates one change so the student can inspect, test, and explain it before moving on.

Prerequisites: DASH-03

Concepts to understand: Traceability; integration tests; date filters.

Expected files/modules: frontend/backend integration tests; docs/test-evidence.

Implementation scope: Fix only dashboard-contract defects in this task.

Not in this task: Other modules, unrelated refactors, new dependencies, and unapproved features.

Ready-to-paste Codex prompt

You are implementing SellerOS, the SE-331 standalone social-commerce seller BI/decision-support capstone. Implement only DASH-04 — Verify dashboard end-to-end with synthetic records. Requirement: Displayed values must be traceable to stored records. Objective/acceptance target: Dashboard totals match seed-set expected values across filters. Scope allowed: Fix only dashboard-contract defects in this task. Likely files/modules: frontend/backend integration tests; docs/test-evidence. Prerequisites: DASH-03. Constraints: follow the approved React/Vite/TypeScript + Django/DRF + PostgreSQL architecture and existing API/data contracts; inspect the repository first; preserve existing working behavior; do not invent unresolved business rules—mark [DECISION REQUIRED]; do not modify unrelated files, add unnecessary dependencies, expose secrets, bypass authentication/store permissions, fabricate AI/ML results, or create autonomous actions. Out of scope for this task: Other modules, unrelated refactors, new dependencies, and unapproved features. Test requirement: Checkpoint 05 passes with recorded screenshots/test logs. Run the narrow relevant checks and report exact commands and outcomes. Expected output: focused implementation, meaningful tests, and concise notes on files changed, decisions, risks, and next dependency. Code quality: small readable changes, type/validation/error handling appropriate to the existing project, no duplicated business formulas, and no generated or sensitive data committed.

Expected Codex output: A focused change for DASH-04, relevant tests, a file-change summary, and exact commands/results. No unrelated implementation.

How to inspect: Review the diff for these boundaries: Fix only dashboard-contract defects in this task. Confirm only expected files changed, validation/permissions match the contract, and tests exercise the requirement.

How to understand: Explain in your own words how Traceability; integration tests; date filters. support this task; trace one normal case and one failure case through the code.

Run commands: Use verified environment commands from SETUP-07. Typical checks: backend: `python manage.py check` and the focused Django test module; frontend: `npm run lint`, focused test, and `npm run build`. Run only commands applicable to changed code and report exact outcomes.

Test steps / expected result: Checkpoint 05 passes with recorded screenshots/test logs. Success means the target is present, tests pass, and failure behavior is understandable.

Common errors: If the DB is unavailable, verify PostgreSQL service, database name, credentials, and env loading. If imports/routes fail, check app registration and URL inclusion. If an API/UI mismatch appears, compare against docs/api-contract.md and correct the contract or implementation deliberately; do not patch around it.

Git milestone: After review and passing tests, commit only this task. Suggested: `git add <reviewed-files> && git commit -m "DASH-04: verify dashboard end-to-end with synthetic records"`. Use a feature branch only when it helps isolate a risky/long feature; no empty commits.

Viva questions: 1. What requirement does DASH-04 satisfy? 2. Which data/API/UI boundary does it change? 3. How is invalid or unauthorized input handled? 4. What test proves it works? 5. What limitation remains?

Definition of Done: ☐ Scope met  ☐ Code understood  ☐ Focused tests pass  ☐ No unrelated changes  ☐ Evidence recorded  ☐ Commit created  ☐ Docs updated if affected  ☐ Viva explanation ready

# Phase 11 — AI Customer Assistant

Retrieve store facts, draft a reply, and leave the decision with the seller.

## ASSISTANT-01 — Specify supported assistant tasks and refusal behavior

Proposal lead / workstream assignment: Jointly assigned to Monira Islam and Rukaiya Akther Trisha — follows the proposal split; this is a planned role, not a contribution record.

Hands-on operator: Monira Islam (you) — you will carry out every task, including tasks assigned to the frontend/UI workstream.

Requirement: AI inbox must provide grounded customer-reply suggestions only.

Target: Requirements define inputs, outputs, unsupported requests, privacy, and review boundary.

Why this task matters: Requirements define inputs, outputs, unsupported requests, privacy, and review boundary. It isolates one change so the student can inspect, test, and explain it before moving on.

Prerequisites: None beyond repository inspection and the approved project baseline.

Concepts to understand: Grounded generation; refusal; human review.

Expected files/modules: docs/ai/assistant-spec.md; test cases.

Implementation scope: No live messaging integration or auto-send.

Not in this task: Other modules, unrelated refactors, new dependencies, and unapproved features.

Ready-to-paste Codex prompt

You are implementing SellerOS, the SE-331 standalone social-commerce seller BI/decision-support capstone. Implement only ASSISTANT-01 — Specify supported assistant tasks and refusal behavior. Requirement: AI inbox must provide grounded customer-reply suggestions only. Objective/acceptance target: Requirements define inputs, outputs, unsupported requests, privacy, and review boundary. Scope allowed: No live messaging integration or auto-send. Likely files/modules: docs/ai/assistant-spec.md; test cases. Prerequisites: none beyond the approved project baseline. Constraints: follow the approved React/Vite/TypeScript + Django/DRF + PostgreSQL architecture and existing API/data contracts; inspect the repository first; preserve existing working behavior; do not invent unresolved business rules—mark [DECISION REQUIRED]; do not modify unrelated files, add unnecessary dependencies, expose secrets, bypass authentication/store permissions, fabricate AI/ML results, or create autonomous actions. Out of scope for this task: Other modules, unrelated refactors, new dependencies, and unapproved features. Test requirement: Accepted case set and out-of-scope behaviors are explicit. Run the narrow relevant checks and report exact commands and outcomes. Expected output: focused implementation, meaningful tests, and concise notes on files changed, decisions, risks, and next dependency. Code quality: small readable changes, type/validation/error handling appropriate to the existing project, no duplicated business formulas, and no generated or sensitive data committed.

Expected Codex output: A focused change for ASSISTANT-01, relevant tests, a file-change summary, and exact commands/results. No unrelated implementation.

How to inspect: Review the diff for these boundaries: No live messaging integration or auto-send. Confirm only expected files changed, validation/permissions match the contract, and tests exercise the requirement.

How to understand: Explain in your own words how Grounded generation; refusal; human review. support this task; trace one normal case and one failure case through the code.

Run commands: Use verified environment commands from SETUP-07. Typical checks: backend: `python manage.py check` and the focused Django test module; frontend: `npm run lint`, focused test, and `npm run build`. Run only commands applicable to changed code and report exact outcomes.

Test steps / expected result: Accepted case set and out-of-scope behaviors are explicit. Success means the target is present, tests pass, and failure behavior is understandable.

Common errors: If the DB is unavailable, verify PostgreSQL service, database name, credentials, and env loading. If imports/routes fail, check app registration and URL inclusion. If an API/UI mismatch appears, compare against docs/api-contract.md and correct the contract or implementation deliberately; do not patch around it.

Git milestone: After review and passing tests, commit only this task. Suggested: `git add <reviewed-files> && git commit -m "ASSISTANT-01: specify supported assistant tasks and refusal behavior"`. Use a feature branch only when it helps isolate a risky/long feature; no empty commits.

Viva questions: 1. What requirement does ASSISTANT-01 satisfy? 2. Which data/API/UI boundary does it change? 3. How is invalid or unauthorized input handled? 4. What test proves it works? 5. What limitation remains?

Definition of Done: ☐ Scope met  ☐ Code understood  ☐ Focused tests pass  ☐ No unrelated changes  ☐ Evidence recorded  ☐ Commit created  ☐ Docs updated if affected  ☐ Viva explanation ready

## ASSISTANT-02 — Implement store-scoped product and stock retrieval

Proposal lead / workstream assignment: Monira Islam — follows the proposal split; this is a planned role, not a contribution record.

Hands-on operator: Monira Islam (you) — you will carry out every task, including tasks assigned to the frontend/UI workstream.

Requirement: Reply drafts need current catalogue, variant, price, and stock facts.

Target: Retrieval returns only relevant authorized store records.

Why this task matters: Retrieval returns only relevant authorized store records. It isolates one change so the student can inspect, test, and explain it before moving on.

Prerequisites: ASSISTANT-01

Concepts to understand: Search; retrieval relevance; permissions.

Expected files/modules: backend/apps/assistant/retrieval; tests.

Implementation scope: No LLM call yet; no cross-store data.

Not in this task: Other modules, unrelated refactors, new dependencies, and unapproved features.

Ready-to-paste Codex prompt

You are implementing SellerOS, the SE-331 standalone social-commerce seller BI/decision-support capstone. Implement only ASSISTANT-02 — Implement store-scoped product and stock retrieval. Requirement: Reply drafts need current catalogue, variant, price, and stock facts. Objective/acceptance target: Retrieval returns only relevant authorized store records. Scope allowed: No LLM call yet; no cross-store data. Likely files/modules: backend/apps/assistant/retrieval; tests. Prerequisites: ASSISTANT-01. Constraints: follow the approved React/Vite/TypeScript + Django/DRF + PostgreSQL architecture and existing API/data contracts; inspect the repository first; preserve existing working behavior; do not invent unresolved business rules—mark [DECISION REQUIRED]; do not modify unrelated files, add unnecessary dependencies, expose secrets, bypass authentication/store permissions, fabricate AI/ML results, or create autonomous actions. Out of scope for this task: Other modules, unrelated refactors, new dependencies, and unapproved features. Test requirement: Known questions return correct records; wrong-store context denied. Run the narrow relevant checks and report exact commands and outcomes. Expected output: focused implementation, meaningful tests, and concise notes on files changed, decisions, risks, and next dependency. Code quality: small readable changes, type/validation/error handling appropriate to the existing project, no duplicated business formulas, and no generated or sensitive data committed.

Expected Codex output: A focused change for ASSISTANT-02, relevant tests, a file-change summary, and exact commands/results. No unrelated implementation.

How to inspect: Review the diff for these boundaries: No LLM call yet; no cross-store data. Confirm only expected files changed, validation/permissions match the contract, and tests exercise the requirement.

How to understand: Explain in your own words how Search; retrieval relevance; permissions. support this task; trace one normal case and one failure case through the code.

Run commands: Use verified environment commands from SETUP-07. Typical checks: backend: `python manage.py check` and the focused Django test module; frontend: `npm run lint`, focused test, and `npm run build`. Run only commands applicable to changed code and report exact outcomes.

Test steps / expected result: Known questions return correct records; wrong-store context denied. Success means the target is present, tests pass, and failure behavior is understandable.

Common errors: If the DB is unavailable, verify PostgreSQL service, database name, credentials, and env loading. If imports/routes fail, check app registration and URL inclusion. If an API/UI mismatch appears, compare against docs/api-contract.md and correct the contract or implementation deliberately; do not patch around it.

Git milestone: After review and passing tests, commit only this task. Suggested: `git add <reviewed-files> && git commit -m "ASSISTANT-02: implement store-scoped product and stock retrieval"`. Use a feature branch only when it helps isolate a risky/long feature; no empty commits.

Viva questions: 1. What requirement does ASSISTANT-02 satisfy? 2. Which data/API/UI boundary does it change? 3. How is invalid or unauthorized input handled? 4. What test proves it works? 5. What limitation remains?

Definition of Done: ☐ Scope met  ☐ Code understood  ☐ Focused tests pass  ☐ No unrelated changes  ☐ Evidence recorded  ☐ Commit created  ☐ Docs updated if affected  ☐ Viva explanation ready

## ASSISTANT-03 — Create minimal context builder and source metadata

Proposal lead / workstream assignment: Monira Islam — follows the proposal split; this is a planned role, not a contribution record.

Hands-on operator: Monira Islam (you) — you will carry out every task, including tasks assigned to the frontend/UI workstream.

Requirement: Provider prompt must use necessary facts with traceable basis.

Target: Context builder returns compact facts and source IDs/timestamps.

Why this task matters: Context builder returns compact facts and source IDs/timestamps. It isolates one change so the student can inspect, test, and explain it before moving on.

Prerequisites: ASSISTANT-02

Concepts to understand: Context window; data minimization; provenance.

Expected files/modules: backend/apps/assistant/context; tests.

Implementation scope: Minimize customer PII; do not pass unrelated records.

Not in this task: Other modules, unrelated refactors, new dependencies, and unapproved features.

Ready-to-paste Codex prompt

You are implementing SellerOS, the SE-331 standalone social-commerce seller BI/decision-support capstone. Implement only ASSISTANT-03 — Create minimal context builder and source metadata. Requirement: Provider prompt must use necessary facts with traceable basis. Objective/acceptance target: Context builder returns compact facts and source IDs/timestamps. Scope allowed: Minimize customer PII; do not pass unrelated records. Likely files/modules: backend/apps/assistant/context; tests. Prerequisites: ASSISTANT-02. Constraints: follow the approved React/Vite/TypeScript + Django/DRF + PostgreSQL architecture and existing API/data contracts; inspect the repository first; preserve existing working behavior; do not invent unresolved business rules—mark [DECISION REQUIRED]; do not modify unrelated files, add unnecessary dependencies, expose secrets, bypass authentication/store permissions, fabricate AI/ML results, or create autonomous actions. Out of scope for this task: Other modules, unrelated refactors, new dependencies, and unapproved features. Test requirement: Tests prove included facts are relevant and scoped. Run the narrow relevant checks and report exact commands and outcomes. Expected output: focused implementation, meaningful tests, and concise notes on files changed, decisions, risks, and next dependency. Code quality: small readable changes, type/validation/error handling appropriate to the existing project, no duplicated business formulas, and no generated or sensitive data committed.

Expected Codex output: A focused change for ASSISTANT-03, relevant tests, a file-change summary, and exact commands/results. No unrelated implementation.

How to inspect: Review the diff for these boundaries: Minimize customer PII; do not pass unrelated records. Confirm only expected files changed, validation/permissions match the contract, and tests exercise the requirement.

How to understand: Explain in your own words how Context window; data minimization; provenance. support this task; trace one normal case and one failure case through the code.

Run commands: Use verified environment commands from SETUP-07. Typical checks: backend: `python manage.py check` and the focused Django test module; frontend: `npm run lint`, focused test, and `npm run build`. Run only commands applicable to changed code and report exact outcomes.

Test steps / expected result: Tests prove included facts are relevant and scoped. Success means the target is present, tests pass, and failure behavior is understandable.

Common errors: If the DB is unavailable, verify PostgreSQL service, database name, credentials, and env loading. If imports/routes fail, check app registration and URL inclusion. If an API/UI mismatch appears, compare against docs/api-contract.md and correct the contract or implementation deliberately; do not patch around it.

Git milestone: After review and passing tests, commit only this task. Suggested: `git add <reviewed-files> && git commit -m "ASSISTANT-03: create minimal context builder and source metadata"`. Use a feature branch only when it helps isolate a risky/long feature; no empty commits.

Viva questions: 1. What requirement does ASSISTANT-03 satisfy? 2. Which data/API/UI boundary does it change? 3. How is invalid or unauthorized input handled? 4. What test proves it works? 5. What limitation remains?

Definition of Done: ☐ Scope met  ☐ Code understood  ☐ Focused tests pass  ☐ No unrelated changes  ☐ Evidence recorded  ☐ Commit created  ☐ Docs updated if affected  ☐ Viva explanation ready

## ASSISTANT-04 — Implement backend-only LLM adapter and safe configuration

Proposal lead / workstream assignment: Monira Islam — follows the proposal split; this is a planned role, not a contribution record.

Hands-on operator: Monira Islam (you) — you will carry out every task, including tasks assigned to the frontend/UI workstream.

Requirement: The provider is accessed securely from the backend.

Target: Adapter isolates provider, timeouts, cost limits, and provider errors.

Why this task matters: Adapter isolates provider, timeouts, cost limits, and provider errors. It isolates one change so the student can inspect, test, and explain it before moving on.

Prerequisites: ASSISTANT-03

Concepts to understand: Secrets; adapter pattern; timeout; retries; provider terms.

Expected files/modules: backend/apps/ai/providers; settings; tests.

Implementation scope: Use provider only after PLAN-06 review; key never reaches browser.

Not in this task: Other modules, unrelated refactors, new dependencies, and unapproved features.

Ready-to-paste Codex prompt

You are implementing SellerOS, the SE-331 standalone social-commerce seller BI/decision-support capstone. Implement only ASSISTANT-04 — Implement backend-only LLM adapter and safe configuration. Requirement: The provider is accessed securely from the backend. Objective/acceptance target: Adapter isolates provider, timeouts, cost limits, and provider errors. Scope allowed: Use provider only after PLAN-06 review; key never reaches browser. Likely files/modules: backend/apps/ai/providers; settings; tests. Prerequisites: ASSISTANT-03. Constraints: follow the approved React/Vite/TypeScript + Django/DRF + PostgreSQL architecture and existing API/data contracts; inspect the repository first; preserve existing working behavior; do not invent unresolved business rules—mark [DECISION REQUIRED]; do not modify unrelated files, add unnecessary dependencies, expose secrets, bypass authentication/store permissions, fabricate AI/ML results, or create autonomous actions. Out of scope for this task: Other modules, unrelated refactors, new dependencies, and unapproved features. Test requirement: Mock tests verify failures and secret non-disclosure. Run the narrow relevant checks and report exact commands and outcomes. Expected output: focused implementation, meaningful tests, and concise notes on files changed, decisions, risks, and next dependency. Code quality: small readable changes, type/validation/error handling appropriate to the existing project, no duplicated business formulas, and no generated or sensitive data committed.

Expected Codex output: A focused change for ASSISTANT-04, relevant tests, a file-change summary, and exact commands/results. No unrelated implementation.

How to inspect: Review the diff for these boundaries: Use provider only after PLAN-06 review; key never reaches browser. Confirm only expected files changed, validation/permissions match the contract, and tests exercise the requirement.

How to understand: Explain in your own words how Secrets; adapter pattern; timeout; retries; provider terms. support this task; trace one normal case and one failure case through the code.

Run commands: Use verified environment commands from SETUP-07. Typical checks: backend: `python manage.py check` and the focused Django test module; frontend: `npm run lint`, focused test, and `npm run build`. Run only commands applicable to changed code and report exact outcomes.

Test steps / expected result: Mock tests verify failures and secret non-disclosure. Success means the target is present, tests pass, and failure behavior is understandable.

Common errors: If the DB is unavailable, verify PostgreSQL service, database name, credentials, and env loading. If imports/routes fail, check app registration and URL inclusion. If an API/UI mismatch appears, compare against docs/api-contract.md and correct the contract or implementation deliberately; do not patch around it.

Git milestone: After review and passing tests, commit only this task. Suggested: `git add <reviewed-files> && git commit -m "ASSISTANT-04: implement backend-only llm adapter and safe configuration"`. Use a feature branch only when it helps isolate a risky/long feature; no empty commits.

Viva questions: 1. What requirement does ASSISTANT-04 satisfy? 2. Which data/API/UI boundary does it change? 3. How is invalid or unauthorized input handled? 4. What test proves it works? 5. What limitation remains?

Definition of Done: ☐ Scope met  ☐ Code understood  ☐ Focused tests pass  ☐ No unrelated changes  ☐ Evidence recorded  ☐ Commit created  ☐ Docs updated if affected  ☐ Viva explanation ready

## ASSISTANT-05 — Draft reply prompt and structured output validator

Proposal lead / workstream assignment: Monira Islam — follows the proposal split; this is a planned role, not a contribution record.

Hands-on operator: Monira Islam (you) — you will carry out every task, including tasks assigned to the frontend/UI workstream.

Requirement: Generated replies must be reviewable and avoid unsupported claims.

Target: Prompt uses retrieved evidence; validator returns draft, sources, warnings, and abstention state.

Why this task matters: Prompt uses retrieved evidence; validator returns draft, sources, warnings, and abstention state. It isolates one change so the student can inspect, test, and explain it before moving on.

Prerequisites: ASSISTANT-04

Concepts to understand: Prompt injection; schema validation; grounding.

Expected files/modules: backend/apps/assistant/prompts; schemas; tests.

Implementation scope: No automatic send; ignore instructions embedded in customer text that conflict with policy.

Not in this task: Other modules, unrelated refactors, new dependencies, and unapproved features.

Ready-to-paste Codex prompt

You are implementing SellerOS, the SE-331 standalone social-commerce seller BI/decision-support capstone. Implement only ASSISTANT-05 — Draft reply prompt and structured output validator. Requirement: Generated replies must be reviewable and avoid unsupported claims. Objective/acceptance target: Prompt uses retrieved evidence; validator returns draft, sources, warnings, and abstention state. Scope allowed: No automatic send; ignore instructions embedded in customer text that conflict with policy. Likely files/modules: backend/apps/assistant/prompts; schemas; tests. Prerequisites: ASSISTANT-04. Constraints: follow the approved React/Vite/TypeScript + Django/DRF + PostgreSQL architecture and existing API/data contracts; inspect the repository first; preserve existing working behavior; do not invent unresolved business rules—mark [DECISION REQUIRED]; do not modify unrelated files, add unnecessary dependencies, expose secrets, bypass authentication/store permissions, fabricate AI/ML results, or create autonomous actions. Out of scope for this task: Other modules, unrelated refactors, new dependencies, and unapproved features. Test requirement: Unsupported fact and injection cases do not become asserted facts. Run the narrow relevant checks and report exact commands and outcomes. Expected output: focused implementation, meaningful tests, and concise notes on files changed, decisions, risks, and next dependency. Code quality: small readable changes, type/validation/error handling appropriate to the existing project, no duplicated business formulas, and no generated or sensitive data committed.

Expected Codex output: A focused change for ASSISTANT-05, relevant tests, a file-change summary, and exact commands/results. No unrelated implementation.

How to inspect: Review the diff for these boundaries: No automatic send; ignore instructions embedded in customer text that conflict with policy. Confirm only expected files changed, validation/permissions match the contract, and tests exercise the requirement.

How to understand: Explain in your own words how Prompt injection; schema validation; grounding. support this task; trace one normal case and one failure case through the code.

Run commands: Use verified environment commands from SETUP-07. Typical checks: backend: `python manage.py check` and the focused Django test module; frontend: `npm run lint`, focused test, and `npm run build`. Run only commands applicable to changed code and report exact outcomes.

Test steps / expected result: Unsupported fact and injection cases do not become asserted facts. Success means the target is present, tests pass, and failure behavior is understandable.

Common errors: If the DB is unavailable, verify PostgreSQL service, database name, credentials, and env loading. If imports/routes fail, check app registration and URL inclusion. If an API/UI mismatch appears, compare against docs/api-contract.md and correct the contract or implementation deliberately; do not patch around it.

Git milestone: After review and passing tests, commit only this task. Suggested: `git add <reviewed-files> && git commit -m "ASSISTANT-05: draft reply prompt and structured output validator"`. Use a feature branch only when it helps isolate a risky/long feature; no empty commits.

Viva questions: 1. What requirement does ASSISTANT-05 satisfy? 2. Which data/API/UI boundary does it change? 3. How is invalid or unauthorized input handled? 4. What test proves it works? 5. What limitation remains?

Definition of Done: ☐ Scope met  ☐ Code understood  ☐ Focused tests pass  ☐ No unrelated changes  ☐ Evidence recorded  ☐ Commit created  ☐ Docs updated if affected  ☐ Viva explanation ready

## ASSISTANT-06 — Implement assistant API and evaluation logging

Proposal lead / workstream assignment: Monira Islam — follows the proposal split; this is a planned role, not a contribution record.

Hands-on operator: Monira Islam (you) — you will carry out every task, including tasks assigned to the frontend/UI workstream.

Requirement: Frontend needs a safe API and evaluation evidence.

Target: Endpoint validates message size, store access, rate/time limits, and logs minimal evaluation metadata.

Why this task matters: Endpoint validates message size, store access, rate/time limits, and logs minimal evaluation metadata. It isolates one change so the student can inspect, test, and explain it before moving on.

Prerequisites: ASSISTANT-05

Concepts to understand: Rate limits; privacy; structured output.

Expected files/modules: backend/apps/assistant/api; models/logging; tests.

Implementation scope: Do not log secrets or unnecessary message PII.

Not in this task: Other modules, unrelated refactors, new dependencies, and unapproved features.

Ready-to-paste Codex prompt

You are implementing SellerOS, the SE-331 standalone social-commerce seller BI/decision-support capstone. Implement only ASSISTANT-06 — Implement assistant API and evaluation logging. Requirement: Frontend needs a safe API and evaluation evidence. Objective/acceptance target: Endpoint validates message size, store access, rate/time limits, and logs minimal evaluation metadata. Scope allowed: Do not log secrets or unnecessary message PII. Likely files/modules: backend/apps/assistant/api; models/logging; tests. Prerequisites: ASSISTANT-05. Constraints: follow the approved React/Vite/TypeScript + Django/DRF + PostgreSQL architecture and existing API/data contracts; inspect the repository first; preserve existing working behavior; do not invent unresolved business rules—mark [DECISION REQUIRED]; do not modify unrelated files, add unnecessary dependencies, expose secrets, bypass authentication/store permissions, fabricate AI/ML results, or create autonomous actions. Out of scope for this task: Other modules, unrelated refactors, new dependencies, and unapproved features. Test requirement: Auth, validation, provider failure, and privacy tests pass. Run the narrow relevant checks and report exact commands and outcomes. Expected output: focused implementation, meaningful tests, and concise notes on files changed, decisions, risks, and next dependency. Code quality: small readable changes, type/validation/error handling appropriate to the existing project, no duplicated business formulas, and no generated or sensitive data committed.

Expected Codex output: A focused change for ASSISTANT-06, relevant tests, a file-change summary, and exact commands/results. No unrelated implementation.

How to inspect: Review the diff for these boundaries: Do not log secrets or unnecessary message PII. Confirm only expected files changed, validation/permissions match the contract, and tests exercise the requirement.

How to understand: Explain in your own words how Rate limits; privacy; structured output. support this task; trace one normal case and one failure case through the code.

Run commands: Use verified environment commands from SETUP-07. Typical checks: backend: `python manage.py check` and the focused Django test module; frontend: `npm run lint`, focused test, and `npm run build`. Run only commands applicable to changed code and report exact outcomes.

Test steps / expected result: Auth, validation, provider failure, and privacy tests pass. Success means the target is present, tests pass, and failure behavior is understandable.

Common errors: If the DB is unavailable, verify PostgreSQL service, database name, credentials, and env loading. If imports/routes fail, check app registration and URL inclusion. If an API/UI mismatch appears, compare against docs/api-contract.md and correct the contract or implementation deliberately; do not patch around it.

Git milestone: After review and passing tests, commit only this task. Suggested: `git add <reviewed-files> && git commit -m "ASSISTANT-06: implement assistant api and evaluation logging"`. Use a feature branch only when it helps isolate a risky/long feature; no empty commits.

Viva questions: 1. What requirement does ASSISTANT-06 satisfy? 2. Which data/API/UI boundary does it change? 3. How is invalid or unauthorized input handled? 4. What test proves it works? 5. What limitation remains?

Definition of Done: ☐ Scope met  ☐ Code understood  ☐ Focused tests pass  ☐ No unrelated changes  ☐ Evidence recorded  ☐ Commit created  ☐ Docs updated if affected  ☐ Viva explanation ready

## ASSISTANT-07 — Build internal AI inbox and draft review UI

Proposal lead / workstream assignment: Rukaiya Akther Trisha — follows the proposal split; this is a planned role, not a contribution record.

Hands-on operator: Monira Islam (you) — you will carry out every task, including tasks assigned to the frontend/UI workstream.

Requirement: Seller must inspect and edit a suggestion before using it.

Target: Inbox accepts pasted message and shows draft, evidence, warnings, and manual copy/edit controls.

Why this task matters: Inbox accepts pasted message and shows draft, evidence, warnings, and manual copy/edit controls. It isolates one change so the student can inspect, test, and explain it before moving on.

Prerequisites: ASSISTANT-06; FRONTEND-03

Concepts to understand: Human-in-the-loop; accessible review; safe rendering.

Expected files/modules: frontend/src/features/assistant; tests.

Implementation scope: No send button or external integration.

Not in this task: Other modules, unrelated refactors, new dependencies, and unapproved features.

Ready-to-paste Codex prompt

You are implementing SellerOS, the SE-331 standalone social-commerce seller BI/decision-support capstone. Implement only ASSISTANT-07 — Build internal AI inbox and draft review UI. Requirement: Seller must inspect and edit a suggestion before using it. Objective/acceptance target: Inbox accepts pasted message and shows draft, evidence, warnings, and manual copy/edit controls. Scope allowed: No send button or external integration. Likely files/modules: frontend/src/features/assistant; tests. Prerequisites: ASSISTANT-06; FRONTEND-03. Constraints: follow the approved React/Vite/TypeScript + Django/DRF + PostgreSQL architecture and existing API/data contracts; inspect the repository first; preserve existing working behavior; do not invent unresolved business rules—mark [DECISION REQUIRED]; do not modify unrelated files, add unnecessary dependencies, expose secrets, bypass authentication/store permissions, fabricate AI/ML results, or create autonomous actions. Out of scope for this task: Other modules, unrelated refactors, new dependencies, and unapproved features. Test requirement: Draft is visibly labeled; no autonomous send path exists. Run the narrow relevant checks and report exact commands and outcomes. Expected output: focused implementation, meaningful tests, and concise notes on files changed, decisions, risks, and next dependency. Code quality: small readable changes, type/validation/error handling appropriate to the existing project, no duplicated business formulas, and no generated or sensitive data committed.

Expected Codex output: A focused change for ASSISTANT-07, relevant tests, a file-change summary, and exact commands/results. No unrelated implementation.

How to inspect: Review the diff for these boundaries: No send button or external integration. Confirm only expected files changed, validation/permissions match the contract, and tests exercise the requirement.

How to understand: Explain in your own words how Human-in-the-loop; accessible review; safe rendering. support this task; trace one normal case and one failure case through the code.

Run commands: Use verified environment commands from SETUP-07. Typical checks: backend: `python manage.py check` and the focused Django test module; frontend: `npm run lint`, focused test, and `npm run build`. Run only commands applicable to changed code and report exact outcomes.

Test steps / expected result: Draft is visibly labeled; no autonomous send path exists. Success means the target is present, tests pass, and failure behavior is understandable.

Common errors: If the DB is unavailable, verify PostgreSQL service, database name, credentials, and env loading. If imports/routes fail, check app registration and URL inclusion. If an API/UI mismatch appears, compare against docs/api-contract.md and correct the contract or implementation deliberately; do not patch around it.

Git milestone: After review and passing tests, commit only this task. Suggested: `git add <reviewed-files> && git commit -m "ASSISTANT-07: build internal ai inbox and draft review ui"`. Use a feature branch only when it helps isolate a risky/long feature; no empty commits.

Viva questions: 1. What requirement does ASSISTANT-07 satisfy? 2. Which data/API/UI boundary does it change? 3. How is invalid or unauthorized input handled? 4. What test proves it works? 5. What limitation remains?

Definition of Done: ☐ Scope met  ☐ Code understood  ☐ Focused tests pass  ☐ No unrelated changes  ☐ Evidence recorded  ☐ Commit created  ☐ Docs updated if affected  ☐ Viva explanation ready

## ASSISTANT-08 — Evaluate assistant grounding, injection, and fallback

Proposal lead / workstream assignment: Jointly assigned to Monira Islam and Rukaiya Akther Trisha — follows the proposal split; this is a planned role, not a contribution record.

Hands-on operator: Monira Islam (you) — you will carry out every task, including tasks assigned to the frontend/UI workstream.

Requirement: AI quality and safety need documented evidence.

Target: Versioned evaluation report records factual support, abstention, injection, latency, and provider failure behavior.

Why this task matters: Versioned evaluation report records factual support, abstention, injection, latency, and provider failure behavior. It isolates one change so the student can inspect, test, and explain it before moving on.

Prerequisites: ASSISTANT-07

Concepts to understand: Rubric; adversarial tests; measured latency.

Expected files/modules: tests/ai/assistant; docs/evaluation/assistant.md.

Implementation scope: Report only observed results; do not claim perfect accuracy.

Not in this task: Other modules, unrelated refactors, new dependencies, and unapproved features.

Ready-to-paste Codex prompt

You are implementing SellerOS, the SE-331 standalone social-commerce seller BI/decision-support capstone. Implement only ASSISTANT-08 — Evaluate assistant grounding, injection, and fallback. Requirement: AI quality and safety need documented evidence. Objective/acceptance target: Versioned evaluation report records factual support, abstention, injection, latency, and provider failure behavior. Scope allowed: Report only observed results; do not claim perfect accuracy. Likely files/modules: tests/ai/assistant; docs/evaluation/assistant.md. Prerequisites: ASSISTANT-07. Constraints: follow the approved React/Vite/TypeScript + Django/DRF + PostgreSQL architecture and existing API/data contracts; inspect the repository first; preserve existing working behavior; do not invent unresolved business rules—mark [DECISION REQUIRED]; do not modify unrelated files, add unnecessary dependencies, expose secrets, bypass authentication/store permissions, fabricate AI/ML results, or create autonomous actions. Out of scope for this task: Other modules, unrelated refactors, new dependencies, and unapproved features. Test requirement: Checkpoint 06 passes defined thresholds or limitations are reported. Run the narrow relevant checks and report exact commands and outcomes. Expected output: focused implementation, meaningful tests, and concise notes on files changed, decisions, risks, and next dependency. Code quality: small readable changes, type/validation/error handling appropriate to the existing project, no duplicated business formulas, and no generated or sensitive data committed.

Expected Codex output: A focused change for ASSISTANT-08, relevant tests, a file-change summary, and exact commands/results. No unrelated implementation.

How to inspect: Review the diff for these boundaries: Report only observed results; do not claim perfect accuracy. Confirm only expected files changed, validation/permissions match the contract, and tests exercise the requirement.

How to understand: Explain in your own words how Rubric; adversarial tests; measured latency. support this task; trace one normal case and one failure case through the code.

Run commands: Use verified environment commands from SETUP-07. Typical checks: backend: `python manage.py check` and the focused Django test module; frontend: `npm run lint`, focused test, and `npm run build`. Run only commands applicable to changed code and report exact outcomes.

Test steps / expected result: Checkpoint 06 passes defined thresholds or limitations are reported. Success means the target is present, tests pass, and failure behavior is understandable.

Common errors: If the DB is unavailable, verify PostgreSQL service, database name, credentials, and env loading. If imports/routes fail, check app registration and URL inclusion. If an API/UI mismatch appears, compare against docs/api-contract.md and correct the contract or implementation deliberately; do not patch around it.

Git milestone: After review and passing tests, commit only this task. Suggested: `git add <reviewed-files> && git commit -m "ASSISTANT-08: evaluate assistant grounding, injection, and fallback"`. Use a feature branch only when it helps isolate a risky/long feature; no empty commits.

Viva questions: 1. What requirement does ASSISTANT-08 satisfy? 2. Which data/API/UI boundary does it change? 3. How is invalid or unauthorized input handled? 4. What test proves it works? 5. What limitation remains?

Definition of Done: ☐ Scope met  ☐ Code understood  ☐ Focused tests pass  ☐ No unrelated changes  ☐ Evidence recorded  ☐ Commit created  ☐ Docs updated if affected  ☐ Viva explanation ready

# Phase 12 — AI Business Advisor

Calculate metrics in code, then use the LLM only to explain verified context.

## ADVISOR-01 — Define advisor metrics and insight templates

Proposal lead / workstream assignment: Jointly assigned to Monira Islam and Rukaiya Akther Trisha — follows the proposal split; this is a planned role, not a contribution record.

Hands-on operator: Monira Islam (you) — you will carry out every task, including tasks assigned to the frontend/UI workstream.

Requirement: AI summaries must refer to verified metrics and disclose limits.

Target: Supported insight types map to deterministic metrics, input periods, and evidence.

Why this task matters: Supported insight types map to deterministic metrics, input periods, and evidence. It isolates one change so the student can inspect, test, and explain it before moving on.

Prerequisites: None beyond repository inspection and the approved project baseline.

Concepts to understand: Metric provenance; explanation quality; evidence.

Expected files/modules: docs/ai/advisor-spec.md; evaluation cases.

Implementation scope: No LLM-authored numbers or unsupported recommendation claims.

Not in this task: Other modules, unrelated refactors, new dependencies, and unapproved features.

Ready-to-paste Codex prompt

You are implementing SellerOS, the SE-331 standalone social-commerce seller BI/decision-support capstone. Implement only ADVISOR-01 — Define advisor metrics and insight templates. Requirement: AI summaries must refer to verified metrics and disclose limits. Objective/acceptance target: Supported insight types map to deterministic metrics, input periods, and evidence. Scope allowed: No LLM-authored numbers or unsupported recommendation claims. Likely files/modules: docs/ai/advisor-spec.md; evaluation cases. Prerequisites: none beyond the approved project baseline. Constraints: follow the approved React/Vite/TypeScript + Django/DRF + PostgreSQL architecture and existing API/data contracts; inspect the repository first; preserve existing working behavior; do not invent unresolved business rules—mark [DECISION REQUIRED]; do not modify unrelated files, add unnecessary dependencies, expose secrets, bypass authentication/store permissions, fabricate AI/ML results, or create autonomous actions. Out of scope for this task: Other modules, unrelated refactors, new dependencies, and unapproved features. Test requirement: Every insight has a valid source metric and scope. Run the narrow relevant checks and report exact commands and outcomes. Expected output: focused implementation, meaningful tests, and concise notes on files changed, decisions, risks, and next dependency. Code quality: small readable changes, type/validation/error handling appropriate to the existing project, no duplicated business formulas, and no generated or sensitive data committed.

Expected Codex output: A focused change for ADVISOR-01, relevant tests, a file-change summary, and exact commands/results. No unrelated implementation.

How to inspect: Review the diff for these boundaries: No LLM-authored numbers or unsupported recommendation claims. Confirm only expected files changed, validation/permissions match the contract, and tests exercise the requirement.

How to understand: Explain in your own words how Metric provenance; explanation quality; evidence. support this task; trace one normal case and one failure case through the code.

Run commands: Use verified environment commands from SETUP-07. Typical checks: backend: `python manage.py check` and the focused Django test module; frontend: `npm run lint`, focused test, and `npm run build`. Run only commands applicable to changed code and report exact outcomes.

Test steps / expected result: Every insight has a valid source metric and scope. Success means the target is present, tests pass, and failure behavior is understandable.

Common errors: If the DB is unavailable, verify PostgreSQL service, database name, credentials, and env loading. If imports/routes fail, check app registration and URL inclusion. If an API/UI mismatch appears, compare against docs/api-contract.md and correct the contract or implementation deliberately; do not patch around it.

Git milestone: After review and passing tests, commit only this task. Suggested: `git add <reviewed-files> && git commit -m "ADVISOR-01: define advisor metrics and insight templates"`. Use a feature branch only when it helps isolate a risky/long feature; no empty commits.

Viva questions: 1. What requirement does ADVISOR-01 satisfy? 2. Which data/API/UI boundary does it change? 3. How is invalid or unauthorized input handled? 4. What test proves it works? 5. What limitation remains?

Definition of Done: ☐ Scope met  ☐ Code understood  ☐ Focused tests pass  ☐ No unrelated changes  ☐ Evidence recorded  ☐ Commit created  ☐ Docs updated if affected  ☐ Viva explanation ready

## ADVISOR-02 — Implement advisor context from analytics services

Proposal lead / workstream assignment: Monira Islam — follows the proposal split; this is a planned role, not a contribution record.

Hands-on operator: Monira Islam (you) — you will carry out every task, including tasks assigned to the frontend/UI workstream.

Requirement: Advisor needs a bounded, accurate summary of business records.

Target: Context builder uses existing sales/profit/stock/customer service outputs.

Why this task matters: Context builder uses existing sales/profit/stock/customer service outputs. It isolates one change so the student can inspect, test, and explain it before moving on.

Prerequisites: ADVISOR-01

Concepts to understand: Service composition; provenance; minimization.

Expected files/modules: backend/apps/advisor/context; tests.

Implementation scope: No duplicate calculations and no unnecessary customer PII.

Not in this task: Other modules, unrelated refactors, new dependencies, and unapproved features.

Ready-to-paste Codex prompt

You are implementing SellerOS, the SE-331 standalone social-commerce seller BI/decision-support capstone. Implement only ADVISOR-02 — Implement advisor context from analytics services. Requirement: Advisor needs a bounded, accurate summary of business records. Objective/acceptance target: Context builder uses existing sales/profit/stock/customer service outputs. Scope allowed: No duplicate calculations and no unnecessary customer PII. Likely files/modules: backend/apps/advisor/context; tests. Prerequisites: ADVISOR-01. Constraints: follow the approved React/Vite/TypeScript + Django/DRF + PostgreSQL architecture and existing API/data contracts; inspect the repository first; preserve existing working behavior; do not invent unresolved business rules—mark [DECISION REQUIRED]; do not modify unrelated files, add unnecessary dependencies, expose secrets, bypass authentication/store permissions, fabricate AI/ML results, or create autonomous actions. Out of scope for this task: Other modules, unrelated refactors, new dependencies, and unapproved features. Test requirement: Context values exactly match source service output. Run the narrow relevant checks and report exact commands and outcomes. Expected output: focused implementation, meaningful tests, and concise notes on files changed, decisions, risks, and next dependency. Code quality: small readable changes, type/validation/error handling appropriate to the existing project, no duplicated business formulas, and no generated or sensitive data committed.

Expected Codex output: A focused change for ADVISOR-02, relevant tests, a file-change summary, and exact commands/results. No unrelated implementation.

How to inspect: Review the diff for these boundaries: No duplicate calculations and no unnecessary customer PII. Confirm only expected files changed, validation/permissions match the contract, and tests exercise the requirement.

How to understand: Explain in your own words how Service composition; provenance; minimization. support this task; trace one normal case and one failure case through the code.

Run commands: Use verified environment commands from SETUP-07. Typical checks: backend: `python manage.py check` and the focused Django test module; frontend: `npm run lint`, focused test, and `npm run build`. Run only commands applicable to changed code and report exact outcomes.

Test steps / expected result: Context values exactly match source service output. Success means the target is present, tests pass, and failure behavior is understandable.

Common errors: If the DB is unavailable, verify PostgreSQL service, database name, credentials, and env loading. If imports/routes fail, check app registration and URL inclusion. If an API/UI mismatch appears, compare against docs/api-contract.md and correct the contract or implementation deliberately; do not patch around it.

Git milestone: After review and passing tests, commit only this task. Suggested: `git add <reviewed-files> && git commit -m "ADVISOR-02: implement advisor context from analytics services"`. Use a feature branch only when it helps isolate a risky/long feature; no empty commits.

Viva questions: 1. What requirement does ADVISOR-02 satisfy? 2. Which data/API/UI boundary does it change? 3. How is invalid or unauthorized input handled? 4. What test proves it works? 5. What limitation remains?

Definition of Done: ☐ Scope met  ☐ Code understood  ☐ Focused tests pass  ☐ No unrelated changes  ☐ Evidence recorded  ☐ Commit created  ☐ Docs updated if affected  ☐ Viva explanation ready

## ADVISOR-03 — Implement advisor generation and response validation

Proposal lead / workstream assignment: Monira Islam — follows the proposal split; this is a planned role, not a contribution record.

Hands-on operator: Monira Islam (you) — you will carry out every task, including tasks assigned to the frontend/UI workstream.

Requirement: Seller needs plain-language explanations with no fabricated business facts.

Target: Backend returns validated explanation linked to metrics, period, and warnings.

Why this task matters: Backend returns validated explanation linked to metrics, period, and warnings. It isolates one change so the student can inspect, test, and explain it before moving on.

Prerequisites: ADVISOR-02

Concepts to understand: Structured generation; grounding; safe fallback.

Expected files/modules: backend/apps/advisor/service; schemas; tests.

Implementation scope: LLM explains only; formulas remain deterministic; unsupported facts abstain.

Not in this task: Other modules, unrelated refactors, new dependencies, and unapproved features.

Ready-to-paste Codex prompt

You are implementing SellerOS, the SE-331 standalone social-commerce seller BI/decision-support capstone. Implement only ADVISOR-03 — Implement advisor generation and response validation. Requirement: Seller needs plain-language explanations with no fabricated business facts. Objective/acceptance target: Backend returns validated explanation linked to metrics, period, and warnings. Scope allowed: LLM explains only; formulas remain deterministic; unsupported facts abstain. Likely files/modules: backend/apps/advisor/service; schemas; tests. Prerequisites: ADVISOR-02. Constraints: follow the approved React/Vite/TypeScript + Django/DRF + PostgreSQL architecture and existing API/data contracts; inspect the repository first; preserve existing working behavior; do not invent unresolved business rules—mark [DECISION REQUIRED]; do not modify unrelated files, add unnecessary dependencies, expose secrets, bypass authentication/store permissions, fabricate AI/ML results, or create autonomous actions. Out of scope for this task: Other modules, unrelated refactors, new dependencies, and unapproved features. Test requirement: Cases for contradiction, missing data, and provider errors pass. Run the narrow relevant checks and report exact commands and outcomes. Expected output: focused implementation, meaningful tests, and concise notes on files changed, decisions, risks, and next dependency. Code quality: small readable changes, type/validation/error handling appropriate to the existing project, no duplicated business formulas, and no generated or sensitive data committed.

Expected Codex output: A focused change for ADVISOR-03, relevant tests, a file-change summary, and exact commands/results. No unrelated implementation.

How to inspect: Review the diff for these boundaries: LLM explains only; formulas remain deterministic; unsupported facts abstain. Confirm only expected files changed, validation/permissions match the contract, and tests exercise the requirement.

How to understand: Explain in your own words how Structured generation; grounding; safe fallback. support this task; trace one normal case and one failure case through the code.

Run commands: Use verified environment commands from SETUP-07. Typical checks: backend: `python manage.py check` and the focused Django test module; frontend: `npm run lint`, focused test, and `npm run build`. Run only commands applicable to changed code and report exact outcomes.

Test steps / expected result: Cases for contradiction, missing data, and provider errors pass. Success means the target is present, tests pass, and failure behavior is understandable.

Common errors: If the DB is unavailable, verify PostgreSQL service, database name, credentials, and env loading. If imports/routes fail, check app registration and URL inclusion. If an API/UI mismatch appears, compare against docs/api-contract.md and correct the contract or implementation deliberately; do not patch around it.

Git milestone: After review and passing tests, commit only this task. Suggested: `git add <reviewed-files> && git commit -m "ADVISOR-03: implement advisor generation and response validation"`. Use a feature branch only when it helps isolate a risky/long feature; no empty commits.

Viva questions: 1. What requirement does ADVISOR-03 satisfy? 2. Which data/API/UI boundary does it change? 3. How is invalid or unauthorized input handled? 4. What test proves it works? 5. What limitation remains?

Definition of Done: ☐ Scope met  ☐ Code understood  ☐ Focused tests pass  ☐ No unrelated changes  ☐ Evidence recorded  ☐ Commit created  ☐ Docs updated if affected  ☐ Viva explanation ready

## ADVISOR-04 — Build advisor insight UI

Proposal lead / workstream assignment: Rukaiya Akther Trisha — follows the proposal split; this is a planned role, not a contribution record.

Hands-on operator: Monira Islam (you) — you will carry out every task, including tasks assigned to the frontend/UI workstream.

Requirement: Seller needs to inspect insight basis before acting.

Target: UI presents summary, period, evidence, limitations, and refresh state.

Why this task matters: UI presents summary, period, evidence, limitations, and refresh state. It isolates one change so the student can inspect, test, and explain it before moving on.

Prerequisites: ADVISOR-03; FRONTEND-03

Concepts to understand: Evidence-based display; accessible disclosure.

Expected files/modules: frontend/src/features/advisor; tests.

Implementation scope: No action automation.

Not in this task: Other modules, unrelated refactors, new dependencies, and unapproved features.

Ready-to-paste Codex prompt

You are implementing SellerOS, the SE-331 standalone social-commerce seller BI/decision-support capstone. Implement only ADVISOR-04 — Build advisor insight UI. Requirement: Seller needs to inspect insight basis before acting. Objective/acceptance target: UI presents summary, period, evidence, limitations, and refresh state. Scope allowed: No action automation. Likely files/modules: frontend/src/features/advisor; tests. Prerequisites: ADVISOR-03; FRONTEND-03. Constraints: follow the approved React/Vite/TypeScript + Django/DRF + PostgreSQL architecture and existing API/data contracts; inspect the repository first; preserve existing working behavior; do not invent unresolved business rules—mark [DECISION REQUIRED]; do not modify unrelated files, add unnecessary dependencies, expose secrets, bypass authentication/store permissions, fabricate AI/ML results, or create autonomous actions. Out of scope for this task: Other modules, unrelated refactors, new dependencies, and unapproved features. Test requirement: Every displayed recommendation links to its basis or is withheld. Run the narrow relevant checks and report exact commands and outcomes. Expected output: focused implementation, meaningful tests, and concise notes on files changed, decisions, risks, and next dependency. Code quality: small readable changes, type/validation/error handling appropriate to the existing project, no duplicated business formulas, and no generated or sensitive data committed.

Expected Codex output: A focused change for ADVISOR-04, relevant tests, a file-change summary, and exact commands/results. No unrelated implementation.

How to inspect: Review the diff for these boundaries: No action automation. Confirm only expected files changed, validation/permissions match the contract, and tests exercise the requirement.

How to understand: Explain in your own words how Evidence-based display; accessible disclosure. support this task; trace one normal case and one failure case through the code.

Run commands: Use verified environment commands from SETUP-07. Typical checks: backend: `python manage.py check` and the focused Django test module; frontend: `npm run lint`, focused test, and `npm run build`. Run only commands applicable to changed code and report exact outcomes.

Test steps / expected result: Every displayed recommendation links to its basis or is withheld. Success means the target is present, tests pass, and failure behavior is understandable.

Common errors: If the DB is unavailable, verify PostgreSQL service, database name, credentials, and env loading. If imports/routes fail, check app registration and URL inclusion. If an API/UI mismatch appears, compare against docs/api-contract.md and correct the contract or implementation deliberately; do not patch around it.

Git milestone: After review and passing tests, commit only this task. Suggested: `git add <reviewed-files> && git commit -m "ADVISOR-04: build advisor insight ui"`. Use a feature branch only when it helps isolate a risky/long feature; no empty commits.

Viva questions: 1. What requirement does ADVISOR-04 satisfy? 2. Which data/API/UI boundary does it change? 3. How is invalid or unauthorized input handled? 4. What test proves it works? 5. What limitation remains?

Definition of Done: ☐ Scope met  ☐ Code understood  ☐ Focused tests pass  ☐ No unrelated changes  ☐ Evidence recorded  ☐ Commit created  ☐ Docs updated if affected  ☐ Viva explanation ready

## ADVISOR-05 — Evaluate advisor factuality and usefulness

Proposal lead / workstream assignment: Jointly assigned to Monira Islam and Rukaiya Akther Trisha — follows the proposal split; this is a planned role, not a contribution record.

Hands-on operator: Monira Islam (you) — you will carry out every task, including tasks assigned to the frontend/UI workstream.

Requirement: AI explanations need representative qualitative evaluation.

Target: Rubric and report assess evidence consistency, clarity, unsupported claims, and errors.

Why this task matters: Rubric and report assess evidence consistency, clarity, unsupported claims, and errors. It isolates one change so the student can inspect, test, and explain it before moving on.

Prerequisites: ADVISOR-04

Concepts to understand: Evaluation rubric; inter-rater notes if available.

Expected files/modules: tests/ai/advisor; docs/evaluation/advisor.md.

Implementation scope: Do not use unreviewed subjective ratings as proof of business impact.

Not in this task: Other modules, unrelated refactors, new dependencies, and unapproved features.

Ready-to-paste Codex prompt

You are implementing SellerOS, the SE-331 standalone social-commerce seller BI/decision-support capstone. Implement only ADVISOR-05 — Evaluate advisor factuality and usefulness. Requirement: AI explanations need representative qualitative evaluation. Objective/acceptance target: Rubric and report assess evidence consistency, clarity, unsupported claims, and errors. Scope allowed: Do not use unreviewed subjective ratings as proof of business impact. Likely files/modules: tests/ai/advisor; docs/evaluation/advisor.md. Prerequisites: ADVISOR-04. Constraints: follow the approved React/Vite/TypeScript + Django/DRF + PostgreSQL architecture and existing API/data contracts; inspect the repository first; preserve existing working behavior; do not invent unresolved business rules—mark [DECISION REQUIRED]; do not modify unrelated files, add unnecessary dependencies, expose secrets, bypass authentication/store permissions, fabricate AI/ML results, or create autonomous actions. Out of scope for this task: Other modules, unrelated refactors, new dependencies, and unapproved features. Test requirement: Observed results and limitations documented. Run the narrow relevant checks and report exact commands and outcomes. Expected output: focused implementation, meaningful tests, and concise notes on files changed, decisions, risks, and next dependency. Code quality: small readable changes, type/validation/error handling appropriate to the existing project, no duplicated business formulas, and no generated or sensitive data committed.

Expected Codex output: A focused change for ADVISOR-05, relevant tests, a file-change summary, and exact commands/results. No unrelated implementation.

How to inspect: Review the diff for these boundaries: Do not use unreviewed subjective ratings as proof of business impact. Confirm only expected files changed, validation/permissions match the contract, and tests exercise the requirement.

How to understand: Explain in your own words how Evaluation rubric; inter-rater notes if available. support this task; trace one normal case and one failure case through the code.

Run commands: Use verified environment commands from SETUP-07. Typical checks: backend: `python manage.py check` and the focused Django test module; frontend: `npm run lint`, focused test, and `npm run build`. Run only commands applicable to changed code and report exact outcomes.

Test steps / expected result: Observed results and limitations documented. Success means the target is present, tests pass, and failure behavior is understandable.

Common errors: If the DB is unavailable, verify PostgreSQL service, database name, credentials, and env loading. If imports/routes fail, check app registration and URL inclusion. If an API/UI mismatch appears, compare against docs/api-contract.md and correct the contract or implementation deliberately; do not patch around it.

Git milestone: After review and passing tests, commit only this task. Suggested: `git add <reviewed-files> && git commit -m "ADVISOR-05: evaluate advisor factuality and usefulness"`. Use a feature branch only when it helps isolate a risky/long feature; no empty commits.

Viva questions: 1. What requirement does ADVISOR-05 satisfy? 2. Which data/API/UI boundary does it change? 3. How is invalid or unauthorized input handled? 4. What test proves it works? 5. What limitation remains?

Definition of Done: ☐ Scope met  ☐ Code understood  ☐ Focused tests pass  ☐ No unrelated changes  ☐ Evidence recorded  ☐ Commit created  ☐ Docs updated if affected  ☐ Viva explanation ready

# Phase 13 — Customer segmentation

Start with explainable behavior rules; use no sensitive attributes.

## SEGMENT-01 — Define customer behavior features and segment criteria

Proposal lead / workstream assignment: Jointly assigned to Monira Islam and Rukaiya Akther Trisha — follows the proposal split; this is a planned role, not a contribution record.

Hands-on operator: Monira Islam (you) — you will carry out every task, including tasks assigned to the frontend/UI workstream.

Requirement: Proposal requires behavior-based customer groups such as new, repeat, high-value, or inactive.

Target: Rules define recency, frequency, spending basis, thresholds, period, and precedence.

Why this task matters: Rules define recency, frequency, spending basis, thresholds, period, and precedence. It isolates one change so the student can inspect, test, and explain it before moving on.

Prerequisites: None beyond repository inspection and the approved project baseline.

Concepts to understand: Feature definitions; threshold choice; bias/privacy.

Expected files/modules: docs/analytics/segments.md; test examples.

Implementation scope: Do not add clustering unless data justify it and team approves.

Not in this task: Other modules, unrelated refactors, new dependencies, and unapproved features.

Ready-to-paste Codex prompt

You are implementing SellerOS, the SE-331 standalone social-commerce seller BI/decision-support capstone. Implement only SEGMENT-01 — Define customer behavior features and segment criteria. Requirement: Proposal requires behavior-based customer groups such as new, repeat, high-value, or inactive. Objective/acceptance target: Rules define recency, frequency, spending basis, thresholds, period, and precedence. Scope allowed: Do not add clustering unless data justify it and team approves. Likely files/modules: docs/analytics/segments.md; test examples. Prerequisites: none beyond the approved project baseline. Constraints: follow the approved React/Vite/TypeScript + Django/DRF + PostgreSQL architecture and existing API/data contracts; inspect the repository first; preserve existing working behavior; do not invent unresolved business rules—mark [DECISION REQUIRED]; do not modify unrelated files, add unnecessary dependencies, expose secrets, bypass authentication/store permissions, fabricate AI/ML results, or create autonomous actions. Out of scope for this task: Other modules, unrelated refactors, new dependencies, and unapproved features. Test requirement: Each example maps to one explainable segment. Run the narrow relevant checks and report exact commands and outcomes. Expected output: focused implementation, meaningful tests, and concise notes on files changed, decisions, risks, and next dependency. Code quality: small readable changes, type/validation/error handling appropriate to the existing project, no duplicated business formulas, and no generated or sensitive data committed.

Expected Codex output: A focused change for SEGMENT-01, relevant tests, a file-change summary, and exact commands/results. No unrelated implementation.

How to inspect: Review the diff for these boundaries: Do not add clustering unless data justify it and team approves. Confirm only expected files changed, validation/permissions match the contract, and tests exercise the requirement.

How to understand: Explain in your own words how Feature definitions; threshold choice; bias/privacy. support this task; trace one normal case and one failure case through the code.

Run commands: Use verified environment commands from SETUP-07. Typical checks: backend: `python manage.py check` and the focused Django test module; frontend: `npm run lint`, focused test, and `npm run build`. Run only commands applicable to changed code and report exact outcomes.

Test steps / expected result: Each example maps to one explainable segment. Success means the target is present, tests pass, and failure behavior is understandable.

Common errors: If the DB is unavailable, verify PostgreSQL service, database name, credentials, and env loading. If imports/routes fail, check app registration and URL inclusion. If an API/UI mismatch appears, compare against docs/api-contract.md and correct the contract or implementation deliberately; do not patch around it.

Git milestone: After review and passing tests, commit only this task. Suggested: `git add <reviewed-files> && git commit -m "SEGMENT-01: define customer behavior features and segment criteria"`. Use a feature branch only when it helps isolate a risky/long feature; no empty commits.

Viva questions: 1. What requirement does SEGMENT-01 satisfy? 2. Which data/API/UI boundary does it change? 3. How is invalid or unauthorized input handled? 4. What test proves it works? 5. What limitation remains?

Definition of Done: ☐ Scope met  ☐ Code understood  ☐ Focused tests pass  ☐ No unrelated changes  ☐ Evidence recorded  ☐ Commit created  ☐ Docs updated if affected  ☐ Viva explanation ready

## SEGMENT-02 — Implement customer feature calculation service

Proposal lead / workstream assignment: Monira Islam — follows the proposal split; this is a planned role, not a contribution record.

Hands-on operator: Monira Islam (you) — you will carry out every task, including tasks assigned to the frontend/UI workstream.

Requirement: Segments require reproducible computed customer features.

Target: Service computes approved purchase-based metrics from eligible orders.

Why this task matters: Service computes approved purchase-based metrics from eligible orders. It isolates one change so the student can inspect, test, and explain it before moving on.

Prerequisites: SEGMENT-01

Concepts to understand: Aggregation; recency; frequency; monetary features.

Expected files/modules: backend/apps/segmentation/features; tests.

Implementation scope: Exclude sensitive fields; preserve store scope.

Not in this task: Other modules, unrelated refactors, new dependencies, and unapproved features.

Ready-to-paste Codex prompt

You are implementing SellerOS, the SE-331 standalone social-commerce seller BI/decision-support capstone. Implement only SEGMENT-02 — Implement customer feature calculation service. Requirement: Segments require reproducible computed customer features. Objective/acceptance target: Service computes approved purchase-based metrics from eligible orders. Scope allowed: Exclude sensitive fields; preserve store scope. Likely files/modules: backend/apps/segmentation/features; tests. Prerequisites: SEGMENT-01. Constraints: follow the approved React/Vite/TypeScript + Django/DRF + PostgreSQL architecture and existing API/data contracts; inspect the repository first; preserve existing working behavior; do not invent unresolved business rules—mark [DECISION REQUIRED]; do not modify unrelated files, add unnecessary dependencies, expose secrets, bypass authentication/store permissions, fabricate AI/ML results, or create autonomous actions. Out of scope for this task: Other modules, unrelated refactors, new dependencies, and unapproved features. Test requirement: Hand-computed cases match output. Run the narrow relevant checks and report exact commands and outcomes. Expected output: focused implementation, meaningful tests, and concise notes on files changed, decisions, risks, and next dependency. Code quality: small readable changes, type/validation/error handling appropriate to the existing project, no duplicated business formulas, and no generated or sensitive data committed.

Expected Codex output: A focused change for SEGMENT-02, relevant tests, a file-change summary, and exact commands/results. No unrelated implementation.

How to inspect: Review the diff for these boundaries: Exclude sensitive fields; preserve store scope. Confirm only expected files changed, validation/permissions match the contract, and tests exercise the requirement.

How to understand: Explain in your own words how Aggregation; recency; frequency; monetary features. support this task; trace one normal case and one failure case through the code.

Run commands: Use verified environment commands from SETUP-07. Typical checks: backend: `python manage.py check` and the focused Django test module; frontend: `npm run lint`, focused test, and `npm run build`. Run only commands applicable to changed code and report exact outcomes.

Test steps / expected result: Hand-computed cases match output. Success means the target is present, tests pass, and failure behavior is understandable.

Common errors: If the DB is unavailable, verify PostgreSQL service, database name, credentials, and env loading. If imports/routes fail, check app registration and URL inclusion. If an API/UI mismatch appears, compare against docs/api-contract.md and correct the contract or implementation deliberately; do not patch around it.

Git milestone: After review and passing tests, commit only this task. Suggested: `git add <reviewed-files> && git commit -m "SEGMENT-02: implement customer feature calculation service"`. Use a feature branch only when it helps isolate a risky/long feature; no empty commits.

Viva questions: 1. What requirement does SEGMENT-02 satisfy? 2. Which data/API/UI boundary does it change? 3. How is invalid or unauthorized input handled? 4. What test proves it works? 5. What limitation remains?

Definition of Done: ☐ Scope met  ☐ Code understood  ☐ Focused tests pass  ☐ No unrelated changes  ☐ Evidence recorded  ☐ Commit created  ☐ Docs updated if affected  ☐ Viva explanation ready

## SEGMENT-03 — Implement rule assignment and explanation API

Proposal lead / workstream assignment: Monira Islam — follows the proposal split; this is a planned role, not a contribution record.

Hands-on operator: Monira Islam (you) — you will carry out every task, including tasks assigned to the frontend/UI workstream.

Requirement: Seller needs group assignments and understandable reasons.

Target: API returns segment, rule version, values used, and explanation.

Why this task matters: API returns segment, rule version, values used, and explanation. It isolates one change so the student can inspect, test, and explain it before moving on.

Prerequisites: SEGMENT-02

Concepts to understand: Rule engine; versioning; explanation.

Expected files/modules: backend/apps/segmentation/service; API; tests.

Implementation scope: No opaque scoring or unsupported customer treatment decision.

Not in this task: Other modules, unrelated refactors, new dependencies, and unapproved features.

Ready-to-paste Codex prompt

You are implementing SellerOS, the SE-331 standalone social-commerce seller BI/decision-support capstone. Implement only SEGMENT-03 — Implement rule assignment and explanation API. Requirement: Seller needs group assignments and understandable reasons. Objective/acceptance target: API returns segment, rule version, values used, and explanation. Scope allowed: No opaque scoring or unsupported customer treatment decision. Likely files/modules: backend/apps/segmentation/service; API; tests. Prerequisites: SEGMENT-02. Constraints: follow the approved React/Vite/TypeScript + Django/DRF + PostgreSQL architecture and existing API/data contracts; inspect the repository first; preserve existing working behavior; do not invent unresolved business rules—mark [DECISION REQUIRED]; do not modify unrelated files, add unnecessary dependencies, expose secrets, bypass authentication/store permissions, fabricate AI/ML results, or create autonomous actions. Out of scope for this task: Other modules, unrelated refactors, new dependencies, and unapproved features. Test requirement: Boundary and overlap tests pass. Run the narrow relevant checks and report exact commands and outcomes. Expected output: focused implementation, meaningful tests, and concise notes on files changed, decisions, risks, and next dependency. Code quality: small readable changes, type/validation/error handling appropriate to the existing project, no duplicated business formulas, and no generated or sensitive data committed.

Expected Codex output: A focused change for SEGMENT-03, relevant tests, a file-change summary, and exact commands/results. No unrelated implementation.

How to inspect: Review the diff for these boundaries: No opaque scoring or unsupported customer treatment decision. Confirm only expected files changed, validation/permissions match the contract, and tests exercise the requirement.

How to understand: Explain in your own words how Rule engine; versioning; explanation. support this task; trace one normal case and one failure case through the code.

Run commands: Use verified environment commands from SETUP-07. Typical checks: backend: `python manage.py check` and the focused Django test module; frontend: `npm run lint`, focused test, and `npm run build`. Run only commands applicable to changed code and report exact outcomes.

Test steps / expected result: Boundary and overlap tests pass. Success means the target is present, tests pass, and failure behavior is understandable.

Common errors: If the DB is unavailable, verify PostgreSQL service, database name, credentials, and env loading. If imports/routes fail, check app registration and URL inclusion. If an API/UI mismatch appears, compare against docs/api-contract.md and correct the contract or implementation deliberately; do not patch around it.

Git milestone: After review and passing tests, commit only this task. Suggested: `git add <reviewed-files> && git commit -m "SEGMENT-03: implement rule assignment and explanation api"`. Use a feature branch only when it helps isolate a risky/long feature; no empty commits.

Viva questions: 1. What requirement does SEGMENT-03 satisfy? 2. Which data/API/UI boundary does it change? 3. How is invalid or unauthorized input handled? 4. What test proves it works? 5. What limitation remains?

Definition of Done: ☐ Scope met  ☐ Code understood  ☐ Focused tests pass  ☐ No unrelated changes  ☐ Evidence recorded  ☐ Commit created  ☐ Docs updated if affected  ☐ Viva explanation ready

## SEGMENT-04 — Build segment overview and customer list UI

Proposal lead / workstream assignment: Rukaiya Akther Trisha — follows the proposal split; this is a planned role, not a contribution record.

Hands-on operator: Monira Islam (you) — you will carry out every task, including tasks assigned to the frontend/UI workstream.

Requirement: Seller needs to inspect groups and the reason for assignment.

Target: Accessible UI filters customers by segment and shows the rule basis.

Why this task matters: Accessible UI filters customers by segment and shows the rule basis. It isolates one change so the student can inspect, test, and explain it before moving on.

Prerequisites: SEGMENT-03; FRONTEND-03

Concepts to understand: Filtering; privacy; accessible data table.

Expected files/modules: frontend/src/features/segments; tests.

Implementation scope: No automated marketing actions.

Not in this task: Other modules, unrelated refactors, new dependencies, and unapproved features.

Ready-to-paste Codex prompt

You are implementing SellerOS, the SE-331 standalone social-commerce seller BI/decision-support capstone. Implement only SEGMENT-04 — Build segment overview and customer list UI. Requirement: Seller needs to inspect groups and the reason for assignment. Objective/acceptance target: Accessible UI filters customers by segment and shows the rule basis. Scope allowed: No automated marketing actions. Likely files/modules: frontend/src/features/segments; tests. Prerequisites: SEGMENT-03; FRONTEND-03. Constraints: follow the approved React/Vite/TypeScript + Django/DRF + PostgreSQL architecture and existing API/data contracts; inspect the repository first; preserve existing working behavior; do not invent unresolved business rules—mark [DECISION REQUIRED]; do not modify unrelated files, add unnecessary dependencies, expose secrets, bypass authentication/store permissions, fabricate AI/ML results, or create autonomous actions. Out of scope for this task: Other modules, unrelated refactors, new dependencies, and unapproved features. Test requirement: UI handles no-data and threshold changes transparently. Run the narrow relevant checks and report exact commands and outcomes. Expected output: focused implementation, meaningful tests, and concise notes on files changed, decisions, risks, and next dependency. Code quality: small readable changes, type/validation/error handling appropriate to the existing project, no duplicated business formulas, and no generated or sensitive data committed.

Expected Codex output: A focused change for SEGMENT-04, relevant tests, a file-change summary, and exact commands/results. No unrelated implementation.

How to inspect: Review the diff for these boundaries: No automated marketing actions. Confirm only expected files changed, validation/permissions match the contract, and tests exercise the requirement.

How to understand: Explain in your own words how Filtering; privacy; accessible data table. support this task; trace one normal case and one failure case through the code.

Run commands: Use verified environment commands from SETUP-07. Typical checks: backend: `python manage.py check` and the focused Django test module; frontend: `npm run lint`, focused test, and `npm run build`. Run only commands applicable to changed code and report exact outcomes.

Test steps / expected result: UI handles no-data and threshold changes transparently. Success means the target is present, tests pass, and failure behavior is understandable.

Common errors: If the DB is unavailable, verify PostgreSQL service, database name, credentials, and env loading. If imports/routes fail, check app registration and URL inclusion. If an API/UI mismatch appears, compare against docs/api-contract.md and correct the contract or implementation deliberately; do not patch around it.

Git milestone: After review and passing tests, commit only this task. Suggested: `git add <reviewed-files> && git commit -m "SEGMENT-04: build segment overview and customer list ui"`. Use a feature branch only when it helps isolate a risky/long feature; no empty commits.

Viva questions: 1. What requirement does SEGMENT-04 satisfy? 2. Which data/API/UI boundary does it change? 3. How is invalid or unauthorized input handled? 4. What test proves it works? 5. What limitation remains?

Definition of Done: ☐ Scope met  ☐ Code understood  ☐ Focused tests pass  ☐ No unrelated changes  ☐ Evidence recorded  ☐ Commit created  ☐ Docs updated if affected  ☐ Viva explanation ready

## SEGMENT-05 — Validate segment edge cases and stability

Proposal lead / workstream assignment: Jointly assigned to Monira Islam and Rukaiya Akther Trisha — follows the proposal split; this is a planned role, not a contribution record.

Hands-on operator: Monira Islam (you) — you will carry out every task, including tasks assigned to the frontend/UI workstream.

Requirement: Rules must behave consistently on sparse and tied histories.

Target: Regression suite covers new, repeat, high-value, inactive, equal thresholds, and no orders.

Why this task matters: Regression suite covers new, repeat, high-value, inactive, equal thresholds, and no orders. It isolates one change so the student can inspect, test, and explain it before moving on.

Prerequisites: SEGMENT-04

Concepts to understand: Boundary conditions; rule stability.

Expected files/modules: backend/frontend tests; docs/evaluation/segments.md.

Implementation scope: Do not claim predictive customer value.

Not in this task: Other modules, unrelated refactors, new dependencies, and unapproved features.

Ready-to-paste Codex prompt

You are implementing SellerOS, the SE-331 standalone social-commerce seller BI/decision-support capstone. Implement only SEGMENT-05 — Validate segment edge cases and stability. Requirement: Rules must behave consistently on sparse and tied histories. Objective/acceptance target: Regression suite covers new, repeat, high-value, inactive, equal thresholds, and no orders. Scope allowed: Do not claim predictive customer value. Likely files/modules: backend/frontend tests; docs/evaluation/segments.md. Prerequisites: SEGMENT-04. Constraints: follow the approved React/Vite/TypeScript + Django/DRF + PostgreSQL architecture and existing API/data contracts; inspect the repository first; preserve existing working behavior; do not invent unresolved business rules—mark [DECISION REQUIRED]; do not modify unrelated files, add unnecessary dependencies, expose secrets, bypass authentication/store permissions, fabricate AI/ML results, or create autonomous actions. Out of scope for this task: Other modules, unrelated refactors, new dependencies, and unapproved features. Test requirement: All cases have expected assignment and explanation. Run the narrow relevant checks and report exact commands and outcomes. Expected output: focused implementation, meaningful tests, and concise notes on files changed, decisions, risks, and next dependency. Code quality: small readable changes, type/validation/error handling appropriate to the existing project, no duplicated business formulas, and no generated or sensitive data committed.

Expected Codex output: A focused change for SEGMENT-05, relevant tests, a file-change summary, and exact commands/results. No unrelated implementation.

How to inspect: Review the diff for these boundaries: Do not claim predictive customer value. Confirm only expected files changed, validation/permissions match the contract, and tests exercise the requirement.

How to understand: Explain in your own words how Boundary conditions; rule stability. support this task; trace one normal case and one failure case through the code.

Run commands: Use verified environment commands from SETUP-07. Typical checks: backend: `python manage.py check` and the focused Django test module; frontend: `npm run lint`, focused test, and `npm run build`. Run only commands applicable to changed code and report exact outcomes.

Test steps / expected result: All cases have expected assignment and explanation. Success means the target is present, tests pass, and failure behavior is understandable.

Common errors: If the DB is unavailable, verify PostgreSQL service, database name, credentials, and env loading. If imports/routes fail, check app registration and URL inclusion. If an API/UI mismatch appears, compare against docs/api-contract.md and correct the contract or implementation deliberately; do not patch around it.

Git milestone: After review and passing tests, commit only this task. Suggested: `git add <reviewed-files> && git commit -m "SEGMENT-05: validate segment edge cases and stability"`. Use a feature branch only when it helps isolate a risky/long feature; no empty commits.

Viva questions: 1. What requirement does SEGMENT-05 satisfy? 2. Which data/API/UI boundary does it change? 3. How is invalid or unauthorized input handled? 4. What test proves it works? 5. What limitation remains?

Definition of Done: ☐ Scope met  ☐ Code understood  ☐ Focused tests pass  ☐ No unrelated changes  ☐ Evidence recorded  ☐ Commit created  ☐ Docs updated if affected  ☐ Viva explanation ready

# Phase 14 — Demand forecasting

Audit data before choosing a model; compare candidates to a time-aware baseline.

## FORECAST-01 — Audit available historical sales data

Proposal lead / workstream assignment: Jointly assigned to Monira Islam and Rukaiya Akther Trisha — follows the proposal split; this is a planned role, not a contribution record.

Hands-on operator: Monira Islam (you) — you will carry out every task, including tasks assigned to the frontend/UI workstream.

Requirement: Forecasting is allowed only when data quality and volume support it.

Target: Audit documents date span, gaps, product coverage, duplicates, returns, and granularity.

Why this task matters: Audit documents date span, gaps, product coverage, duplicates, returns, and granularity. It isolates one change so the student can inspect, test, and explain it before moving on.

Prerequisites: None beyond repository inspection and the approved project baseline.

Concepts to understand: Time-series data quality; leakage risk.

Expected files/modules: notebooks or scripts/forecast_audit; docs/forecast-data-audit.md.

Implementation scope: Do not train a model during this task.

Not in this task: Other modules, unrelated refactors, new dependencies, and unapproved features.

Ready-to-paste Codex prompt

You are implementing SellerOS, the SE-331 standalone social-commerce seller BI/decision-support capstone. Implement only FORECAST-01 — Audit available historical sales data. Requirement: Forecasting is allowed only when data quality and volume support it. Objective/acceptance target: Audit documents date span, gaps, product coverage, duplicates, returns, and granularity. Scope allowed: Do not train a model during this task. Likely files/modules: notebooks or scripts/forecast_audit; docs/forecast-data-audit.md. Prerequisites: none beyond the approved project baseline. Constraints: follow the approved React/Vite/TypeScript + Django/DRF + PostgreSQL architecture and existing API/data contracts; inspect the repository first; preserve existing working behavior; do not invent unresolved business rules—mark [DECISION REQUIRED]; do not modify unrelated files, add unnecessary dependencies, expose secrets, bypass authentication/store permissions, fabricate AI/ML results, or create autonomous actions. Out of scope for this task: Other modules, unrelated refactors, new dependencies, and unapproved features. Test requirement: Audit is reproducible and reports limitations. Run the narrow relevant checks and report exact commands and outcomes. Expected output: focused implementation, meaningful tests, and concise notes on files changed, decisions, risks, and next dependency. Code quality: small readable changes, type/validation/error handling appropriate to the existing project, no duplicated business formulas, and no generated or sensitive data committed.

Expected Codex output: A focused change for FORECAST-01, relevant tests, a file-change summary, and exact commands/results. No unrelated implementation.

How to inspect: Review the diff for these boundaries: Do not train a model during this task. Confirm only expected files changed, validation/permissions match the contract, and tests exercise the requirement.

How to understand: Explain in your own words how Time-series data quality; leakage risk. support this task; trace one normal case and one failure case through the code.

Run commands: Use verified environment commands from SETUP-07. Typical checks: backend: `python manage.py check` and the focused Django test module; frontend: `npm run lint`, focused test, and `npm run build`. Run only commands applicable to changed code and report exact outcomes.

Test steps / expected result: Audit is reproducible and reports limitations. Success means the target is present, tests pass, and failure behavior is understandable.

Common errors: If the DB is unavailable, verify PostgreSQL service, database name, credentials, and env loading. If imports/routes fail, check app registration and URL inclusion. If an API/UI mismatch appears, compare against docs/api-contract.md and correct the contract or implementation deliberately; do not patch around it.

Git milestone: After review and passing tests, commit only this task. Suggested: `git add <reviewed-files> && git commit -m "FORECAST-01: audit available historical sales data"`. Use a feature branch only when it helps isolate a risky/long feature; no empty commits.

Viva questions: 1. What requirement does FORECAST-01 satisfy? 2. Which data/API/UI boundary does it change? 3. How is invalid or unauthorized input handled? 4. What test proves it works? 5. What limitation remains?

Definition of Done: ☐ Scope met  ☐ Code understood  ☐ Focused tests pass  ☐ No unrelated changes  ☐ Evidence recorded  ☐ Commit created  ☐ Docs updated if affected  ☐ Viva explanation ready

## FORECAST-02 — Define minimum-data and eligibility rule

Proposal lead / workstream assignment: Jointly assigned to Monira Islam and Rukaiya Akther Trisha — follows the proposal split; this is a planned role, not a contribution record.

Hands-on operator: Monira Islam (you) — you will carry out every task, including tasks assigned to the frontend/UI workstream.

Requirement: System must explain when history is insufficient.

Target: Eligibility rule specifies minimum observations and valid periods with rationale.

Why this task matters: Eligibility rule specifies minimum observations and valid periods with rationale. It isolates one change so the student can inspect, test, and explain it before moving on.

Prerequisites: FORECAST-01

Concepts to understand: Sample size; seasonality; data sufficiency.

Expected files/modules: docs/forecast-method.md; tests.

Implementation scope: Threshold remains [DECISION REQUIRED] until evidence and supervisor/team review.

Not in this task: Other modules, unrelated refactors, new dependencies, and unapproved features.

Ready-to-paste Codex prompt

You are implementing SellerOS, the SE-331 standalone social-commerce seller BI/decision-support capstone. Implement only FORECAST-02 — Define minimum-data and eligibility rule. Requirement: System must explain when history is insufficient. Objective/acceptance target: Eligibility rule specifies minimum observations and valid periods with rationale. Scope allowed: Threshold remains [DECISION REQUIRED] until evidence and supervisor/team review. Likely files/modules: docs/forecast-method.md; tests. Prerequisites: FORECAST-01. Constraints: follow the approved React/Vite/TypeScript + Django/DRF + PostgreSQL architecture and existing API/data contracts; inspect the repository first; preserve existing working behavior; do not invent unresolved business rules—mark [DECISION REQUIRED]; do not modify unrelated files, add unnecessary dependencies, expose secrets, bypass authentication/store permissions, fabricate AI/ML results, or create autonomous actions. Out of scope for this task: Other modules, unrelated refactors, new dependencies, and unapproved features. Test requirement: Insufficient-data cases are explicit. Run the narrow relevant checks and report exact commands and outcomes. Expected output: focused implementation, meaningful tests, and concise notes on files changed, decisions, risks, and next dependency. Code quality: small readable changes, type/validation/error handling appropriate to the existing project, no duplicated business formulas, and no generated or sensitive data committed.

Expected Codex output: A focused change for FORECAST-02, relevant tests, a file-change summary, and exact commands/results. No unrelated implementation.

How to inspect: Review the diff for these boundaries: Threshold remains [DECISION REQUIRED] until evidence and supervisor/team review. Confirm only expected files changed, validation/permissions match the contract, and tests exercise the requirement.

How to understand: Explain in your own words how Sample size; seasonality; data sufficiency. support this task; trace one normal case and one failure case through the code.

Run commands: Use verified environment commands from SETUP-07. Typical checks: backend: `python manage.py check` and the focused Django test module; frontend: `npm run lint`, focused test, and `npm run build`. Run only commands applicable to changed code and report exact outcomes.

Test steps / expected result: Insufficient-data cases are explicit. Success means the target is present, tests pass, and failure behavior is understandable.

Common errors: If the DB is unavailable, verify PostgreSQL service, database name, credentials, and env loading. If imports/routes fail, check app registration and URL inclusion. If an API/UI mismatch appears, compare against docs/api-contract.md and correct the contract or implementation deliberately; do not patch around it.

Git milestone: After review and passing tests, commit only this task. Suggested: `git add <reviewed-files> && git commit -m "FORECAST-02: define minimum-data and eligibility rule"`. Use a feature branch only when it helps isolate a risky/long feature; no empty commits.

Viva questions: 1. What requirement does FORECAST-02 satisfy? 2. Which data/API/UI boundary does it change? 3. How is invalid or unauthorized input handled? 4. What test proves it works? 5. What limitation remains?

Definition of Done: ☐ Scope met  ☐ Code understood  ☐ Focused tests pass  ☐ No unrelated changes  ☐ Evidence recorded  ☐ Commit created  ☐ Docs updated if affected  ☐ Viva explanation ready

## FORECAST-03 — Prepare chronological product demand dataset

Proposal lead / workstream assignment: Monira Islam — follows the proposal split; this is a planned role, not a contribution record.

Hands-on operator: Monira Islam (you) — you will carry out every task, including tasks assigned to the frontend/UI workstream.

Requirement: Model inputs must preserve time ordering and product identity.

Target: Dataset aggregation produces documented product-period series.

Why this task matters: Dataset aggregation produces documented product-period series. It isolates one change so the student can inspect, test, and explain it before moving on.

Prerequisites: FORECAST-02

Concepts to understand: Resampling; missing dates; chronology.

Expected files/modules: backend/apps/forecasting/data; tests.

Implementation scope: No random shuffle; no future information in features.

Not in this task: Other modules, unrelated refactors, new dependencies, and unapproved features.

Ready-to-paste Codex prompt

You are implementing SellerOS, the SE-331 standalone social-commerce seller BI/decision-support capstone. Implement only FORECAST-03 — Prepare chronological product demand dataset. Requirement: Model inputs must preserve time ordering and product identity. Objective/acceptance target: Dataset aggregation produces documented product-period series. Scope allowed: No random shuffle; no future information in features. Likely files/modules: backend/apps/forecasting/data; tests. Prerequisites: FORECAST-02. Constraints: follow the approved React/Vite/TypeScript + Django/DRF + PostgreSQL architecture and existing API/data contracts; inspect the repository first; preserve existing working behavior; do not invent unresolved business rules—mark [DECISION REQUIRED]; do not modify unrelated files, add unnecessary dependencies, expose secrets, bypass authentication/store permissions, fabricate AI/ML results, or create autonomous actions. Out of scope for this task: Other modules, unrelated refactors, new dependencies, and unapproved features. Test requirement: Known synthetic series yields expected values. Run the narrow relevant checks and report exact commands and outcomes. Expected output: focused implementation, meaningful tests, and concise notes on files changed, decisions, risks, and next dependency. Code quality: small readable changes, type/validation/error handling appropriate to the existing project, no duplicated business formulas, and no generated or sensitive data committed.

Expected Codex output: A focused change for FORECAST-03, relevant tests, a file-change summary, and exact commands/results. No unrelated implementation.

How to inspect: Review the diff for these boundaries: No random shuffle; no future information in features. Confirm only expected files changed, validation/permissions match the contract, and tests exercise the requirement.

How to understand: Explain in your own words how Resampling; missing dates; chronology. support this task; trace one normal case and one failure case through the code.

Run commands: Use verified environment commands from SETUP-07. Typical checks: backend: `python manage.py check` and the focused Django test module; frontend: `npm run lint`, focused test, and `npm run build`. Run only commands applicable to changed code and report exact outcomes.

Test steps / expected result: Known synthetic series yields expected values. Success means the target is present, tests pass, and failure behavior is understandable.

Common errors: If the DB is unavailable, verify PostgreSQL service, database name, credentials, and env loading. If imports/routes fail, check app registration and URL inclusion. If an API/UI mismatch appears, compare against docs/api-contract.md and correct the contract or implementation deliberately; do not patch around it.

Git milestone: After review and passing tests, commit only this task. Suggested: `git add <reviewed-files> && git commit -m "FORECAST-03: prepare chronological product demand dataset"`. Use a feature branch only when it helps isolate a risky/long feature; no empty commits.

Viva questions: 1. What requirement does FORECAST-03 satisfy? 2. Which data/API/UI boundary does it change? 3. How is invalid or unauthorized input handled? 4. What test proves it works? 5. What limitation remains?

Definition of Done: ☐ Scope met  ☐ Code understood  ☐ Focused tests pass  ☐ No unrelated changes  ☐ Evidence recorded  ☐ Commit created  ☐ Docs updated if affected  ☐ Viva explanation ready

## FORECAST-04 — Choose baseline and candidate model

Proposal lead / workstream assignment: Jointly assigned to Monira Islam and Rukaiya Akther Trisha — follows the proposal split; this is a planned role, not a contribution record.

Hands-on operator: Monira Islam (you) — you will carry out every task, including tasks assigned to the frontend/UI workstream.

Requirement: A candidate only adds value if it beats a suitable simple baseline.

Target: Method note justifies baseline and one candidate using available data.

Why this task matters: Method note justifies baseline and one candidate using available data. It isolates one change so the student can inspect, test, and explain it before moving on.

Prerequisites: FORECAST-03

Concepts to understand: Naive baseline; model selection; reproducibility.

Expected files/modules: docs/forecast-method.md; experiment config.

Implementation scope: Scikit-learn baseline first; XGBoost only if justified; no presumed benefit.

Not in this task: Other modules, unrelated refactors, new dependencies, and unapproved features.

Ready-to-paste Codex prompt

You are implementing SellerOS, the SE-331 standalone social-commerce seller BI/decision-support capstone. Implement only FORECAST-04 — Choose baseline and candidate model. Requirement: A candidate only adds value if it beats a suitable simple baseline. Objective/acceptance target: Method note justifies baseline and one candidate using available data. Scope allowed: Scikit-learn baseline first; XGBoost only if justified; no presumed benefit. Likely files/modules: docs/forecast-method.md; experiment config. Prerequisites: FORECAST-03. Constraints: follow the approved React/Vite/TypeScript + Django/DRF + PostgreSQL architecture and existing API/data contracts; inspect the repository first; preserve existing working behavior; do not invent unresolved business rules—mark [DECISION REQUIRED]; do not modify unrelated files, add unnecessary dependencies, expose secrets, bypass authentication/store permissions, fabricate AI/ML results, or create autonomous actions. Out of scope for this task: Other modules, unrelated refactors, new dependencies, and unapproved features. Test requirement: Decision is recorded before final evaluation. Run the narrow relevant checks and report exact commands and outcomes. Expected output: focused implementation, meaningful tests, and concise notes on files changed, decisions, risks, and next dependency. Code quality: small readable changes, type/validation/error handling appropriate to the existing project, no duplicated business formulas, and no generated or sensitive data committed.

Expected Codex output: A focused change for FORECAST-04, relevant tests, a file-change summary, and exact commands/results. No unrelated implementation.

How to inspect: Review the diff for these boundaries: Scikit-learn baseline first; XGBoost only if justified; no presumed benefit. Confirm only expected files changed, validation/permissions match the contract, and tests exercise the requirement.

How to understand: Explain in your own words how Naive baseline; model selection; reproducibility. support this task; trace one normal case and one failure case through the code.

Run commands: Use verified environment commands from SETUP-07. Typical checks: backend: `python manage.py check` and the focused Django test module; frontend: `npm run lint`, focused test, and `npm run build`. Run only commands applicable to changed code and report exact outcomes.

Test steps / expected result: Decision is recorded before final evaluation. Success means the target is present, tests pass, and failure behavior is understandable.

Common errors: If the DB is unavailable, verify PostgreSQL service, database name, credentials, and env loading. If imports/routes fail, check app registration and URL inclusion. If an API/UI mismatch appears, compare against docs/api-contract.md and correct the contract or implementation deliberately; do not patch around it.

Git milestone: After review and passing tests, commit only this task. Suggested: `git add <reviewed-files> && git commit -m "FORECAST-04: choose baseline and candidate model"`. Use a feature branch only when it helps isolate a risky/long feature; no empty commits.

Viva questions: 1. What requirement does FORECAST-04 satisfy? 2. Which data/API/UI boundary does it change? 3. How is invalid or unauthorized input handled? 4. What test proves it works? 5. What limitation remains?

Definition of Done: ☐ Scope met  ☐ Code understood  ☐ Focused tests pass  ☐ No unrelated changes  ☐ Evidence recorded  ☐ Commit created  ☐ Docs updated if affected  ☐ Viva explanation ready

## FORECAST-05 — Define metrics and rolling evaluation split

Proposal lead / workstream assignment: Jointly assigned to Monira Islam and Rukaiya Akther Trisha — follows the proposal split; this is a planned role, not a contribution record.

Hands-on operator: Monira Islam (you) — you will carry out every task, including tasks assigned to the frontend/UI workstream.

Requirement: Forecast claims need time-aware evidence.

Target: Evaluation protocol defines horizon, rolling or chronological split, metrics, and aggregation.

Why this task matters: Evaluation protocol defines horizon, rolling or chronological split, metrics, and aggregation. It isolates one change so the student can inspect, test, and explain it before moving on.

Prerequisites: FORECAST-04

Concepts to understand: MAE/other suitable metric; rolling origin; horizon.

Expected files/modules: docs/forecast-evaluation.md; tests.

Implementation scope: Never random train/test split for time series.

Not in this task: Other modules, unrelated refactors, new dependencies, and unapproved features.

Ready-to-paste Codex prompt

You are implementing SellerOS, the SE-331 standalone social-commerce seller BI/decision-support capstone. Implement only FORECAST-05 — Define metrics and rolling evaluation split. Requirement: Forecast claims need time-aware evidence. Objective/acceptance target: Evaluation protocol defines horizon, rolling or chronological split, metrics, and aggregation. Scope allowed: Never random train/test split for time series. Likely files/modules: docs/forecast-evaluation.md; tests. Prerequisites: FORECAST-04. Constraints: follow the approved React/Vite/TypeScript + Django/DRF + PostgreSQL architecture and existing API/data contracts; inspect the repository first; preserve existing working behavior; do not invent unresolved business rules—mark [DECISION REQUIRED]; do not modify unrelated files, add unnecessary dependencies, expose secrets, bypass authentication/store permissions, fabricate AI/ML results, or create autonomous actions. Out of scope for this task: Other modules, unrelated refactors, new dependencies, and unapproved features. Test requirement: Split prevents future leakage and is reproducible. Run the narrow relevant checks and report exact commands and outcomes. Expected output: focused implementation, meaningful tests, and concise notes on files changed, decisions, risks, and next dependency. Code quality: small readable changes, type/validation/error handling appropriate to the existing project, no duplicated business formulas, and no generated or sensitive data committed.

Expected Codex output: A focused change for FORECAST-05, relevant tests, a file-change summary, and exact commands/results. No unrelated implementation.

How to inspect: Review the diff for these boundaries: Never random train/test split for time series. Confirm only expected files changed, validation/permissions match the contract, and tests exercise the requirement.

How to understand: Explain in your own words how MAE/other suitable metric; rolling origin; horizon. support this task; trace one normal case and one failure case through the code.

Run commands: Use verified environment commands from SETUP-07. Typical checks: backend: `python manage.py check` and the focused Django test module; frontend: `npm run lint`, focused test, and `npm run build`. Run only commands applicable to changed code and report exact outcomes.

Test steps / expected result: Split prevents future leakage and is reproducible. Success means the target is present, tests pass, and failure behavior is understandable.

Common errors: If the DB is unavailable, verify PostgreSQL service, database name, credentials, and env loading. If imports/routes fail, check app registration and URL inclusion. If an API/UI mismatch appears, compare against docs/api-contract.md and correct the contract or implementation deliberately; do not patch around it.

Git milestone: After review and passing tests, commit only this task. Suggested: `git add <reviewed-files> && git commit -m "FORECAST-05: define metrics and rolling evaluation split"`. Use a feature branch only when it helps isolate a risky/long feature; no empty commits.

Viva questions: 1. What requirement does FORECAST-05 satisfy? 2. Which data/API/UI boundary does it change? 3. How is invalid or unauthorized input handled? 4. What test proves it works? 5. What limitation remains?

Definition of Done: ☐ Scope met  ☐ Code understood  ☐ Focused tests pass  ☐ No unrelated changes  ☐ Evidence recorded  ☐ Commit created  ☐ Docs updated if affected  ☐ Viva explanation ready

## FORECAST-06 — Implement training and baseline evaluation

Proposal lead / workstream assignment: Monira Islam — follows the proposal split; this is a planned role, not a contribution record.

Hands-on operator: Monira Islam (you) — you will carry out every task, including tasks assigned to the frontend/UI workstream.

Requirement: Candidate performance must be measured against baseline.

Target: Script/service evaluates baseline and approved candidate on chronological folds.

Why this task matters: Script/service evaluates baseline and approved candidate on chronological folds. It isolates one change so the student can inspect, test, and explain it before moving on.

Prerequisites: FORECAST-05

Concepts to understand: Train/validation separation; experiment tracking.

Expected files/modules: backend/apps/forecasting/experiments; results.

Implementation scope: Record seed, versions, data, metric; do not tune on final test.

Not in this task: Other modules, unrelated refactors, new dependencies, and unapproved features.

Ready-to-paste Codex prompt

You are implementing SellerOS, the SE-331 standalone social-commerce seller BI/decision-support capstone. Implement only FORECAST-06 — Implement training and baseline evaluation. Requirement: Candidate performance must be measured against baseline. Objective/acceptance target: Script/service evaluates baseline and approved candidate on chronological folds. Scope allowed: Record seed, versions, data, metric; do not tune on final test. Likely files/modules: backend/apps/forecasting/experiments; results. Prerequisites: FORECAST-05. Constraints: follow the approved React/Vite/TypeScript + Django/DRF + PostgreSQL architecture and existing API/data contracts; inspect the repository first; preserve existing working behavior; do not invent unresolved business rules—mark [DECISION REQUIRED]; do not modify unrelated files, add unnecessary dependencies, expose secrets, bypass authentication/store permissions, fabricate AI/ML results, or create autonomous actions. Out of scope for this task: Other modules, unrelated refactors, new dependencies, and unapproved features. Test requirement: Results are reproducible and include all planned folds. Run the narrow relevant checks and report exact commands and outcomes. Expected output: focused implementation, meaningful tests, and concise notes on files changed, decisions, risks, and next dependency. Code quality: small readable changes, type/validation/error handling appropriate to the existing project, no duplicated business formulas, and no generated or sensitive data committed.

Expected Codex output: A focused change for FORECAST-06, relevant tests, a file-change summary, and exact commands/results. No unrelated implementation.

How to inspect: Review the diff for these boundaries: Record seed, versions, data, metric; do not tune on final test. Confirm only expected files changed, validation/permissions match the contract, and tests exercise the requirement.

How to understand: Explain in your own words how Train/validation separation; experiment tracking. support this task; trace one normal case and one failure case through the code.

Run commands: Use verified environment commands from SETUP-07. Typical checks: backend: `python manage.py check` and the focused Django test module; frontend: `npm run lint`, focused test, and `npm run build`. Run only commands applicable to changed code and report exact outcomes.

Test steps / expected result: Results are reproducible and include all planned folds. Success means the target is present, tests pass, and failure behavior is understandable.

Common errors: If the DB is unavailable, verify PostgreSQL service, database name, credentials, and env loading. If imports/routes fail, check app registration and URL inclusion. If an API/UI mismatch appears, compare against docs/api-contract.md and correct the contract or implementation deliberately; do not patch around it.

Git milestone: After review and passing tests, commit only this task. Suggested: `git add <reviewed-files> && git commit -m "FORECAST-06: implement training and baseline evaluation"`. Use a feature branch only when it helps isolate a risky/long feature; no empty commits.

Viva questions: 1. What requirement does FORECAST-06 satisfy? 2. Which data/API/UI boundary does it change? 3. How is invalid or unauthorized input handled? 4. What test proves it works? 5. What limitation remains?

Definition of Done: ☐ Scope met  ☐ Code understood  ☐ Focused tests pass  ☐ No unrelated changes  ☐ Evidence recorded  ☐ Commit created  ☐ Docs updated if affected  ☐ Viva explanation ready

## FORECAST-07 — Run leakage and plausibility checks

Proposal lead / workstream assignment: Jointly assigned to Monira Islam and Rukaiya Akther Trisha — follows the proposal split; this is a planned role, not a contribution record.

Hands-on operator: Monira Islam (you) — you will carry out every task, including tasks assigned to the frontend/UI workstream.

Requirement: A good metric is invalid if data leakage or implausible outputs remain.

Target: Tests check future fields, negative forecasts, sparse products, and comparison against baseline.

Why this task matters: Tests check future fields, negative forecasts, sparse products, and comparison against baseline. It isolates one change so the student can inspect, test, and explain it before moving on.

Prerequisites: FORECAST-06

Concepts to understand: Leakage; residual checks; forecast bounds.

Expected files/modules: forecast tests; docs/forecast-evaluation.md.

Implementation scope: Do not claim accuracy without run evidence.

Not in this task: Other modules, unrelated refactors, new dependencies, and unapproved features.

Ready-to-paste Codex prompt

You are implementing SellerOS, the SE-331 standalone social-commerce seller BI/decision-support capstone. Implement only FORECAST-07 — Run leakage and plausibility checks. Requirement: A good metric is invalid if data leakage or implausible outputs remain. Objective/acceptance target: Tests check future fields, negative forecasts, sparse products, and comparison against baseline. Scope allowed: Do not claim accuracy without run evidence. Likely files/modules: forecast tests; docs/forecast-evaluation.md. Prerequisites: FORECAST-06. Constraints: follow the approved React/Vite/TypeScript + Django/DRF + PostgreSQL architecture and existing API/data contracts; inspect the repository first; preserve existing working behavior; do not invent unresolved business rules—mark [DECISION REQUIRED]; do not modify unrelated files, add unnecessary dependencies, expose secrets, bypass authentication/store permissions, fabricate AI/ML results, or create autonomous actions. Out of scope for this task: Other modules, unrelated refactors, new dependencies, and unapproved features. Test requirement: Issues are fixed or explicitly bounded/documented. Run the narrow relevant checks and report exact commands and outcomes. Expected output: focused implementation, meaningful tests, and concise notes on files changed, decisions, risks, and next dependency. Code quality: small readable changes, type/validation/error handling appropriate to the existing project, no duplicated business formulas, and no generated or sensitive data committed.

Expected Codex output: A focused change for FORECAST-07, relevant tests, a file-change summary, and exact commands/results. No unrelated implementation.

How to inspect: Review the diff for these boundaries: Do not claim accuracy without run evidence. Confirm only expected files changed, validation/permissions match the contract, and tests exercise the requirement.

How to understand: Explain in your own words how Leakage; residual checks; forecast bounds. support this task; trace one normal case and one failure case through the code.

Run commands: Use verified environment commands from SETUP-07. Typical checks: backend: `python manage.py check` and the focused Django test module; frontend: `npm run lint`, focused test, and `npm run build`. Run only commands applicable to changed code and report exact outcomes.

Test steps / expected result: Issues are fixed or explicitly bounded/documented. Success means the target is present, tests pass, and failure behavior is understandable.

Common errors: If the DB is unavailable, verify PostgreSQL service, database name, credentials, and env loading. If imports/routes fail, check app registration and URL inclusion. If an API/UI mismatch appears, compare against docs/api-contract.md and correct the contract or implementation deliberately; do not patch around it.

Git milestone: After review and passing tests, commit only this task. Suggested: `git add <reviewed-files> && git commit -m "FORECAST-07: run leakage and plausibility checks"`. Use a feature branch only when it helps isolate a risky/long feature; no empty commits.

Viva questions: 1. What requirement does FORECAST-07 satisfy? 2. Which data/API/UI boundary does it change? 3. How is invalid or unauthorized input handled? 4. What test proves it works? 5. What limitation remains?

Definition of Done: ☐ Scope met  ☐ Code understood  ☐ Focused tests pass  ☐ No unrelated changes  ☐ Evidence recorded  ☐ Commit created  ☐ Docs updated if affected  ☐ Viva explanation ready

## FORECAST-08 — Implement forecast service and insufficient-data response

Proposal lead / workstream assignment: Monira Islam — follows the proposal split; this is a planned role, not a contribution record.

Hands-on operator: Monira Islam (you) — you will carry out every task, including tasks assigned to the frontend/UI workstream.

Requirement: Seller needs estimates only when conditions are met.

Target: Service returns estimate, horizon, method, baseline comparison, history, and limitation state.

Why this task matters: Service returns estimate, horizon, method, baseline comparison, history, and limitation state. It isolates one change so the student can inspect, test, and explain it before moving on.

Prerequisites: FORECAST-07

Concepts to understand: Service boundary; model serialization; abstention.

Expected files/modules: backend/apps/forecasting/service; schemas; tests.

Implementation scope: No confident estimate when eligibility fails.

Not in this task: Other modules, unrelated refactors, new dependencies, and unapproved features.

Ready-to-paste Codex prompt

You are implementing SellerOS, the SE-331 standalone social-commerce seller BI/decision-support capstone. Implement only FORECAST-08 — Implement forecast service and insufficient-data response. Requirement: Seller needs estimates only when conditions are met. Objective/acceptance target: Service returns estimate, horizon, method, baseline comparison, history, and limitation state. Scope allowed: No confident estimate when eligibility fails. Likely files/modules: backend/apps/forecasting/service; schemas; tests. Prerequisites: FORECAST-07. Constraints: follow the approved React/Vite/TypeScript + Django/DRF + PostgreSQL architecture and existing API/data contracts; inspect the repository first; preserve existing working behavior; do not invent unresolved business rules—mark [DECISION REQUIRED]; do not modify unrelated files, add unnecessary dependencies, expose secrets, bypass authentication/store permissions, fabricate AI/ML results, or create autonomous actions. Out of scope for this task: Other modules, unrelated refactors, new dependencies, and unapproved features. Test requirement: Eligible and insufficient-data cases return distinct valid states. Run the narrow relevant checks and report exact commands and outcomes. Expected output: focused implementation, meaningful tests, and concise notes on files changed, decisions, risks, and next dependency. Code quality: small readable changes, type/validation/error handling appropriate to the existing project, no duplicated business formulas, and no generated or sensitive data committed.

Expected Codex output: A focused change for FORECAST-08, relevant tests, a file-change summary, and exact commands/results. No unrelated implementation.

How to inspect: Review the diff for these boundaries: No confident estimate when eligibility fails. Confirm only expected files changed, validation/permissions match the contract, and tests exercise the requirement.

How to understand: Explain in your own words how Service boundary; model serialization; abstention. support this task; trace one normal case and one failure case through the code.

Run commands: Use verified environment commands from SETUP-07. Typical checks: backend: `python manage.py check` and the focused Django test module; frontend: `npm run lint`, focused test, and `npm run build`. Run only commands applicable to changed code and report exact outcomes.

Test steps / expected result: Eligible and insufficient-data cases return distinct valid states. Success means the target is present, tests pass, and failure behavior is understandable.

Common errors: If the DB is unavailable, verify PostgreSQL service, database name, credentials, and env loading. If imports/routes fail, check app registration and URL inclusion. If an API/UI mismatch appears, compare against docs/api-contract.md and correct the contract or implementation deliberately; do not patch around it.

Git milestone: After review and passing tests, commit only this task. Suggested: `git add <reviewed-files> && git commit -m "FORECAST-08: implement forecast service and insufficient-data response"`. Use a feature branch only when it helps isolate a risky/long feature; no empty commits.

Viva questions: 1. What requirement does FORECAST-08 satisfy? 2. Which data/API/UI boundary does it change? 3. How is invalid or unauthorized input handled? 4. What test proves it works? 5. What limitation remains?

Definition of Done: ☐ Scope met  ☐ Code understood  ☐ Focused tests pass  ☐ No unrelated changes  ☐ Evidence recorded  ☐ Commit created  ☐ Docs updated if affected  ☐ Viva explanation ready

## FORECAST-09 — Implement forecast API, UI, and result disclosure

Proposal lead / workstream assignment: Rukaiya Akther Trisha — follows the proposal split; this is a planned role, not a contribution record.

Hands-on operator: Monira Islam (you) — you will carry out every task, including tasks assigned to the frontend/UI workstream.

Requirement: Seller needs understandable forecast output and limits.

Target: API/client/UI show estimate with horizon, history, method, evaluation basis, and warning.

Why this task matters: API/client/UI show estimate with horizon, history, method, evaluation basis, and warning. It isolates one change so the student can inspect, test, and explain it before moving on.

Prerequisites: FORECAST-08; FRONTEND-03

Concepts to understand: API integration; uncertainty; chart labels.

Expected files/modules: backend API; frontend/src/features/forecast; tests.

Implementation scope: Do not hide uncertainty or imply guaranteed inventory need.

Not in this task: Other modules, unrelated refactors, new dependencies, and unapproved features.

Ready-to-paste Codex prompt

You are implementing SellerOS, the SE-331 standalone social-commerce seller BI/decision-support capstone. Implement only FORECAST-09 — Implement forecast API, UI, and result disclosure. Requirement: Seller needs understandable forecast output and limits. Objective/acceptance target: API/client/UI show estimate with horizon, history, method, evaluation basis, and warning. Scope allowed: Do not hide uncertainty or imply guaranteed inventory need. Likely files/modules: backend API; frontend/src/features/forecast; tests. Prerequisites: FORECAST-08; FRONTEND-03. Constraints: follow the approved React/Vite/TypeScript + Django/DRF + PostgreSQL architecture and existing API/data contracts; inspect the repository first; preserve existing working behavior; do not invent unresolved business rules—mark [DECISION REQUIRED]; do not modify unrelated files, add unnecessary dependencies, expose secrets, bypass authentication/store permissions, fabricate AI/ML results, or create autonomous actions. Out of scope for this task: Other modules, unrelated refactors, new dependencies, and unapproved features. Test requirement: UI handles insufficient data and errors without fake chart points. Run the narrow relevant checks and report exact commands and outcomes. Expected output: focused implementation, meaningful tests, and concise notes on files changed, decisions, risks, and next dependency. Code quality: small readable changes, type/validation/error handling appropriate to the existing project, no duplicated business formulas, and no generated or sensitive data committed.

Expected Codex output: A focused change for FORECAST-09, relevant tests, a file-change summary, and exact commands/results. No unrelated implementation.

How to inspect: Review the diff for these boundaries: Do not hide uncertainty or imply guaranteed inventory need. Confirm only expected files changed, validation/permissions match the contract, and tests exercise the requirement.

How to understand: Explain in your own words how API integration; uncertainty; chart labels. support this task; trace one normal case and one failure case through the code.

Run commands: Use verified environment commands from SETUP-07. Typical checks: backend: `python manage.py check` and the focused Django test module; frontend: `npm run lint`, focused test, and `npm run build`. Run only commands applicable to changed code and report exact outcomes.

Test steps / expected result: UI handles insufficient data and errors without fake chart points. Success means the target is present, tests pass, and failure behavior is understandable.

Common errors: If the DB is unavailable, verify PostgreSQL service, database name, credentials, and env loading. If imports/routes fail, check app registration and URL inclusion. If an API/UI mismatch appears, compare against docs/api-contract.md and correct the contract or implementation deliberately; do not patch around it.

Git milestone: After review and passing tests, commit only this task. Suggested: `git add <reviewed-files> && git commit -m "FORECAST-09: implement forecast api, ui, and result disclosure"`. Use a feature branch only when it helps isolate a risky/long feature; no empty commits.

Viva questions: 1. What requirement does FORECAST-09 satisfy? 2. Which data/API/UI boundary does it change? 3. How is invalid or unauthorized input handled? 4. What test proves it works? 5. What limitation remains?

Definition of Done: ☐ Scope met  ☐ Code understood  ☐ Focused tests pass  ☐ No unrelated changes  ☐ Evidence recorded  ☐ Commit created  ☐ Docs updated if affected  ☐ Viva explanation ready

## FORECAST-10 — Document forecast limitations and tested performance

Proposal lead / workstream assignment: Jointly assigned to Monira Islam and Rukaiya Akther Trisha — follows the proposal split; this is a planned role, not a contribution record.

Hands-on operator: Monira Islam (you) — you will carry out every task, including tasks assigned to the frontend/UI workstream.

Requirement: Users and evaluators need reproducible evidence and scope.

Target: Report describes data, method, baseline, metric, environment, results, and limitations.

Why this task matters: Report describes data, method, baseline, metric, environment, results, and limitations. It isolates one change so the student can inspect, test, and explain it before moving on.

Prerequisites: FORECAST-09

Concepts to understand: Reproducibility; reporting; limitation disclosure.

Expected files/modules: docs/evaluation/forecast.md; README.

Implementation scope: Report only actually measured results; distinguish planned and observed.

Not in this task: Other modules, unrelated refactors, new dependencies, and unapproved features.

Ready-to-paste Codex prompt

You are implementing SellerOS, the SE-331 standalone social-commerce seller BI/decision-support capstone. Implement only FORECAST-10 — Document forecast limitations and tested performance. Requirement: Users and evaluators need reproducible evidence and scope. Objective/acceptance target: Report describes data, method, baseline, metric, environment, results, and limitations. Scope allowed: Report only actually measured results; distinguish planned and observed. Likely files/modules: docs/evaluation/forecast.md; README. Prerequisites: FORECAST-09. Constraints: follow the approved React/Vite/TypeScript + Django/DRF + PostgreSQL architecture and existing API/data contracts; inspect the repository first; preserve existing working behavior; do not invent unresolved business rules—mark [DECISION REQUIRED]; do not modify unrelated files, add unnecessary dependencies, expose secrets, bypass authentication/store permissions, fabricate AI/ML results, or create autonomous actions. Out of scope for this task: Other modules, unrelated refactors, new dependencies, and unapproved features. Test requirement: Checkpoint 09 passes or feature is honestly shown as insufficient-data. Run the narrow relevant checks and report exact commands and outcomes. Expected output: focused implementation, meaningful tests, and concise notes on files changed, decisions, risks, and next dependency. Code quality: small readable changes, type/validation/error handling appropriate to the existing project, no duplicated business formulas, and no generated or sensitive data committed.

Expected Codex output: A focused change for FORECAST-10, relevant tests, a file-change summary, and exact commands/results. No unrelated implementation.

How to inspect: Review the diff for these boundaries: Report only actually measured results; distinguish planned and observed. Confirm only expected files changed, validation/permissions match the contract, and tests exercise the requirement.

How to understand: Explain in your own words how Reproducibility; reporting; limitation disclosure. support this task; trace one normal case and one failure case through the code.

Run commands: Use verified environment commands from SETUP-07. Typical checks: backend: `python manage.py check` and the focused Django test module; frontend: `npm run lint`, focused test, and `npm run build`. Run only commands applicable to changed code and report exact outcomes.

Test steps / expected result: Checkpoint 09 passes or feature is honestly shown as insufficient-data. Success means the target is present, tests pass, and failure behavior is understandable.

Common errors: If the DB is unavailable, verify PostgreSQL service, database name, credentials, and env loading. If imports/routes fail, check app registration and URL inclusion. If an API/UI mismatch appears, compare against docs/api-contract.md and correct the contract or implementation deliberately; do not patch around it.

Git milestone: After review and passing tests, commit only this task. Suggested: `git add <reviewed-files> && git commit -m "FORECAST-10: document forecast limitations and tested performance"`. Use a feature branch only when it helps isolate a risky/long feature; no empty commits.

Viva questions: 1. What requirement does FORECAST-10 satisfy? 2. Which data/API/UI boundary does it change? 3. How is invalid or unauthorized input handled? 4. What test proves it works? 5. What limitation remains?

Definition of Done: ☐ Scope met  ☐ Code understood  ☐ Focused tests pass  ☐ No unrelated changes  ☐ Evidence recorded  ☐ Commit created  ☐ Docs updated if affected  ☐ Viva explanation ready

# Phase 15 — What-if business simulator

Implement a transparent deterministic estimate for selected price or discount scenarios.

## SIM-01 — Define supported scenario and assumptions

Proposal lead / workstream assignment: Jointly assigned to Monira Islam and Rukaiya Akther Trisha — follows the proposal split; this is a planned role, not a contribution record.

Hands-on operator: Monira Islam (you) — you will carry out every task, including tasks assigned to the frontend/UI workstream.

Requirement: Proposal covers selected price or discount changes, not unconstrained prediction.

Target: Scope defines supported inputs, baseline, unchanged factors, output units, and unsupported cases.

Why this task matters: Scope defines supported inputs, baseline, unchanged factors, output units, and unsupported cases. It isolates one change so the student can inspect, test, and explain it before moving on.

Prerequisites: None beyond repository inspection and the approved project baseline.

Concepts to understand: Scenario analysis; assumptions; causal limits.

Expected files/modules: docs/simulator-spec.md; example scenarios.

Implementation scope: Mark elasticity/demand response as [DECISION REQUIRED]; never imply causal certainty.

Not in this task: Other modules, unrelated refactors, new dependencies, and unapproved features.

Ready-to-paste Codex prompt

You are implementing SellerOS, the SE-331 standalone social-commerce seller BI/decision-support capstone. Implement only SIM-01 — Define supported scenario and assumptions. Requirement: Proposal covers selected price or discount changes, not unconstrained prediction. Objective/acceptance target: Scope defines supported inputs, baseline, unchanged factors, output units, and unsupported cases. Scope allowed: Mark elasticity/demand response as [DECISION REQUIRED]; never imply causal certainty. Likely files/modules: docs/simulator-spec.md; example scenarios. Prerequisites: none beyond the approved project baseline. Constraints: follow the approved React/Vite/TypeScript + Django/DRF + PostgreSQL architecture and existing API/data contracts; inspect the repository first; preserve existing working behavior; do not invent unresolved business rules—mark [DECISION REQUIRED]; do not modify unrelated files, add unnecessary dependencies, expose secrets, bypass authentication/store permissions, fabricate AI/ML results, or create autonomous actions. Out of scope for this task: Other modules, unrelated refactors, new dependencies, and unapproved features. Test requirement: Every output can be reproduced from stated inputs. Run the narrow relevant checks and report exact commands and outcomes. Expected output: focused implementation, meaningful tests, and concise notes on files changed, decisions, risks, and next dependency. Code quality: small readable changes, type/validation/error handling appropriate to the existing project, no duplicated business formulas, and no generated or sensitive data committed.

Expected Codex output: A focused change for SIM-01, relevant tests, a file-change summary, and exact commands/results. No unrelated implementation.

How to inspect: Review the diff for these boundaries: Mark elasticity/demand response as [DECISION REQUIRED]; never imply causal certainty. Confirm only expected files changed, validation/permissions match the contract, and tests exercise the requirement.

How to understand: Explain in your own words how Scenario analysis; assumptions; causal limits. support this task; trace one normal case and one failure case through the code.

Run commands: Use verified environment commands from SETUP-07. Typical checks: backend: `python manage.py check` and the focused Django test module; frontend: `npm run lint`, focused test, and `npm run build`. Run only commands applicable to changed code and report exact outcomes.

Test steps / expected result: Every output can be reproduced from stated inputs. Success means the target is present, tests pass, and failure behavior is understandable.

Common errors: If the DB is unavailable, verify PostgreSQL service, database name, credentials, and env loading. If imports/routes fail, check app registration and URL inclusion. If an API/UI mismatch appears, compare against docs/api-contract.md and correct the contract or implementation deliberately; do not patch around it.

Git milestone: After review and passing tests, commit only this task. Suggested: `git add <reviewed-files> && git commit -m "SIM-01: define supported scenario and assumptions"`. Use a feature branch only when it helps isolate a risky/long feature; no empty commits.

Viva questions: 1. What requirement does SIM-01 satisfy? 2. Which data/API/UI boundary does it change? 3. How is invalid or unauthorized input handled? 4. What test proves it works? 5. What limitation remains?

Definition of Done: ☐ Scope met  ☐ Code understood  ☐ Focused tests pass  ☐ No unrelated changes  ☐ Evidence recorded  ☐ Commit created  ☐ Docs updated if affected  ☐ Viva explanation ready

## SIM-02 — Design simulator request and response contract

Proposal lead / workstream assignment: Jointly assigned to Monira Islam and Rukaiya Akther Trisha — follows the proposal split; this is a planned role, not a contribution record.

Hands-on operator: Monira Islam (you) — you will carry out every task, including tasks assigned to the frontend/UI workstream.

Requirement: Frontend and calculation logic need a stable interface.

Target: Schema includes product/period, scenario input, baseline, estimated outputs, assumptions, and validation errors.

Why this task matters: Schema includes product/period, scenario input, baseline, estimated outputs, assumptions, and validation errors. It isolates one change so the student can inspect, test, and explain it before moving on.

Prerequisites: SIM-01

Concepts to understand: Input validation; API contract; provenance.

Expected files/modules: docs/api-contract.md; backend schema; frontend types.

Implementation scope: Only agreed scenario types.

Not in this task: Other modules, unrelated refactors, new dependencies, and unapproved features.

Ready-to-paste Codex prompt

You are implementing SellerOS, the SE-331 standalone social-commerce seller BI/decision-support capstone. Implement only SIM-02 — Design simulator request and response contract. Requirement: Frontend and calculation logic need a stable interface. Objective/acceptance target: Schema includes product/period, scenario input, baseline, estimated outputs, assumptions, and validation errors. Scope allowed: Only agreed scenario types. Likely files/modules: docs/api-contract.md; backend schema; frontend types. Prerequisites: SIM-01. Constraints: follow the approved React/Vite/TypeScript + Django/DRF + PostgreSQL architecture and existing API/data contracts; inspect the repository first; preserve existing working behavior; do not invent unresolved business rules—mark [DECISION REQUIRED]; do not modify unrelated files, add unnecessary dependencies, expose secrets, bypass authentication/store permissions, fabricate AI/ML results, or create autonomous actions. Out of scope for this task: Other modules, unrelated refactors, new dependencies, and unapproved features. Test requirement: Examples align across request and response. Run the narrow relevant checks and report exact commands and outcomes. Expected output: focused implementation, meaningful tests, and concise notes on files changed, decisions, risks, and next dependency. Code quality: small readable changes, type/validation/error handling appropriate to the existing project, no duplicated business formulas, and no generated or sensitive data committed.

Expected Codex output: A focused change for SIM-02, relevant tests, a file-change summary, and exact commands/results. No unrelated implementation.

How to inspect: Review the diff for these boundaries: Only agreed scenario types. Confirm only expected files changed, validation/permissions match the contract, and tests exercise the requirement.

How to understand: Explain in your own words how Input validation; API contract; provenance. support this task; trace one normal case and one failure case through the code.

Run commands: Use verified environment commands from SETUP-07. Typical checks: backend: `python manage.py check` and the focused Django test module; frontend: `npm run lint`, focused test, and `npm run build`. Run only commands applicable to changed code and report exact outcomes.

Test steps / expected result: Examples align across request and response. Success means the target is present, tests pass, and failure behavior is understandable.

Common errors: If the DB is unavailable, verify PostgreSQL service, database name, credentials, and env loading. If imports/routes fail, check app registration and URL inclusion. If an API/UI mismatch appears, compare against docs/api-contract.md and correct the contract or implementation deliberately; do not patch around it.

Git milestone: After review and passing tests, commit only this task. Suggested: `git add <reviewed-files> && git commit -m "SIM-02: design simulator request and response contract"`. Use a feature branch only when it helps isolate a risky/long feature; no empty commits.

Viva questions: 1. What requirement does SIM-02 satisfy? 2. Which data/API/UI boundary does it change? 3. How is invalid or unauthorized input handled? 4. What test proves it works? 5. What limitation remains?

Definition of Done: ☐ Scope met  ☐ Code understood  ☐ Focused tests pass  ☐ No unrelated changes  ☐ Evidence recorded  ☐ Commit created  ☐ Docs updated if affected  ☐ Viva explanation ready

## SIM-03 — Implement deterministic scenario calculation service

Proposal lead / workstream assignment: Monira Islam — follows the proposal split; this is a planned role, not a contribution record.

Hands-on operator: Monira Islam (you) — you will carry out every task, including tasks assigned to the frontend/UI workstream.

Requirement: Seller needs a transparent estimate from approved formula.

Target: Pure service calculates supported price/discount scenario and labels assumptions.

Why this task matters: Pure service calculates supported price/discount scenario and labels assumptions. It isolates one change so the student can inspect, test, and explain it before moving on.

Prerequisites: SIM-02

Concepts to understand: Sensitivity analysis; Decimal; deterministic calculation.

Expected files/modules: backend/apps/simulator/service; tests.

Implementation scope: Do not call LLM for arithmetic or invent demand elasticity.

Not in this task: Other modules, unrelated refactors, new dependencies, and unapproved features.

Ready-to-paste Codex prompt

You are implementing SellerOS, the SE-331 standalone social-commerce seller BI/decision-support capstone. Implement only SIM-03 — Implement deterministic scenario calculation service. Requirement: Seller needs a transparent estimate from approved formula. Objective/acceptance target: Pure service calculates supported price/discount scenario and labels assumptions. Scope allowed: Do not call LLM for arithmetic or invent demand elasticity. Likely files/modules: backend/apps/simulator/service; tests. Prerequisites: SIM-02. Constraints: follow the approved React/Vite/TypeScript + Django/DRF + PostgreSQL architecture and existing API/data contracts; inspect the repository first; preserve existing working behavior; do not invent unresolved business rules—mark [DECISION REQUIRED]; do not modify unrelated files, add unnecessary dependencies, expose secrets, bypass authentication/store permissions, fabricate AI/ML results, or create autonomous actions. Out of scope for this task: Other modules, unrelated refactors, new dependencies, and unapproved features. Test requirement: Expected values match hand calculations. Run the narrow relevant checks and report exact commands and outcomes. Expected output: focused implementation, meaningful tests, and concise notes on files changed, decisions, risks, and next dependency. Code quality: small readable changes, type/validation/error handling appropriate to the existing project, no duplicated business formulas, and no generated or sensitive data committed.

Expected Codex output: A focused change for SIM-03, relevant tests, a file-change summary, and exact commands/results. No unrelated implementation.

How to inspect: Review the diff for these boundaries: Do not call LLM for arithmetic or invent demand elasticity. Confirm only expected files changed, validation/permissions match the contract, and tests exercise the requirement.

How to understand: Explain in your own words how Sensitivity analysis; Decimal; deterministic calculation. support this task; trace one normal case and one failure case through the code.

Run commands: Use verified environment commands from SETUP-07. Typical checks: backend: `python manage.py check` and the focused Django test module; frontend: `npm run lint`, focused test, and `npm run build`. Run only commands applicable to changed code and report exact outcomes.

Test steps / expected result: Expected values match hand calculations. Success means the target is present, tests pass, and failure behavior is understandable.

Common errors: If the DB is unavailable, verify PostgreSQL service, database name, credentials, and env loading. If imports/routes fail, check app registration and URL inclusion. If an API/UI mismatch appears, compare against docs/api-contract.md and correct the contract or implementation deliberately; do not patch around it.

Git milestone: After review and passing tests, commit only this task. Suggested: `git add <reviewed-files> && git commit -m "SIM-03: implement deterministic scenario calculation service"`. Use a feature branch only when it helps isolate a risky/long feature; no empty commits.

Viva questions: 1. What requirement does SIM-03 satisfy? 2. Which data/API/UI boundary does it change? 3. How is invalid or unauthorized input handled? 4. What test proves it works? 5. What limitation remains?

Definition of Done: ☐ Scope met  ☐ Code understood  ☐ Focused tests pass  ☐ No unrelated changes  ☐ Evidence recorded  ☐ Commit created  ☐ Docs updated if affected  ☐ Viva explanation ready

## SIM-04 — Implement simulator API and edge-case validation

Proposal lead / workstream assignment: Monira Islam — follows the proposal split; this is a planned role, not a contribution record.

Hands-on operator: Monira Islam (you) — you will carry out every task, including tasks assigned to the frontend/UI workstream.

Requirement: Seller needs protected access and explicit invalid-input responses.

Target: Store-scoped endpoint validates inputs and returns estimate or limitation.

Why this task matters: Store-scoped endpoint validates inputs and returns estimate or limitation. It isolates one change so the student can inspect, test, and explain it before moving on.

Prerequisites: SIM-03

Concepts to understand: Read-only API; boundaries; validation.

Expected files/modules: backend/apps/simulator/api; tests.

Implementation scope: No record mutations, price updates, or order changes.

Not in this task: Other modules, unrelated refactors, new dependencies, and unapproved features.

Ready-to-paste Codex prompt

You are implementing SellerOS, the SE-331 standalone social-commerce seller BI/decision-support capstone. Implement only SIM-04 — Implement simulator API and edge-case validation. Requirement: Seller needs protected access and explicit invalid-input responses. Objective/acceptance target: Store-scoped endpoint validates inputs and returns estimate or limitation. Scope allowed: No record mutations, price updates, or order changes. Likely files/modules: backend/apps/simulator/api; tests. Prerequisites: SIM-03. Constraints: follow the approved React/Vite/TypeScript + Django/DRF + PostgreSQL architecture and existing API/data contracts; inspect the repository first; preserve existing working behavior; do not invent unresolved business rules—mark [DECISION REQUIRED]; do not modify unrelated files, add unnecessary dependencies, expose secrets, bypass authentication/store permissions, fabricate AI/ML results, or create autonomous actions. Out of scope for this task: Other modules, unrelated refactors, new dependencies, and unapproved features. Test requirement: Zero/negative/extreme/missing inputs tested. Run the narrow relevant checks and report exact commands and outcomes. Expected output: focused implementation, meaningful tests, and concise notes on files changed, decisions, risks, and next dependency. Code quality: small readable changes, type/validation/error handling appropriate to the existing project, no duplicated business formulas, and no generated or sensitive data committed.

Expected Codex output: A focused change for SIM-04, relevant tests, a file-change summary, and exact commands/results. No unrelated implementation.

How to inspect: Review the diff for these boundaries: No record mutations, price updates, or order changes. Confirm only expected files changed, validation/permissions match the contract, and tests exercise the requirement.

How to understand: Explain in your own words how Read-only API; boundaries; validation. support this task; trace one normal case and one failure case through the code.

Run commands: Use verified environment commands from SETUP-07. Typical checks: backend: `python manage.py check` and the focused Django test module; frontend: `npm run lint`, focused test, and `npm run build`. Run only commands applicable to changed code and report exact outcomes.

Test steps / expected result: Zero/negative/extreme/missing inputs tested. Success means the target is present, tests pass, and failure behavior is understandable.

Common errors: If the DB is unavailable, verify PostgreSQL service, database name, credentials, and env loading. If imports/routes fail, check app registration and URL inclusion. If an API/UI mismatch appears, compare against docs/api-contract.md and correct the contract or implementation deliberately; do not patch around it.

Git milestone: After review and passing tests, commit only this task. Suggested: `git add <reviewed-files> && git commit -m "SIM-04: implement simulator api and edge-case validation"`. Use a feature branch only when it helps isolate a risky/long feature; no empty commits.

Viva questions: 1. What requirement does SIM-04 satisfy? 2. Which data/API/UI boundary does it change? 3. How is invalid or unauthorized input handled? 4. What test proves it works? 5. What limitation remains?

Definition of Done: ☐ Scope met  ☐ Code understood  ☐ Focused tests pass  ☐ No unrelated changes  ☐ Evidence recorded  ☐ Commit created  ☐ Docs updated if affected  ☐ Viva explanation ready

## SIM-05 — Build simulator UI and assumption disclosure

Proposal lead / workstream assignment: Rukaiya Akther Trisha — follows the proposal split; this is a planned role, not a contribution record.

Hands-on operator: Monira Islam (you) — you will carry out every task, including tasks assigned to the frontend/UI workstream.

Requirement: Seller needs to compare a proposed scenario with a baseline.

Target: UI presents inputs, baseline, estimate, assumptions, and limitation label.

Why this task matters: UI presents inputs, baseline, estimate, assumptions, and limitation label. It isolates one change so the student can inspect, test, and explain it before moving on.

Prerequisites: SIM-04; FRONTEND-03

Concepts to understand: Controlled inputs; comparison charts; disclosures.

Expected files/modules: frontend/src/features/simulator; tests.

Implementation scope: No save/apply action that changes actual records.

Not in this task: Other modules, unrelated refactors, new dependencies, and unapproved features.

Ready-to-paste Codex prompt

You are implementing SellerOS, the SE-331 standalone social-commerce seller BI/decision-support capstone. Implement only SIM-05 — Build simulator UI and assumption disclosure. Requirement: Seller needs to compare a proposed scenario with a baseline. Objective/acceptance target: UI presents inputs, baseline, estimate, assumptions, and limitation label. Scope allowed: No save/apply action that changes actual records. Likely files/modules: frontend/src/features/simulator; tests. Prerequisites: SIM-04; FRONTEND-03. Constraints: follow the approved React/Vite/TypeScript + Django/DRF + PostgreSQL architecture and existing API/data contracts; inspect the repository first; preserve existing working behavior; do not invent unresolved business rules—mark [DECISION REQUIRED]; do not modify unrelated files, add unnecessary dependencies, expose secrets, bypass authentication/store permissions, fabricate AI/ML results, or create autonomous actions. Out of scope for this task: Other modules, unrelated refactors, new dependencies, and unapproved features. Test requirement: Estimate is visibly distinguished from actual result. Run the narrow relevant checks and report exact commands and outcomes. Expected output: focused implementation, meaningful tests, and concise notes on files changed, decisions, risks, and next dependency. Code quality: small readable changes, type/validation/error handling appropriate to the existing project, no duplicated business formulas, and no generated or sensitive data committed.

Expected Codex output: A focused change for SIM-05, relevant tests, a file-change summary, and exact commands/results. No unrelated implementation.

How to inspect: Review the diff for these boundaries: No save/apply action that changes actual records. Confirm only expected files changed, validation/permissions match the contract, and tests exercise the requirement.

How to understand: Explain in your own words how Controlled inputs; comparison charts; disclosures. support this task; trace one normal case and one failure case through the code.

Run commands: Use verified environment commands from SETUP-07. Typical checks: backend: `python manage.py check` and the focused Django test module; frontend: `npm run lint`, focused test, and `npm run build`. Run only commands applicable to changed code and report exact outcomes.

Test steps / expected result: Estimate is visibly distinguished from actual result. Success means the target is present, tests pass, and failure behavior is understandable.

Common errors: If the DB is unavailable, verify PostgreSQL service, database name, credentials, and env loading. If imports/routes fail, check app registration and URL inclusion. If an API/UI mismatch appears, compare against docs/api-contract.md and correct the contract or implementation deliberately; do not patch around it.

Git milestone: After review and passing tests, commit only this task. Suggested: `git add <reviewed-files> && git commit -m "SIM-05: build simulator ui and assumption disclosure"`. Use a feature branch only when it helps isolate a risky/long feature; no empty commits.

Viva questions: 1. What requirement does SIM-05 satisfy? 2. Which data/API/UI boundary does it change? 3. How is invalid or unauthorized input handled? 4. What test proves it works? 5. What limitation remains?

Definition of Done: ☐ Scope met  ☐ Code understood  ☐ Focused tests pass  ☐ No unrelated changes  ☐ Evidence recorded  ☐ Commit created  ☐ Docs updated if affected  ☐ Viva explanation ready

## SIM-06 — Evaluate simulator examples and boundaries

Proposal lead / workstream assignment: Jointly assigned to Monira Islam and Rukaiya Akther Trisha — follows the proposal split; this is a planned role, not a contribution record.

Hands-on operator: Monira Islam (you) — you will carry out every task, including tasks assigned to the frontend/UI workstream.

Requirement: Scenario outputs must remain interpretable and safe.

Target: Test set covers normal and boundary scenarios with independent calculations.

Why this task matters: Test set covers normal and boundary scenarios with independent calculations. It isolates one change so the student can inspect, test, and explain it before moving on.

Prerequisites: SIM-05

Concepts to understand: Sensitivity; edge cases; reproducibility.

Expected files/modules: tests/simulator; docs/evaluation/simulator.md.

Implementation scope: Do not claim predicted outcome or causal effect.

Not in this task: Other modules, unrelated refactors, new dependencies, and unapproved features.

Ready-to-paste Codex prompt

You are implementing SellerOS, the SE-331 standalone social-commerce seller BI/decision-support capstone. Implement only SIM-06 — Evaluate simulator examples and boundaries. Requirement: Scenario outputs must remain interpretable and safe. Objective/acceptance target: Test set covers normal and boundary scenarios with independent calculations. Scope allowed: Do not claim predicted outcome or causal effect. Likely files/modules: tests/simulator; docs/evaluation/simulator.md. Prerequisites: SIM-05. Constraints: follow the approved React/Vite/TypeScript + Django/DRF + PostgreSQL architecture and existing API/data contracts; inspect the repository first; preserve existing working behavior; do not invent unresolved business rules—mark [DECISION REQUIRED]; do not modify unrelated files, add unnecessary dependencies, expose secrets, bypass authentication/store permissions, fabricate AI/ML results, or create autonomous actions. Out of scope for this task: Other modules, unrelated refactors, new dependencies, and unapproved features. Test requirement: Checkpoint 10 passes all approved examples. Run the narrow relevant checks and report exact commands and outcomes. Expected output: focused implementation, meaningful tests, and concise notes on files changed, decisions, risks, and next dependency. Code quality: small readable changes, type/validation/error handling appropriate to the existing project, no duplicated business formulas, and no generated or sensitive data committed.

Expected Codex output: A focused change for SIM-06, relevant tests, a file-change summary, and exact commands/results. No unrelated implementation.

How to inspect: Review the diff for these boundaries: Do not claim predicted outcome or causal effect. Confirm only expected files changed, validation/permissions match the contract, and tests exercise the requirement.

How to understand: Explain in your own words how Sensitivity; edge cases; reproducibility. support this task; trace one normal case and one failure case through the code.

Run commands: Use verified environment commands from SETUP-07. Typical checks: backend: `python manage.py check` and the focused Django test module; frontend: `npm run lint`, focused test, and `npm run build`. Run only commands applicable to changed code and report exact outcomes.

Test steps / expected result: Checkpoint 10 passes all approved examples. Success means the target is present, tests pass, and failure behavior is understandable.

Common errors: If the DB is unavailable, verify PostgreSQL service, database name, credentials, and env loading. If imports/routes fail, check app registration and URL inclusion. If an API/UI mismatch appears, compare against docs/api-contract.md and correct the contract or implementation deliberately; do not patch around it.

Git milestone: After review and passing tests, commit only this task. Suggested: `git add <reviewed-files> && git commit -m "SIM-06: evaluate simulator examples and boundaries"`. Use a feature branch only when it helps isolate a risky/long feature; no empty commits.

Viva questions: 1. What requirement does SIM-06 satisfy? 2. Which data/API/UI boundary does it change? 3. How is invalid or unauthorized input handled? 4. What test proves it works? 5. What limitation remains?

Definition of Done: ☐ Scope met  ☐ Code understood  ☐ Focused tests pass  ☐ No unrelated changes  ☐ Evidence recorded  ☐ Commit created  ☐ Docs updated if affected  ☐ Viva explanation ready

# Phase 16 — Integration and verification

Test the full record-to-insight flow and address concrete defects.

## INTEGRATION-01 — Run cross-module contract review

Proposal lead / workstream assignment: Jointly assigned to Monira Islam and Rukaiya Akther Trisha — follows the proposal split; this is a planned role, not a contribution record.

Hands-on operator: Monira Islam (you) — you will carry out every task, including tasks assigned to the frontend/UI workstream.

Requirement: Independent features must agree on IDs, statuses, dates, and errors.

Target: Contract matrix covers product/order/inventory/customer/analytics/AI endpoints.

Why this task matters: Contract matrix covers product/order/inventory/customer/analytics/AI endpoints. It isolates one change so the student can inspect, test, and explain it before moving on.

Prerequisites: None beyond repository inspection and the approved project baseline.

Concepts to understand: Contract testing; compatibility.

Expected files/modules: docs/api-contract.md; OpenAPI or equivalent; tests.

Implementation scope: Change shared contracts only with impact review and approval.

Not in this task: Other modules, unrelated refactors, new dependencies, and unapproved features.

Ready-to-paste Codex prompt

You are implementing SellerOS, the SE-331 standalone social-commerce seller BI/decision-support capstone. Implement only INTEGRATION-01 — Run cross-module contract review. Requirement: Independent features must agree on IDs, statuses, dates, and errors. Objective/acceptance target: Contract matrix covers product/order/inventory/customer/analytics/AI endpoints. Scope allowed: Change shared contracts only with impact review and approval. Likely files/modules: docs/api-contract.md; OpenAPI or equivalent; tests. Prerequisites: none beyond the approved project baseline. Constraints: follow the approved React/Vite/TypeScript + Django/DRF + PostgreSQL architecture and existing API/data contracts; inspect the repository first; preserve existing working behavior; do not invent unresolved business rules—mark [DECISION REQUIRED]; do not modify unrelated files, add unnecessary dependencies, expose secrets, bypass authentication/store permissions, fabricate AI/ML results, or create autonomous actions. Out of scope for this task: Other modules, unrelated refactors, new dependencies, and unapproved features. Test requirement: Frontend/backend fixtures agree. Run the narrow relevant checks and report exact commands and outcomes. Expected output: focused implementation, meaningful tests, and concise notes on files changed, decisions, risks, and next dependency. Code quality: small readable changes, type/validation/error handling appropriate to the existing project, no duplicated business formulas, and no generated or sensitive data committed.

Expected Codex output: A focused change for INTEGRATION-01, relevant tests, a file-change summary, and exact commands/results. No unrelated implementation.

How to inspect: Review the diff for these boundaries: Change shared contracts only with impact review and approval. Confirm only expected files changed, validation/permissions match the contract, and tests exercise the requirement.

How to understand: Explain in your own words how Contract testing; compatibility. support this task; trace one normal case and one failure case through the code.

Run commands: Use verified environment commands from SETUP-07. Typical checks: backend: `python manage.py check` and the focused Django test module; frontend: `npm run lint`, focused test, and `npm run build`. Run only commands applicable to changed code and report exact outcomes.

Test steps / expected result: Frontend/backend fixtures agree. Success means the target is present, tests pass, and failure behavior is understandable.

Common errors: If the DB is unavailable, verify PostgreSQL service, database name, credentials, and env loading. If imports/routes fail, check app registration and URL inclusion. If an API/UI mismatch appears, compare against docs/api-contract.md and correct the contract or implementation deliberately; do not patch around it.

Git milestone: After review and passing tests, commit only this task. Suggested: `git add <reviewed-files> && git commit -m "INTEGRATION-01: run cross-module contract review"`. Use a feature branch only when it helps isolate a risky/long feature; no empty commits.

Viva questions: 1. What requirement does INTEGRATION-01 satisfy? 2. Which data/API/UI boundary does it change? 3. How is invalid or unauthorized input handled? 4. What test proves it works? 5. What limitation remains?

Definition of Done: ☐ Scope met  ☐ Code understood  ☐ Focused tests pass  ☐ No unrelated changes  ☐ Evidence recorded  ☐ Commit created  ☐ Docs updated if affected  ☐ Viva explanation ready

## INTEGRATION-02 — Verify end-to-end seller workflow

Proposal lead / workstream assignment: Jointly assigned to Monira Islam and Rukaiya Akther Trisha — follows the proposal split; this is a planned role, not a contribution record.

Hands-on operator: Monira Islam (you) — you will carry out every task, including tasks assigned to the frontend/UI workstream.

Requirement: The prototype must support an end-to-end seller use case.

Target: A seller can add product, adjust stock, add customer/order/expense, and view analysis.

Why this task matters: A seller can add product, adjust stock, add customer/order/expense, and view analysis. It isolates one change so the student can inspect, test, and explain it before moving on.

Prerequisites: INTEGRATION-01

Concepts to understand: Browser automation; transactions; traceability.

Expected files/modules: e2e tests; docs/test-evidence/workflow.

Implementation scope: Use synthetic data and documented order rules.

Not in this task: Other modules, unrelated refactors, new dependencies, and unapproved features.

Ready-to-paste Codex prompt

You are implementing SellerOS, the SE-331 standalone social-commerce seller BI/decision-support capstone. Implement only INTEGRATION-02 — Verify end-to-end seller workflow. Requirement: The prototype must support an end-to-end seller use case. Objective/acceptance target: A seller can add product, adjust stock, add customer/order/expense, and view analysis. Scope allowed: Use synthetic data and documented order rules. Likely files/modules: e2e tests; docs/test-evidence/workflow. Prerequisites: INTEGRATION-01. Constraints: follow the approved React/Vite/TypeScript + Django/DRF + PostgreSQL architecture and existing API/data contracts; inspect the repository first; preserve existing working behavior; do not invent unresolved business rules—mark [DECISION REQUIRED]; do not modify unrelated files, add unnecessary dependencies, expose secrets, bypass authentication/store permissions, fabricate AI/ML results, or create autonomous actions. Out of scope for this task: Other modules, unrelated refactors, new dependencies, and unapproved features. Test requirement: Checkpoint 11 passes with evidence. Run the narrow relevant checks and report exact commands and outcomes. Expected output: focused implementation, meaningful tests, and concise notes on files changed, decisions, risks, and next dependency. Code quality: small readable changes, type/validation/error handling appropriate to the existing project, no duplicated business formulas, and no generated or sensitive data committed.

Expected Codex output: A focused change for INTEGRATION-02, relevant tests, a file-change summary, and exact commands/results. No unrelated implementation.

How to inspect: Review the diff for these boundaries: Use synthetic data and documented order rules. Confirm only expected files changed, validation/permissions match the contract, and tests exercise the requirement.

How to understand: Explain in your own words how Browser automation; transactions; traceability. support this task; trace one normal case and one failure case through the code.

Run commands: Use verified environment commands from SETUP-07. Typical checks: backend: `python manage.py check` and the focused Django test module; frontend: `npm run lint`, focused test, and `npm run build`. Run only commands applicable to changed code and report exact outcomes.

Test steps / expected result: Checkpoint 11 passes with evidence. Success means the target is present, tests pass, and failure behavior is understandable.

Common errors: If the DB is unavailable, verify PostgreSQL service, database name, credentials, and env loading. If imports/routes fail, check app registration and URL inclusion. If an API/UI mismatch appears, compare against docs/api-contract.md and correct the contract or implementation deliberately; do not patch around it.

Git milestone: After review and passing tests, commit only this task. Suggested: `git add <reviewed-files> && git commit -m "INTEGRATION-02: verify end-to-end seller workflow"`. Use a feature branch only when it helps isolate a risky/long feature; no empty commits.

Viva questions: 1. What requirement does INTEGRATION-02 satisfy? 2. Which data/API/UI boundary does it change? 3. How is invalid or unauthorized input handled? 4. What test proves it works? 5. What limitation remains?

Definition of Done: ☐ Scope met  ☐ Code understood  ☐ Focused tests pass  ☐ No unrelated changes  ☐ Evidence recorded  ☐ Commit created  ☐ Docs updated if affected  ☐ Viva explanation ready

## INTEGRATION-03 — Verify AI workflow against operational data

Proposal lead / workstream assignment: Jointly assigned to Monira Islam and Rukaiya Akther Trisha — follows the proposal split; this is a planned role, not a contribution record.

Hands-on operator: Monira Islam (you) — you will carry out every task, including tasks assigned to the frontend/UI workstream.

Requirement: AI features should use current authorized records.

Target: Assistant/advisor/segment/forecast/simulator outputs trace to current store data and documented rules.

Why this task matters: Assistant/advisor/segment/forecast/simulator outputs trace to current store data and documented rules. It isolates one change so the student can inspect, test, and explain it before moving on.

Prerequisites: INTEGRATION-02

Concepts to understand: Data lineage; cache invalidation; permissions.

Expected files/modules: integration tests; docs/ai-evidence.

Implementation scope: No auto action; verify stale-data behavior.

Not in this task: Other modules, unrelated refactors, new dependencies, and unapproved features.

Ready-to-paste Codex prompt

You are implementing SellerOS, the SE-331 standalone social-commerce seller BI/decision-support capstone. Implement only INTEGRATION-03 — Verify AI workflow against operational data. Requirement: AI features should use current authorized records. Objective/acceptance target: Assistant/advisor/segment/forecast/simulator outputs trace to current store data and documented rules. Scope allowed: No auto action; verify stale-data behavior. Likely files/modules: integration tests; docs/ai-evidence. Prerequisites: INTEGRATION-02. Constraints: follow the approved React/Vite/TypeScript + Django/DRF + PostgreSQL architecture and existing API/data contracts; inspect the repository first; preserve existing working behavior; do not invent unresolved business rules—mark [DECISION REQUIRED]; do not modify unrelated files, add unnecessary dependencies, expose secrets, bypass authentication/store permissions, fabricate AI/ML results, or create autonomous actions. Out of scope for this task: Other modules, unrelated refactors, new dependencies, and unapproved features. Test requirement: No unsupported output and no cross-store context leakage. Run the narrow relevant checks and report exact commands and outcomes. Expected output: focused implementation, meaningful tests, and concise notes on files changed, decisions, risks, and next dependency. Code quality: small readable changes, type/validation/error handling appropriate to the existing project, no duplicated business formulas, and no generated or sensitive data committed.

Expected Codex output: A focused change for INTEGRATION-03, relevant tests, a file-change summary, and exact commands/results. No unrelated implementation.

How to inspect: Review the diff for these boundaries: No auto action; verify stale-data behavior. Confirm only expected files changed, validation/permissions match the contract, and tests exercise the requirement.

How to understand: Explain in your own words how Data lineage; cache invalidation; permissions. support this task; trace one normal case and one failure case through the code.

Run commands: Use verified environment commands from SETUP-07. Typical checks: backend: `python manage.py check` and the focused Django test module; frontend: `npm run lint`, focused test, and `npm run build`. Run only commands applicable to changed code and report exact outcomes.

Test steps / expected result: No unsupported output and no cross-store context leakage. Success means the target is present, tests pass, and failure behavior is understandable.

Common errors: If the DB is unavailable, verify PostgreSQL service, database name, credentials, and env loading. If imports/routes fail, check app registration and URL inclusion. If an API/UI mismatch appears, compare against docs/api-contract.md and correct the contract or implementation deliberately; do not patch around it.

Git milestone: After review and passing tests, commit only this task. Suggested: `git add <reviewed-files> && git commit -m "INTEGRATION-03: verify ai workflow against operational data"`. Use a feature branch only when it helps isolate a risky/long feature; no empty commits.

Viva questions: 1. What requirement does INTEGRATION-03 satisfy? 2. Which data/API/UI boundary does it change? 3. How is invalid or unauthorized input handled? 4. What test proves it works? 5. What limitation remains?

Definition of Done: ☐ Scope met  ☐ Code understood  ☐ Focused tests pass  ☐ No unrelated changes  ☐ Evidence recorded  ☐ Commit created  ☐ Docs updated if affected  ☐ Viva explanation ready

## INTEGRATION-04 — Triage and fix verified integration defects

Proposal lead / workstream assignment: Jointly assigned to Monira Islam and Rukaiya Akther Trisha — follows the proposal split; this is a planned role, not a contribution record.

Hands-on operator: Monira Islam (you) — you will carry out every task, including tasks assigned to the frontend/UI workstream.

Requirement: Known defects must be resolved before release validation.

Target: Defect log has severity, reproduction, fix, and regression test.

Why this task matters: Defect log has severity, reproduction, fix, and regression test. It isolates one change so the student can inspect, test, and explain it before moving on.

Prerequisites: INTEGRATION-03

Concepts to understand: Reproduction; regression; severity.

Expected files/modules: defect log; affected modules/tests.

Implementation scope: Fix only reproduced defects; keep changes focused and reviewed.

Not in this task: Other modules, unrelated refactors, new dependencies, and unapproved features.

Ready-to-paste Codex prompt

You are implementing SellerOS, the SE-331 standalone social-commerce seller BI/decision-support capstone. Implement only INTEGRATION-04 — Triage and fix verified integration defects. Requirement: Known defects must be resolved before release validation. Objective/acceptance target: Defect log has severity, reproduction, fix, and regression test. Scope allowed: Fix only reproduced defects; keep changes focused and reviewed. Likely files/modules: defect log; affected modules/tests. Prerequisites: INTEGRATION-03. Constraints: follow the approved React/Vite/TypeScript + Django/DRF + PostgreSQL architecture and existing API/data contracts; inspect the repository first; preserve existing working behavior; do not invent unresolved business rules—mark [DECISION REQUIRED]; do not modify unrelated files, add unnecessary dependencies, expose secrets, bypass authentication/store permissions, fabricate AI/ML results, or create autonomous actions. Out of scope for this task: Other modules, unrelated refactors, new dependencies, and unapproved features. Test requirement: All release-blocking defects closed or documented. Run the narrow relevant checks and report exact commands and outcomes. Expected output: focused implementation, meaningful tests, and concise notes on files changed, decisions, risks, and next dependency. Code quality: small readable changes, type/validation/error handling appropriate to the existing project, no duplicated business formulas, and no generated or sensitive data committed.

Expected Codex output: A focused change for INTEGRATION-04, relevant tests, a file-change summary, and exact commands/results. No unrelated implementation.

How to inspect: Review the diff for these boundaries: Fix only reproduced defects; keep changes focused and reviewed. Confirm only expected files changed, validation/permissions match the contract, and tests exercise the requirement.

How to understand: Explain in your own words how Reproduction; regression; severity. support this task; trace one normal case and one failure case through the code.

Run commands: Use verified environment commands from SETUP-07. Typical checks: backend: `python manage.py check` and the focused Django test module; frontend: `npm run lint`, focused test, and `npm run build`. Run only commands applicable to changed code and report exact outcomes.

Test steps / expected result: All release-blocking defects closed or documented. Success means the target is present, tests pass, and failure behavior is understandable.

Common errors: If the DB is unavailable, verify PostgreSQL service, database name, credentials, and env loading. If imports/routes fail, check app registration and URL inclusion. If an API/UI mismatch appears, compare against docs/api-contract.md and correct the contract or implementation deliberately; do not patch around it.

Git milestone: After review and passing tests, commit only this task. Suggested: `git add <reviewed-files> && git commit -m "INTEGRATION-04: triage and fix verified integration defects"`. Use a feature branch only when it helps isolate a risky/long feature; no empty commits.

Viva questions: 1. What requirement does INTEGRATION-04 satisfy? 2. Which data/API/UI boundary does it change? 3. How is invalid or unauthorized input handled? 4. What test proves it works? 5. What limitation remains?

Definition of Done: ☐ Scope met  ☐ Code understood  ☐ Focused tests pass  ☐ No unrelated changes  ☐ Evidence recorded  ☐ Commit created  ☐ Docs updated if affected  ☐ Viva explanation ready

## INTEGRATION-05 — Run full regression and record results

Proposal lead / workstream assignment: Jointly assigned to Monira Islam and Rukaiya Akther Trisha — follows the proposal split; this is a planned role, not a contribution record.

Hands-on operator: Monira Islam (you) — you will carry out every task, including tasks assigned to the frontend/UI workstream.

Requirement: Release claims need a repeatable verification record.

Target: Backend, frontend, integration, and AI evaluation suites run from clean state.

Why this task matters: Backend, frontend, integration, and AI evaluation suites run from clean state. It isolates one change so the student can inspect, test, and explain it before moving on.

Prerequisites: INTEGRATION-04

Concepts to understand: Regression suite; environment capture.

Expected files/modules: CI config; docs/test-evidence/release-regression.

Implementation scope: Do not describe unrun checks as passed.

Not in this task: Other modules, unrelated refactors, new dependencies, and unapproved features.

Ready-to-paste Codex prompt

You are implementing SellerOS, the SE-331 standalone social-commerce seller BI/decision-support capstone. Implement only INTEGRATION-05 — Run full regression and record results. Requirement: Release claims need a repeatable verification record. Objective/acceptance target: Backend, frontend, integration, and AI evaluation suites run from clean state. Scope allowed: Do not describe unrun checks as passed. Likely files/modules: CI config; docs/test-evidence/release-regression. Prerequisites: INTEGRATION-04. Constraints: follow the approved React/Vite/TypeScript + Django/DRF + PostgreSQL architecture and existing API/data contracts; inspect the repository first; preserve existing working behavior; do not invent unresolved business rules—mark [DECISION REQUIRED]; do not modify unrelated files, add unnecessary dependencies, expose secrets, bypass authentication/store permissions, fabricate AI/ML results, or create autonomous actions. Out of scope for this task: Other modules, unrelated refactors, new dependencies, and unapproved features. Test requirement: Checkpoint 12 passes or blockers are listed honestly. Run the narrow relevant checks and report exact commands and outcomes. Expected output: focused implementation, meaningful tests, and concise notes on files changed, decisions, risks, and next dependency. Code quality: small readable changes, type/validation/error handling appropriate to the existing project, no duplicated business formulas, and no generated or sensitive data committed.

Expected Codex output: A focused change for INTEGRATION-05, relevant tests, a file-change summary, and exact commands/results. No unrelated implementation.

How to inspect: Review the diff for these boundaries: Do not describe unrun checks as passed. Confirm only expected files changed, validation/permissions match the contract, and tests exercise the requirement.

How to understand: Explain in your own words how Regression suite; environment capture. support this task; trace one normal case and one failure case through the code.

Run commands: Use verified environment commands from SETUP-07. Typical checks: backend: `python manage.py check` and the focused Django test module; frontend: `npm run lint`, focused test, and `npm run build`. Run only commands applicable to changed code and report exact outcomes.

Test steps / expected result: Checkpoint 12 passes or blockers are listed honestly. Success means the target is present, tests pass, and failure behavior is understandable.

Common errors: If the DB is unavailable, verify PostgreSQL service, database name, credentials, and env loading. If imports/routes fail, check app registration and URL inclusion. If an API/UI mismatch appears, compare against docs/api-contract.md and correct the contract or implementation deliberately; do not patch around it.

Git milestone: After review and passing tests, commit only this task. Suggested: `git add <reviewed-files> && git commit -m "INTEGRATION-05: run full regression and record results"`. Use a feature branch only when it helps isolate a risky/long feature; no empty commits.

Viva questions: 1. What requirement does INTEGRATION-05 satisfy? 2. Which data/API/UI boundary does it change? 3. How is invalid or unauthorized input handled? 4. What test proves it works? 5. What limitation remains?

Definition of Done: ☐ Scope met  ☐ Code understood  ☐ Focused tests pass  ☐ No unrelated changes  ☐ Evidence recorded  ☐ Commit created  ☐ Docs updated if affected  ☐ Viva explanation ready

# Phase 17 — Testing, security, performance, and usability

Build evidence incrementally and report actual measurements only.

## TEST-01 — Add model and constraint tests across modules

Proposal lead / workstream assignment: Monira Islam — follows the proposal split; this is a planned role, not a contribution record.

Hands-on operator: Monira Islam (you) — you will carry out every task, including tasks assigned to the frontend/UI workstream.

Requirement: Database invariants need fast regression checks.

Target: Core models, constraints, and deletion behaviors have isolated tests.

Why this task matters: Core models, constraints, and deletion behaviors have isolated tests. It isolates one change so the student can inspect, test, and explain it before moving on.

Prerequisites: None beyond repository inspection and the approved project baseline.

Concepts to understand: Unit tests; constraints; factories.

Expected files/modules: backend/apps/*/tests/test_models.py.

Implementation scope: No broad tests with opaque assertions.

Not in this task: Other modules, unrelated refactors, new dependencies, and unapproved features.

Ready-to-paste Codex prompt

You are implementing SellerOS, the SE-331 standalone social-commerce seller BI/decision-support capstone. Implement only TEST-01 — Add model and constraint tests across modules. Requirement: Database invariants need fast regression checks. Objective/acceptance target: Core models, constraints, and deletion behaviors have isolated tests. Scope allowed: No broad tests with opaque assertions. Likely files/modules: backend/apps/*/tests/test_models.py. Prerequisites: none beyond the approved project baseline. Constraints: follow the approved React/Vite/TypeScript + Django/DRF + PostgreSQL architecture and existing API/data contracts; inspect the repository first; preserve existing working behavior; do not invent unresolved business rules—mark [DECISION REQUIRED]; do not modify unrelated files, add unnecessary dependencies, expose secrets, bypass authentication/store permissions, fabricate AI/ML results, or create autonomous actions. Out of scope for this task: Other modules, unrelated refactors, new dependencies, and unapproved features. Test requirement: Tests prove specific invariants and pass on PostgreSQL. Run the narrow relevant checks and report exact commands and outcomes. Expected output: focused implementation, meaningful tests, and concise notes on files changed, decisions, risks, and next dependency. Code quality: small readable changes, type/validation/error handling appropriate to the existing project, no duplicated business formulas, and no generated or sensitive data committed.

Expected Codex output: A focused change for TEST-01, relevant tests, a file-change summary, and exact commands/results. No unrelated implementation.

How to inspect: Review the diff for these boundaries: No broad tests with opaque assertions. Confirm only expected files changed, validation/permissions match the contract, and tests exercise the requirement.

How to understand: Explain in your own words how Unit tests; constraints; factories. support this task; trace one normal case and one failure case through the code.

Run commands: Use verified environment commands from SETUP-07. Typical checks: backend: `python manage.py check` and the focused Django test module; frontend: `npm run lint`, focused test, and `npm run build`. Run only commands applicable to changed code and report exact outcomes.

Test steps / expected result: Tests prove specific invariants and pass on PostgreSQL. Success means the target is present, tests pass, and failure behavior is understandable.

Common errors: If the DB is unavailable, verify PostgreSQL service, database name, credentials, and env loading. If imports/routes fail, check app registration and URL inclusion. If an API/UI mismatch appears, compare against docs/api-contract.md and correct the contract or implementation deliberately; do not patch around it.

Git milestone: After review and passing tests, commit only this task. Suggested: `git add <reviewed-files> && git commit -m "TEST-01: add model and constraint tests across modules"`. Use a feature branch only when it helps isolate a risky/long feature; no empty commits.

Viva questions: 1. What requirement does TEST-01 satisfy? 2. Which data/API/UI boundary does it change? 3. How is invalid or unauthorized input handled? 4. What test proves it works? 5. What limitation remains?

Definition of Done: ☐ Scope met  ☐ Code understood  ☐ Focused tests pass  ☐ No unrelated changes  ☐ Evidence recorded  ☐ Commit created  ☐ Docs updated if affected  ☐ Viva explanation ready

## TEST-02 — Add serializer and validation test matrix

Proposal lead / workstream assignment: Monira Islam — follows the proposal split; this is a planned role, not a contribution record.

Hands-on operator: Monira Islam (you) — you will carry out every task, including tasks assigned to the frontend/UI workstream.

Requirement: Invalid input must fail safely and consistently.

Target: Each write endpoint has valid, missing, malformed, and boundary payload tests.

Why this task matters: Each write endpoint has valid, missing, malformed, and boundary payload tests. It isolates one change so the student can inspect, test, and explain it before moving on.

Prerequisites: TEST-01

Concepts to understand: Boundary testing; validation errors.

Expected files/modules: backend/apps/*/tests/test_serializers.py.

Implementation scope: Cover documented rules only.

Not in this task: Other modules, unrelated refactors, new dependencies, and unapproved features.

Ready-to-paste Codex prompt

You are implementing SellerOS, the SE-331 standalone social-commerce seller BI/decision-support capstone. Implement only TEST-02 — Add serializer and validation test matrix. Requirement: Invalid input must fail safely and consistently. Objective/acceptance target: Each write endpoint has valid, missing, malformed, and boundary payload tests. Scope allowed: Cover documented rules only. Likely files/modules: backend/apps/*/tests/test_serializers.py. Prerequisites: TEST-01. Constraints: follow the approved React/Vite/TypeScript + Django/DRF + PostgreSQL architecture and existing API/data contracts; inspect the repository first; preserve existing working behavior; do not invent unresolved business rules—mark [DECISION REQUIRED]; do not modify unrelated files, add unnecessary dependencies, expose secrets, bypass authentication/store permissions, fabricate AI/ML results, or create autonomous actions. Out of scope for this task: Other modules, unrelated refactors, new dependencies, and unapproved features. Test requirement: Response matches shared error contract. Run the narrow relevant checks and report exact commands and outcomes. Expected output: focused implementation, meaningful tests, and concise notes on files changed, decisions, risks, and next dependency. Code quality: small readable changes, type/validation/error handling appropriate to the existing project, no duplicated business formulas, and no generated or sensitive data committed.

Expected Codex output: A focused change for TEST-02, relevant tests, a file-change summary, and exact commands/results. No unrelated implementation.

How to inspect: Review the diff for these boundaries: Cover documented rules only. Confirm only expected files changed, validation/permissions match the contract, and tests exercise the requirement.

How to understand: Explain in your own words how Boundary testing; validation errors. support this task; trace one normal case and one failure case through the code.

Run commands: Use verified environment commands from SETUP-07. Typical checks: backend: `python manage.py check` and the focused Django test module; frontend: `npm run lint`, focused test, and `npm run build`. Run only commands applicable to changed code and report exact outcomes.

Test steps / expected result: Response matches shared error contract. Success means the target is present, tests pass, and failure behavior is understandable.

Common errors: If the DB is unavailable, verify PostgreSQL service, database name, credentials, and env loading. If imports/routes fail, check app registration and URL inclusion. If an API/UI mismatch appears, compare against docs/api-contract.md and correct the contract or implementation deliberately; do not patch around it.

Git milestone: After review and passing tests, commit only this task. Suggested: `git add <reviewed-files> && git commit -m "TEST-02: add serializer and validation test matrix"`. Use a feature branch only when it helps isolate a risky/long feature; no empty commits.

Viva questions: 1. What requirement does TEST-02 satisfy? 2. Which data/API/UI boundary does it change? 3. How is invalid or unauthorized input handled? 4. What test proves it works? 5. What limitation remains?

Definition of Done: ☐ Scope met  ☐ Code understood  ☐ Focused tests pass  ☐ No unrelated changes  ☐ Evidence recorded  ☐ Commit created  ☐ Docs updated if affected  ☐ Viva explanation ready

## TEST-03 — Add API and permission test matrix

Proposal lead / workstream assignment: Jointly assigned to Monira Islam and Rukaiya Akther Trisha — follows the proposal split; this is a planned role, not a contribution record.

Hands-on operator: Monira Islam (you) — you will carry out every task, including tasks assigned to the frontend/UI workstream.

Requirement: Endpoint behavior and authorization require direct coverage.

Target: Read/write endpoints cover status codes, filters, roles, and cross-store requests.

Why this task matters: Read/write endpoints cover status codes, filters, roles, and cross-store requests. It isolates one change so the student can inspect, test, and explain it before moving on.

Prerequisites: TEST-02

Concepts to understand: API testing; RBAC; IDOR.

Expected files/modules: backend/apps/*/tests/test_api.py; security tests.

Implementation scope: No endpoint marked covered without executing test.

Not in this task: Other modules, unrelated refactors, new dependencies, and unapproved features.

Ready-to-paste Codex prompt

You are implementing SellerOS, the SE-331 standalone social-commerce seller BI/decision-support capstone. Implement only TEST-03 — Add API and permission test matrix. Requirement: Endpoint behavior and authorization require direct coverage. Objective/acceptance target: Read/write endpoints cover status codes, filters, roles, and cross-store requests. Scope allowed: No endpoint marked covered without executing test. Likely files/modules: backend/apps/*/tests/test_api.py; security tests. Prerequisites: TEST-02. Constraints: follow the approved React/Vite/TypeScript + Django/DRF + PostgreSQL architecture and existing API/data contracts; inspect the repository first; preserve existing working behavior; do not invent unresolved business rules—mark [DECISION REQUIRED]; do not modify unrelated files, add unnecessary dependencies, expose secrets, bypass authentication/store permissions, fabricate AI/ML results, or create autonomous actions. Out of scope for this task: Other modules, unrelated refactors, new dependencies, and unapproved features. Test requirement: All protected endpoints have negative tests. Run the narrow relevant checks and report exact commands and outcomes. Expected output: focused implementation, meaningful tests, and concise notes on files changed, decisions, risks, and next dependency. Code quality: small readable changes, type/validation/error handling appropriate to the existing project, no duplicated business formulas, and no generated or sensitive data committed.

Expected Codex output: A focused change for TEST-03, relevant tests, a file-change summary, and exact commands/results. No unrelated implementation.

How to inspect: Review the diff for these boundaries: No endpoint marked covered without executing test. Confirm only expected files changed, validation/permissions match the contract, and tests exercise the requirement.

How to understand: Explain in your own words how API testing; RBAC; IDOR. support this task; trace one normal case and one failure case through the code.

Run commands: Use verified environment commands from SETUP-07. Typical checks: backend: `python manage.py check` and the focused Django test module; frontend: `npm run lint`, focused test, and `npm run build`. Run only commands applicable to changed code and report exact outcomes.

Test steps / expected result: All protected endpoints have negative tests. Success means the target is present, tests pass, and failure behavior is understandable.

Common errors: If the DB is unavailable, verify PostgreSQL service, database name, credentials, and env loading. If imports/routes fail, check app registration and URL inclusion. If an API/UI mismatch appears, compare against docs/api-contract.md and correct the contract or implementation deliberately; do not patch around it.

Git milestone: After review and passing tests, commit only this task. Suggested: `git add <reviewed-files> && git commit -m "TEST-03: add api and permission test matrix"`. Use a feature branch only when it helps isolate a risky/long feature; no empty commits.

Viva questions: 1. What requirement does TEST-03 satisfy? 2. Which data/API/UI boundary does it change? 3. How is invalid or unauthorized input handled? 4. What test proves it works? 5. What limitation remains?

Definition of Done: ☐ Scope met  ☐ Code understood  ☐ Focused tests pass  ☐ No unrelated changes  ☐ Evidence recorded  ☐ Commit created  ☐ Docs updated if affected  ☐ Viva explanation ready

## TEST-04 — Add frontend form and state tests

Proposal lead / workstream assignment: Rukaiya Akther Trisha — follows the proposal split; this is a planned role, not a contribution record.

Hands-on operator: Monira Islam (you) — you will carry out every task, including tasks assigned to the frontend/UI workstream.

Requirement: UI behavior includes validation and failures, not only happy paths.

Target: Forms, empty/loading/error/success and accessible feedback are tested.

Why this task matters: Forms, empty/loading/error/success and accessible feedback are tested. It isolates one change so the student can inspect, test, and explain it before moving on.

Prerequisites: TEST-03

Concepts to understand: Component tests; accessibility; mocked API.

Expected files/modules: frontend/src/**/*.test.tsx.

Implementation scope: No tests tied only to implementation details.

Not in this task: Other modules, unrelated refactors, new dependencies, and unapproved features.

Ready-to-paste Codex prompt

You are implementing SellerOS, the SE-331 standalone social-commerce seller BI/decision-support capstone. Implement only TEST-04 — Add frontend form and state tests. Requirement: UI behavior includes validation and failures, not only happy paths. Objective/acceptance target: Forms, empty/loading/error/success and accessible feedback are tested. Scope allowed: No tests tied only to implementation details. Likely files/modules: frontend/src/**/*.test.tsx. Prerequisites: TEST-03. Constraints: follow the approved React/Vite/TypeScript + Django/DRF + PostgreSQL architecture and existing API/data contracts; inspect the repository first; preserve existing working behavior; do not invent unresolved business rules—mark [DECISION REQUIRED]; do not modify unrelated files, add unnecessary dependencies, expose secrets, bypass authentication/store permissions, fabricate AI/ML results, or create autonomous actions. Out of scope for this task: Other modules, unrelated refactors, new dependencies, and unapproved features. Test requirement: User-visible behaviors covered. Run the narrow relevant checks and report exact commands and outcomes. Expected output: focused implementation, meaningful tests, and concise notes on files changed, decisions, risks, and next dependency. Code quality: small readable changes, type/validation/error handling appropriate to the existing project, no duplicated business formulas, and no generated or sensitive data committed.

Expected Codex output: A focused change for TEST-04, relevant tests, a file-change summary, and exact commands/results. No unrelated implementation.

How to inspect: Review the diff for these boundaries: No tests tied only to implementation details. Confirm only expected files changed, validation/permissions match the contract, and tests exercise the requirement.

How to understand: Explain in your own words how Component tests; accessibility; mocked API. support this task; trace one normal case and one failure case through the code.

Run commands: Use verified environment commands from SETUP-07. Typical checks: backend: `python manage.py check` and the focused Django test module; frontend: `npm run lint`, focused test, and `npm run build`. Run only commands applicable to changed code and report exact outcomes.

Test steps / expected result: User-visible behaviors covered. Success means the target is present, tests pass, and failure behavior is understandable.

Common errors: If the DB is unavailable, verify PostgreSQL service, database name, credentials, and env loading. If imports/routes fail, check app registration and URL inclusion. If an API/UI mismatch appears, compare against docs/api-contract.md and correct the contract or implementation deliberately; do not patch around it.

Git milestone: After review and passing tests, commit only this task. Suggested: `git add <reviewed-files> && git commit -m "TEST-04: add frontend form and state tests"`. Use a feature branch only when it helps isolate a risky/long feature; no empty commits.

Viva questions: 1. What requirement does TEST-04 satisfy? 2. Which data/API/UI boundary does it change? 3. How is invalid or unauthorized input handled? 4. What test proves it works? 5. What limitation remains?

Definition of Done: ☐ Scope met  ☐ Code understood  ☐ Focused tests pass  ☐ No unrelated changes  ☐ Evidence recorded  ☐ Commit created  ☐ Docs updated if affected  ☐ Viva explanation ready

## TEST-05 — Add end-to-end workflow tests

Proposal lead / workstream assignment: Jointly assigned to Monira Islam and Rukaiya Akther Trisha — follows the proposal split; this is a planned role, not a contribution record.

Hands-on operator: Monira Islam (you) — you will carry out every task, including tasks assigned to the frontend/UI workstream.

Requirement: Core SellerOS workflows need integrated browser evidence.

Target: Main CRUD and analytics flows run against test services.

Why this task matters: Main CRUD and analytics flows run against test services. It isolates one change so the student can inspect, test, and explain it before moving on.

Prerequisites: TEST-04

Concepts to understand: E2E; test isolation; seeded records.

Expected files/modules: frontend/e2e; test environment config.

Implementation scope: Keep deterministic; no production provider calls.

Not in this task: Other modules, unrelated refactors, new dependencies, and unapproved features.

Ready-to-paste Codex prompt

You are implementing SellerOS, the SE-331 standalone social-commerce seller BI/decision-support capstone. Implement only TEST-05 — Add end-to-end workflow tests. Requirement: Core SellerOS workflows need integrated browser evidence. Objective/acceptance target: Main CRUD and analytics flows run against test services. Scope allowed: Keep deterministic; no production provider calls. Likely files/modules: frontend/e2e; test environment config. Prerequisites: TEST-04. Constraints: follow the approved React/Vite/TypeScript + Django/DRF + PostgreSQL architecture and existing API/data contracts; inspect the repository first; preserve existing working behavior; do not invent unresolved business rules—mark [DECISION REQUIRED]; do not modify unrelated files, add unnecessary dependencies, expose secrets, bypass authentication/store permissions, fabricate AI/ML results, or create autonomous actions. Out of scope for this task: Other modules, unrelated refactors, new dependencies, and unapproved features. Test requirement: Workflow passes from a clean reset. Run the narrow relevant checks and report exact commands and outcomes. Expected output: focused implementation, meaningful tests, and concise notes on files changed, decisions, risks, and next dependency. Code quality: small readable changes, type/validation/error handling appropriate to the existing project, no duplicated business formulas, and no generated or sensitive data committed.

Expected Codex output: A focused change for TEST-05, relevant tests, a file-change summary, and exact commands/results. No unrelated implementation.

How to inspect: Review the diff for these boundaries: Keep deterministic; no production provider calls. Confirm only expected files changed, validation/permissions match the contract, and tests exercise the requirement.

How to understand: Explain in your own words how E2E; test isolation; seeded records. support this task; trace one normal case and one failure case through the code.

Run commands: Use verified environment commands from SETUP-07. Typical checks: backend: `python manage.py check` and the focused Django test module; frontend: `npm run lint`, focused test, and `npm run build`. Run only commands applicable to changed code and report exact outcomes.

Test steps / expected result: Workflow passes from a clean reset. Success means the target is present, tests pass, and failure behavior is understandable.

Common errors: If the DB is unavailable, verify PostgreSQL service, database name, credentials, and env loading. If imports/routes fail, check app registration and URL inclusion. If an API/UI mismatch appears, compare against docs/api-contract.md and correct the contract or implementation deliberately; do not patch around it.

Git milestone: After review and passing tests, commit only this task. Suggested: `git add <reviewed-files> && git commit -m "TEST-05: add end-to-end workflow tests"`. Use a feature branch only when it helps isolate a risky/long feature; no empty commits.

Viva questions: 1. What requirement does TEST-05 satisfy? 2. Which data/API/UI boundary does it change? 3. How is invalid or unauthorized input handled? 4. What test proves it works? 5. What limitation remains?

Definition of Done: ☐ Scope met  ☐ Code understood  ☐ Focused tests pass  ☐ No unrelated changes  ☐ Evidence recorded  ☐ Commit created  ☐ Docs updated if affected  ☐ Viva explanation ready

## TEST-06 — Run security review and remediation

Proposal lead / workstream assignment: Jointly assigned to Monira Islam and Rukaiya Akther Trisha — follows the proposal split; this is a planned role, not a contribution record.

Hands-on operator: Monira Islam (you) — you will carry out every task, including tasks assigned to the frontend/UI workstream.

Requirement: Authentication, store isolation, secrets, and AI inputs are risk areas.

Target: Security checklist and findings document covers access, input, secrets, dependencies, and AI injection.

Why this task matters: Security checklist and findings document covers access, input, secrets, dependencies, and AI injection. It isolates one change so the student can inspect, test, and explain it before moving on.

Prerequisites: TEST-05

Concepts to understand: OWASP basics; threat modeling; secret scan.

Expected files/modules: docs/security-review.md; dependency reports; tests.

Implementation scope: No claim of security certification.

Not in this task: Other modules, unrelated refactors, new dependencies, and unapproved features.

Ready-to-paste Codex prompt

You are implementing SellerOS, the SE-331 standalone social-commerce seller BI/decision-support capstone. Implement only TEST-06 — Run security review and remediation. Requirement: Authentication, store isolation, secrets, and AI inputs are risk areas. Objective/acceptance target: Security checklist and findings document covers access, input, secrets, dependencies, and AI injection. Scope allowed: No claim of security certification. Likely files/modules: docs/security-review.md; dependency reports; tests. Prerequisites: TEST-05. Constraints: follow the approved React/Vite/TypeScript + Django/DRF + PostgreSQL architecture and existing API/data contracts; inspect the repository first; preserve existing working behavior; do not invent unresolved business rules—mark [DECISION REQUIRED]; do not modify unrelated files, add unnecessary dependencies, expose secrets, bypass authentication/store permissions, fabricate AI/ML results, or create autonomous actions. Out of scope for this task: Other modules, unrelated refactors, new dependencies, and unapproved features. Test requirement: High-priority findings resolved or disclosed. Run the narrow relevant checks and report exact commands and outcomes. Expected output: focused implementation, meaningful tests, and concise notes on files changed, decisions, risks, and next dependency. Code quality: small readable changes, type/validation/error handling appropriate to the existing project, no duplicated business formulas, and no generated or sensitive data committed.

Expected Codex output: A focused change for TEST-06, relevant tests, a file-change summary, and exact commands/results. No unrelated implementation.

How to inspect: Review the diff for these boundaries: No claim of security certification. Confirm only expected files changed, validation/permissions match the contract, and tests exercise the requirement.

How to understand: Explain in your own words how OWASP basics; threat modeling; secret scan. support this task; trace one normal case and one failure case through the code.

Run commands: Use verified environment commands from SETUP-07. Typical checks: backend: `python manage.py check` and the focused Django test module; frontend: `npm run lint`, focused test, and `npm run build`. Run only commands applicable to changed code and report exact outcomes.

Test steps / expected result: High-priority findings resolved or disclosed. Success means the target is present, tests pass, and failure behavior is understandable.

Common errors: If the DB is unavailable, verify PostgreSQL service, database name, credentials, and env loading. If imports/routes fail, check app registration and URL inclusion. If an API/UI mismatch appears, compare against docs/api-contract.md and correct the contract or implementation deliberately; do not patch around it.

Git milestone: After review and passing tests, commit only this task. Suggested: `git add <reviewed-files> && git commit -m "TEST-06: run security review and remediation"`. Use a feature branch only when it helps isolate a risky/long feature; no empty commits.

Viva questions: 1. What requirement does TEST-06 satisfy? 2. Which data/API/UI boundary does it change? 3. How is invalid or unauthorized input handled? 4. What test proves it works? 5. What limitation remains?

Definition of Done: ☐ Scope met  ☐ Code understood  ☐ Focused tests pass  ☐ No unrelated changes  ☐ Evidence recorded  ☐ Commit created  ☐ Docs updated if affected  ☐ Viva explanation ready

## TEST-07 — Measure performance and run usability checks

Proposal lead / workstream assignment: Jointly assigned to Monira Islam and Rukaiya Akther Trisha — follows the proposal split; this is a planned role, not a contribution record.

Hands-on operator: Monira Islam (you) — you will carry out every task, including tasks assigned to the frontend/UI workstream.

Requirement: Performance and usability statements need measured evidence.

Target: Representative request timings, data size, setup, task observations, and defects are recorded.

Why this task matters: Representative request timings, data size, setup, task observations, and defects are recorded. It isolates one change so the student can inspect, test, and explain it before moving on.

Prerequisites: TEST-06

Concepts to understand: Benchmark method; sample size; usability observation.

Expected files/modules: docs/evaluation/performance-usability.md; scripts.

Implementation scope: Do not claim scale or improvement without measurement.

Not in this task: Other modules, unrelated refactors, new dependencies, and unapproved features.

Ready-to-paste Codex prompt

You are implementing SellerOS, the SE-331 standalone social-commerce seller BI/decision-support capstone. Implement only TEST-07 — Measure performance and run usability checks. Requirement: Performance and usability statements need measured evidence. Objective/acceptance target: Representative request timings, data size, setup, task observations, and defects are recorded. Scope allowed: Do not claim scale or improvement without measurement. Likely files/modules: docs/evaluation/performance-usability.md; scripts. Prerequisites: TEST-06. Constraints: follow the approved React/Vite/TypeScript + Django/DRF + PostgreSQL architecture and existing API/data contracts; inspect the repository first; preserve existing working behavior; do not invent unresolved business rules—mark [DECISION REQUIRED]; do not modify unrelated files, add unnecessary dependencies, expose secrets, bypass authentication/store permissions, fabricate AI/ML results, or create autonomous actions. Out of scope for this task: Other modules, unrelated refactors, new dependencies, and unapproved features. Test requirement: Report states environment, method, findings, and limitations. Run the narrow relevant checks and report exact commands and outcomes. Expected output: focused implementation, meaningful tests, and concise notes on files changed, decisions, risks, and next dependency. Code quality: small readable changes, type/validation/error handling appropriate to the existing project, no duplicated business formulas, and no generated or sensitive data committed.

Expected Codex output: A focused change for TEST-07, relevant tests, a file-change summary, and exact commands/results. No unrelated implementation.

How to inspect: Review the diff for these boundaries: Do not claim scale or improvement without measurement. Confirm only expected files changed, validation/permissions match the contract, and tests exercise the requirement.

How to understand: Explain in your own words how Benchmark method; sample size; usability observation. support this task; trace one normal case and one failure case through the code.

Run commands: Use verified environment commands from SETUP-07. Typical checks: backend: `python manage.py check` and the focused Django test module; frontend: `npm run lint`, focused test, and `npm run build`. Run only commands applicable to changed code and report exact outcomes.

Test steps / expected result: Report states environment, method, findings, and limitations. Success means the target is present, tests pass, and failure behavior is understandable.

Common errors: If the DB is unavailable, verify PostgreSQL service, database name, credentials, and env loading. If imports/routes fail, check app registration and URL inclusion. If an API/UI mismatch appears, compare against docs/api-contract.md and correct the contract or implementation deliberately; do not patch around it.

Git milestone: After review and passing tests, commit only this task. Suggested: `git add <reviewed-files> && git commit -m "TEST-07: measure performance and run usability checks"`. Use a feature branch only when it helps isolate a risky/long feature; no empty commits.

Viva questions: 1. What requirement does TEST-07 satisfy? 2. Which data/API/UI boundary does it change? 3. How is invalid or unauthorized input handled? 4. What test proves it works? 5. What limitation remains?

Definition of Done: ☐ Scope met  ☐ Code understood  ☐ Focused tests pass  ☐ No unrelated changes  ☐ Evidence recorded  ☐ Commit created  ☐ Docs updated if affected  ☐ Viva explanation ready

# Phase 18 — Demo readiness, documentation, and viva

Package the prototype and evidence so the student can explain every part honestly.

## DEPLOY-01 — Choose local demo or approved deployment target

Proposal lead / workstream assignment: Jointly assigned to Monira Islam and Rukaiya Akther Trisha — follows the proposal split; this is a planned role, not a contribution record.

Hands-on operator: Monira Islam (you) — you will carry out every task, including tasks assigned to the frontend/UI workstream.

Requirement: Deployment must match course/demo needs and data policy.

Target: Target, access model, environment variables, database backup/reset, and cost limit are recorded.

Why this task matters: Target, access model, environment variables, database backup/reset, and cost limit are recorded. It isolates one change so the student can inspect, test, and explain it before moving on.

Prerequisites: None beyond repository inspection and the approved project baseline.

Concepts to understand: Deployment model; environment; backup.

Expected files/modules: docs/deployment-plan.md; .env.example.

Implementation scope: No cloud account/service unless explicitly approved; keep secrets private.

Not in this task: Other modules, unrelated refactors, new dependencies, and unapproved features.

Ready-to-paste Codex prompt

You are implementing SellerOS, the SE-331 standalone social-commerce seller BI/decision-support capstone. Implement only DEPLOY-01 — Choose local demo or approved deployment target. Requirement: Deployment must match course/demo needs and data policy. Objective/acceptance target: Target, access model, environment variables, database backup/reset, and cost limit are recorded. Scope allowed: No cloud account/service unless explicitly approved; keep secrets private. Likely files/modules: docs/deployment-plan.md; .env.example. Prerequisites: none beyond the approved project baseline. Constraints: follow the approved React/Vite/TypeScript + Django/DRF + PostgreSQL architecture and existing API/data contracts; inspect the repository first; preserve existing working behavior; do not invent unresolved business rules—mark [DECISION REQUIRED]; do not modify unrelated files, add unnecessary dependencies, expose secrets, bypass authentication/store permissions, fabricate AI/ML results, or create autonomous actions. Out of scope for this task: Other modules, unrelated refactors, new dependencies, and unapproved features. Test requirement: Target approved before provisioning. Run the narrow relevant checks and report exact commands and outcomes. Expected output: focused implementation, meaningful tests, and concise notes on files changed, decisions, risks, and next dependency. Code quality: small readable changes, type/validation/error handling appropriate to the existing project, no duplicated business formulas, and no generated or sensitive data committed.

Expected Codex output: A focused change for DEPLOY-01, relevant tests, a file-change summary, and exact commands/results. No unrelated implementation.

How to inspect: Review the diff for these boundaries: No cloud account/service unless explicitly approved; keep secrets private. Confirm only expected files changed, validation/permissions match the contract, and tests exercise the requirement.

How to understand: Explain in your own words how Deployment model; environment; backup. support this task; trace one normal case and one failure case through the code.

Run commands: Use verified environment commands from SETUP-07. Typical checks: backend: `python manage.py check` and the focused Django test module; frontend: `npm run lint`, focused test, and `npm run build`. Run only commands applicable to changed code and report exact outcomes.

Test steps / expected result: Target approved before provisioning. Success means the target is present, tests pass, and failure behavior is understandable.

Common errors: If the DB is unavailable, verify PostgreSQL service, database name, credentials, and env loading. If imports/routes fail, check app registration and URL inclusion. If an API/UI mismatch appears, compare against docs/api-contract.md and correct the contract or implementation deliberately; do not patch around it.

Git milestone: After review and passing tests, commit only this task. Suggested: `git add <reviewed-files> && git commit -m "DEPLOY-01: choose local demo or approved deployment target"`. Use a feature branch only when it helps isolate a risky/long feature; no empty commits.

Viva questions: 1. What requirement does DEPLOY-01 satisfy? 2. Which data/API/UI boundary does it change? 3. How is invalid or unauthorized input handled? 4. What test proves it works? 5. What limitation remains?

Definition of Done: ☐ Scope met  ☐ Code understood  ☐ Focused tests pass  ☐ No unrelated changes  ☐ Evidence recorded  ☐ Commit created  ☐ Docs updated if affected  ☐ Viva explanation ready

## DEPLOY-02 — Prepare repeatable demo build and environment

Proposal lead / workstream assignment: Monira Islam — follows the proposal split; this is a planned role, not a contribution record.

Hands-on operator: Monira Islam (you) — you will carry out every task, including tasks assigned to the frontend/UI workstream.

Requirement: A stable demo needs documented setup and health checks.

Target: Backend/frontend build and database migration operate in the target environment.

Why this task matters: Backend/frontend build and database migration operate in the target environment. It isolates one change so the student can inspect, test, and explain it before moving on.

Prerequisites: DEPLOY-01

Concepts to understand: Build artifacts; env validation; migrations.

Expected files/modules: deployment config; README; scripts.

Implementation scope: Do not load production customer data.

Not in this task: Other modules, unrelated refactors, new dependencies, and unapproved features.

Ready-to-paste Codex prompt

You are implementing SellerOS, the SE-331 standalone social-commerce seller BI/decision-support capstone. Implement only DEPLOY-02 — Prepare repeatable demo build and environment. Requirement: A stable demo needs documented setup and health checks. Objective/acceptance target: Backend/frontend build and database migration operate in the target environment. Scope allowed: Do not load production customer data. Likely files/modules: deployment config; README; scripts. Prerequisites: DEPLOY-01. Constraints: follow the approved React/Vite/TypeScript + Django/DRF + PostgreSQL architecture and existing API/data contracts; inspect the repository first; preserve existing working behavior; do not invent unresolved business rules—mark [DECISION REQUIRED]; do not modify unrelated files, add unnecessary dependencies, expose secrets, bypass authentication/store permissions, fabricate AI/ML results, or create autonomous actions. Out of scope for this task: Other modules, unrelated refactors, new dependencies, and unapproved features. Test requirement: Fresh environment smoke test passes. Run the narrow relevant checks and report exact commands and outcomes. Expected output: focused implementation, meaningful tests, and concise notes on files changed, decisions, risks, and next dependency. Code quality: small readable changes, type/validation/error handling appropriate to the existing project, no duplicated business formulas, and no generated or sensitive data committed.

Expected Codex output: A focused change for DEPLOY-02, relevant tests, a file-change summary, and exact commands/results. No unrelated implementation.

How to inspect: Review the diff for these boundaries: Do not load production customer data. Confirm only expected files changed, validation/permissions match the contract, and tests exercise the requirement.

How to understand: Explain in your own words how Build artifacts; env validation; migrations. support this task; trace one normal case and one failure case through the code.

Run commands: Use verified environment commands from SETUP-07. Typical checks: backend: `python manage.py check` and the focused Django test module; frontend: `npm run lint`, focused test, and `npm run build`. Run only commands applicable to changed code and report exact outcomes.

Test steps / expected result: Fresh environment smoke test passes. Success means the target is present, tests pass, and failure behavior is understandable.

Common errors: If the DB is unavailable, verify PostgreSQL service, database name, credentials, and env loading. If imports/routes fail, check app registration and URL inclusion. If an API/UI mismatch appears, compare against docs/api-contract.md and correct the contract or implementation deliberately; do not patch around it.

Git milestone: After review and passing tests, commit only this task. Suggested: `git add <reviewed-files> && git commit -m "DEPLOY-02: prepare repeatable demo build and environment"`. Use a feature branch only when it helps isolate a risky/long feature; no empty commits.

Viva questions: 1. What requirement does DEPLOY-02 satisfy? 2. Which data/API/UI boundary does it change? 3. How is invalid or unauthorized input handled? 4. What test proves it works? 5. What limitation remains?

Definition of Done: ☐ Scope met  ☐ Code understood  ☐ Focused tests pass  ☐ No unrelated changes  ☐ Evidence recorded  ☐ Commit created  ☐ Docs updated if affected  ☐ Viva explanation ready

## DEPLOY-03 — Run release smoke test and rollback rehearsal

Proposal lead / workstream assignment: Jointly assigned to Monira Islam and Rukaiya Akther Trisha — follows the proposal split; this is a planned role, not a contribution record.

Hands-on operator: Monira Islam (you) — you will carry out every task, including tasks assigned to the frontend/UI workstream.

Requirement: A demo release should have a recovery path.

Target: Smoke checklist and backup/restore or rollback steps are verified.

Why this task matters: Smoke checklist and backup/restore or rollback steps are verified. It isolates one change so the student can inspect, test, and explain it before moving on.

Prerequisites: DEPLOY-02

Concepts to understand: Release verification; recovery.

Expected files/modules: docs/release-checklist.md; scripts.

Implementation scope: No irreversible data migration without backup.

Not in this task: Other modules, unrelated refactors, new dependencies, and unapproved features.

Ready-to-paste Codex prompt

You are implementing SellerOS, the SE-331 standalone social-commerce seller BI/decision-support capstone. Implement only DEPLOY-03 — Run release smoke test and rollback rehearsal. Requirement: A demo release should have a recovery path. Objective/acceptance target: Smoke checklist and backup/restore or rollback steps are verified. Scope allowed: No irreversible data migration without backup. Likely files/modules: docs/release-checklist.md; scripts. Prerequisites: DEPLOY-02. Constraints: follow the approved React/Vite/TypeScript + Django/DRF + PostgreSQL architecture and existing API/data contracts; inspect the repository first; preserve existing working behavior; do not invent unresolved business rules—mark [DECISION REQUIRED]; do not modify unrelated files, add unnecessary dependencies, expose secrets, bypass authentication/store permissions, fabricate AI/ML results, or create autonomous actions. Out of scope for this task: Other modules, unrelated refactors, new dependencies, and unapproved features. Test requirement: Checkpoint 12 has evidence. Run the narrow relevant checks and report exact commands and outcomes. Expected output: focused implementation, meaningful tests, and concise notes on files changed, decisions, risks, and next dependency. Code quality: small readable changes, type/validation/error handling appropriate to the existing project, no duplicated business formulas, and no generated or sensitive data committed.

Expected Codex output: A focused change for DEPLOY-03, relevant tests, a file-change summary, and exact commands/results. No unrelated implementation.

How to inspect: Review the diff for these boundaries: No irreversible data migration without backup. Confirm only expected files changed, validation/permissions match the contract, and tests exercise the requirement.

How to understand: Explain in your own words how Release verification; recovery. support this task; trace one normal case and one failure case through the code.

Run commands: Use verified environment commands from SETUP-07. Typical checks: backend: `python manage.py check` and the focused Django test module; frontend: `npm run lint`, focused test, and `npm run build`. Run only commands applicable to changed code and report exact outcomes.

Test steps / expected result: Checkpoint 12 has evidence. Success means the target is present, tests pass, and failure behavior is understandable.

Common errors: If the DB is unavailable, verify PostgreSQL service, database name, credentials, and env loading. If imports/routes fail, check app registration and URL inclusion. If an API/UI mismatch appears, compare against docs/api-contract.md and correct the contract or implementation deliberately; do not patch around it.

Git milestone: After review and passing tests, commit only this task. Suggested: `git add <reviewed-files> && git commit -m "DEPLOY-03: run release smoke test and rollback rehearsal"`. Use a feature branch only when it helps isolate a risky/long feature; no empty commits.

Viva questions: 1. What requirement does DEPLOY-03 satisfy? 2. Which data/API/UI boundary does it change? 3. How is invalid or unauthorized input handled? 4. What test proves it works? 5. What limitation remains?

Definition of Done: ☐ Scope met  ☐ Code understood  ☐ Focused tests pass  ☐ No unrelated changes  ☐ Evidence recorded  ☐ Commit created  ☐ Docs updated if affected  ☐ Viva explanation ready

## DOC-01 — Write system architecture and data-flow documentation

Proposal lead / workstream assignment: Jointly assigned to Monira Islam and Rukaiya Akther Trisha — follows the proposal split; this is a planned role, not a contribution record.

Hands-on operator: Monira Islam (you) — you will carry out every task, including tasks assigned to the frontend/UI workstream.

Requirement: Both members and evaluator need to understand boundaries.

Target: Architecture, responsibilities, trust boundaries, data flow, and key decisions are documented.

Why this task matters: Architecture, responsibilities, trust boundaries, data flow, and key decisions are documented. It isolates one change so the student can inspect, test, and explain it before moving on.

Prerequisites: DEPLOY-03

Concepts to understand: Architecture views; data lineage.

Expected files/modules: docs/architecture.md; ERD; sequence/data-flow diagram source.

Implementation scope: Update docs from actual code, not planned-only design.

Not in this task: Other modules, unrelated refactors, new dependencies, and unapproved features.

Ready-to-paste Codex prompt

You are implementing SellerOS, the SE-331 standalone social-commerce seller BI/decision-support capstone. Implement only DOC-01 — Write system architecture and data-flow documentation. Requirement: Both members and evaluator need to understand boundaries. Objective/acceptance target: Architecture, responsibilities, trust boundaries, data flow, and key decisions are documented. Scope allowed: Update docs from actual code, not planned-only design. Likely files/modules: docs/architecture.md; ERD; sequence/data-flow diagram source. Prerequisites: DEPLOY-03. Constraints: follow the approved React/Vite/TypeScript + Django/DRF + PostgreSQL architecture and existing API/data contracts; inspect the repository first; preserve existing working behavior; do not invent unresolved business rules—mark [DECISION REQUIRED]; do not modify unrelated files, add unnecessary dependencies, expose secrets, bypass authentication/store permissions, fabricate AI/ML results, or create autonomous actions. Out of scope for this task: Other modules, unrelated refactors, new dependencies, and unapproved features. Test requirement: Diagrams match implemented code. Run the narrow relevant checks and report exact commands and outcomes. Expected output: focused implementation, meaningful tests, and concise notes on files changed, decisions, risks, and next dependency. Code quality: small readable changes, type/validation/error handling appropriate to the existing project, no duplicated business formulas, and no generated or sensitive data committed.

Expected Codex output: A focused change for DOC-01, relevant tests, a file-change summary, and exact commands/results. No unrelated implementation.

How to inspect: Review the diff for these boundaries: Update docs from actual code, not planned-only design. Confirm only expected files changed, validation/permissions match the contract, and tests exercise the requirement.

How to understand: Explain in your own words how Architecture views; data lineage. support this task; trace one normal case and one failure case through the code.

Run commands: Use verified environment commands from SETUP-07. Typical checks: backend: `python manage.py check` and the focused Django test module; frontend: `npm run lint`, focused test, and `npm run build`. Run only commands applicable to changed code and report exact outcomes.

Test steps / expected result: Diagrams match implemented code. Success means the target is present, tests pass, and failure behavior is understandable.

Common errors: If the DB is unavailable, verify PostgreSQL service, database name, credentials, and env loading. If imports/routes fail, check app registration and URL inclusion. If an API/UI mismatch appears, compare against docs/api-contract.md and correct the contract or implementation deliberately; do not patch around it.

Git milestone: After review and passing tests, commit only this task. Suggested: `git add <reviewed-files> && git commit -m "DOC-01: write system architecture and data-flow documentation"`. Use a feature branch only when it helps isolate a risky/long feature; no empty commits.

Viva questions: 1. What requirement does DOC-01 satisfy? 2. Which data/API/UI boundary does it change? 3. How is invalid or unauthorized input handled? 4. What test proves it works? 5. What limitation remains?

Definition of Done: ☐ Scope met  ☐ Code understood  ☐ Focused tests pass  ☐ No unrelated changes  ☐ Evidence recorded  ☐ Commit created  ☐ Docs updated if affected  ☐ Viva explanation ready

## DOC-02 — Write API, database, and business-rule documentation

Proposal lead / workstream assignment: Monira Islam — follows the proposal split; this is a planned role, not a contribution record.

Hands-on operator: Monira Islam (you) — you will carry out every task, including tasks assigned to the frontend/UI workstream.

Requirement: Backend behavior needs stable handoff and viva references.

Target: API schemas, entity fields, calculations, order rules, and limitations are documented.

Why this task matters: API schemas, entity fields, calculations, order rules, and limitations are documented. It isolates one change so the student can inspect, test, and explain it before moving on.

Prerequisites: DOC-01

Concepts to understand: Technical writing; schema traceability.

Expected files/modules: docs/api; data dictionary; metric docs.

Implementation scope: No undocumented endpoint contract.

Not in this task: Other modules, unrelated refactors, new dependencies, and unapproved features.

Ready-to-paste Codex prompt

You are implementing SellerOS, the SE-331 standalone social-commerce seller BI/decision-support capstone. Implement only DOC-02 — Write API, database, and business-rule documentation. Requirement: Backend behavior needs stable handoff and viva references. Objective/acceptance target: API schemas, entity fields, calculations, order rules, and limitations are documented. Scope allowed: No undocumented endpoint contract. Likely files/modules: docs/api; data dictionary; metric docs. Prerequisites: DOC-01. Constraints: follow the approved React/Vite/TypeScript + Django/DRF + PostgreSQL architecture and existing API/data contracts; inspect the repository first; preserve existing working behavior; do not invent unresolved business rules—mark [DECISION REQUIRED]; do not modify unrelated files, add unnecessary dependencies, expose secrets, bypass authentication/store permissions, fabricate AI/ML results, or create autonomous actions. Out of scope for this task: Other modules, unrelated refactors, new dependencies, and unapproved features. Test requirement: Docs match generated/verified implementation. Run the narrow relevant checks and report exact commands and outcomes. Expected output: focused implementation, meaningful tests, and concise notes on files changed, decisions, risks, and next dependency. Code quality: small readable changes, type/validation/error handling appropriate to the existing project, no duplicated business formulas, and no generated or sensitive data committed.

Expected Codex output: A focused change for DOC-02, relevant tests, a file-change summary, and exact commands/results. No unrelated implementation.

How to inspect: Review the diff for these boundaries: No undocumented endpoint contract. Confirm only expected files changed, validation/permissions match the contract, and tests exercise the requirement.

How to understand: Explain in your own words how Technical writing; schema traceability. support this task; trace one normal case and one failure case through the code.

Run commands: Use verified environment commands from SETUP-07. Typical checks: backend: `python manage.py check` and the focused Django test module; frontend: `npm run lint`, focused test, and `npm run build`. Run only commands applicable to changed code and report exact outcomes.

Test steps / expected result: Docs match generated/verified implementation. Success means the target is present, tests pass, and failure behavior is understandable.

Common errors: If the DB is unavailable, verify PostgreSQL service, database name, credentials, and env loading. If imports/routes fail, check app registration and URL inclusion. If an API/UI mismatch appears, compare against docs/api-contract.md and correct the contract or implementation deliberately; do not patch around it.

Git milestone: After review and passing tests, commit only this task. Suggested: `git add <reviewed-files> && git commit -m "DOC-02: write api, database, and business-rule documentation"`. Use a feature branch only when it helps isolate a risky/long feature; no empty commits.

Viva questions: 1. What requirement does DOC-02 satisfy? 2. Which data/API/UI boundary does it change? 3. How is invalid or unauthorized input handled? 4. What test proves it works? 5. What limitation remains?

Definition of Done: ☐ Scope met  ☐ Code understood  ☐ Focused tests pass  ☐ No unrelated changes  ☐ Evidence recorded  ☐ Commit created  ☐ Docs updated if affected  ☐ Viva explanation ready

## DOC-03 — Write setup, user, and troubleshooting guide

Proposal lead / workstream assignment: Rukaiya Akther Trisha — follows the proposal split; this is a planned role, not a contribution record.

Hands-on operator: Monira Islam (you) — you will carry out every task, including tasks assigned to the frontend/UI workstream.

Requirement: A reviewer should run the app without oral instructions.

Target: Install, login, workflows, reset, errors, and limitations are documented.

Why this task matters: Install, login, workflows, reset, errors, and limitations are documented. It isolates one change so the student can inspect, test, and explain it before moving on.

Prerequisites: DOC-02

Concepts to understand: Reproducibility; user documentation.

Expected files/modules: README; docs/user-guide.md; docs/troubleshooting.md.

Implementation scope: Use verified commands; remove placeholders.

Not in this task: Other modules, unrelated refactors, new dependencies, and unapproved features.

Ready-to-paste Codex prompt

You are implementing SellerOS, the SE-331 standalone social-commerce seller BI/decision-support capstone. Implement only DOC-03 — Write setup, user, and troubleshooting guide. Requirement: A reviewer should run the app without oral instructions. Objective/acceptance target: Install, login, workflows, reset, errors, and limitations are documented. Scope allowed: Use verified commands; remove placeholders. Likely files/modules: README; docs/user-guide.md; docs/troubleshooting.md. Prerequisites: DOC-02. Constraints: follow the approved React/Vite/TypeScript + Django/DRF + PostgreSQL architecture and existing API/data contracts; inspect the repository first; preserve existing working behavior; do not invent unresolved business rules—mark [DECISION REQUIRED]; do not modify unrelated files, add unnecessary dependencies, expose secrets, bypass authentication/store permissions, fabricate AI/ML results, or create autonomous actions. Out of scope for this task: Other modules, unrelated refactors, new dependencies, and unapproved features. Test requirement: Fresh-clone rehearsal succeeds. Run the narrow relevant checks and report exact commands and outcomes. Expected output: focused implementation, meaningful tests, and concise notes on files changed, decisions, risks, and next dependency. Code quality: small readable changes, type/validation/error handling appropriate to the existing project, no duplicated business formulas, and no generated or sensitive data committed.

Expected Codex output: A focused change for DOC-03, relevant tests, a file-change summary, and exact commands/results. No unrelated implementation.

How to inspect: Review the diff for these boundaries: Use verified commands; remove placeholders. Confirm only expected files changed, validation/permissions match the contract, and tests exercise the requirement.

How to understand: Explain in your own words how Reproducibility; user documentation. support this task; trace one normal case and one failure case through the code.

Run commands: Use verified environment commands from SETUP-07. Typical checks: backend: `python manage.py check` and the focused Django test module; frontend: `npm run lint`, focused test, and `npm run build`. Run only commands applicable to changed code and report exact outcomes.

Test steps / expected result: Fresh-clone rehearsal succeeds. Success means the target is present, tests pass, and failure behavior is understandable.

Common errors: If the DB is unavailable, verify PostgreSQL service, database name, credentials, and env loading. If imports/routes fail, check app registration and URL inclusion. If an API/UI mismatch appears, compare against docs/api-contract.md and correct the contract or implementation deliberately; do not patch around it.

Git milestone: After review and passing tests, commit only this task. Suggested: `git add <reviewed-files> && git commit -m "DOC-03: write setup, user, and troubleshooting guide"`. Use a feature branch only when it helps isolate a risky/long feature; no empty commits.

Viva questions: 1. What requirement does DOC-03 satisfy? 2. Which data/API/UI boundary does it change? 3. How is invalid or unauthorized input handled? 4. What test proves it works? 5. What limitation remains?

Definition of Done: ☐ Scope met  ☐ Code understood  ☐ Focused tests pass  ☐ No unrelated changes  ☐ Evidence recorded  ☐ Commit created  ☐ Docs updated if affected  ☐ Viva explanation ready

## DOC-04 — Prepare testing, AI evaluation, and limitation report

Proposal lead / workstream assignment: Jointly assigned to Monira Islam and Rukaiya Akther Trisha — follows the proposal split; this is a planned role, not a contribution record.

Hands-on operator: Monira Islam (you) — you will carry out every task, including tasks assigned to the frontend/UI workstream.

Requirement: Project results must distinguish measured evidence from plans.

Target: Report lists tests, metrics, data, outcomes, failures, and limitations with dates/environment.

Why this task matters: Report lists tests, metrics, data, outcomes, failures, and limitations with dates/environment. It isolates one change so the student can inspect, test, and explain it before moving on.

Prerequisites: DOC-03

Concepts to understand: Evaluation validity; reporting.

Expected files/modules: docs/evaluation/final-report.md; evidence logs.

Implementation scope: Do not fabricate results or model accuracy.

Not in this task: Other modules, unrelated refactors, new dependencies, and unapproved features.

Ready-to-paste Codex prompt

You are implementing SellerOS, the SE-331 standalone social-commerce seller BI/decision-support capstone. Implement only DOC-04 — Prepare testing, AI evaluation, and limitation report. Requirement: Project results must distinguish measured evidence from plans. Objective/acceptance target: Report lists tests, metrics, data, outcomes, failures, and limitations with dates/environment. Scope allowed: Do not fabricate results or model accuracy. Likely files/modules: docs/evaluation/final-report.md; evidence logs. Prerequisites: DOC-03. Constraints: follow the approved React/Vite/TypeScript + Django/DRF + PostgreSQL architecture and existing API/data contracts; inspect the repository first; preserve existing working behavior; do not invent unresolved business rules—mark [DECISION REQUIRED]; do not modify unrelated files, add unnecessary dependencies, expose secrets, bypass authentication/store permissions, fabricate AI/ML results, or create autonomous actions. Out of scope for this task: Other modules, unrelated refactors, new dependencies, and unapproved features. Test requirement: Every reported number has retained evidence. Run the narrow relevant checks and report exact commands and outcomes. Expected output: focused implementation, meaningful tests, and concise notes on files changed, decisions, risks, and next dependency. Code quality: small readable changes, type/validation/error handling appropriate to the existing project, no duplicated business formulas, and no generated or sensitive data committed.

Expected Codex output: A focused change for DOC-04, relevant tests, a file-change summary, and exact commands/results. No unrelated implementation.

How to inspect: Review the diff for these boundaries: Do not fabricate results or model accuracy. Confirm only expected files changed, validation/permissions match the contract, and tests exercise the requirement.

How to understand: Explain in your own words how Evaluation validity; reporting. support this task; trace one normal case and one failure case through the code.

Run commands: Use verified environment commands from SETUP-07. Typical checks: backend: `python manage.py check` and the focused Django test module; frontend: `npm run lint`, focused test, and `npm run build`. Run only commands applicable to changed code and report exact outcomes.

Test steps / expected result: Every reported number has retained evidence. Success means the target is present, tests pass, and failure behavior is understandable.

Common errors: If the DB is unavailable, verify PostgreSQL service, database name, credentials, and env loading. If imports/routes fail, check app registration and URL inclusion. If an API/UI mismatch appears, compare against docs/api-contract.md and correct the contract or implementation deliberately; do not patch around it.

Git milestone: After review and passing tests, commit only this task. Suggested: `git add <reviewed-files> && git commit -m "DOC-04: prepare testing, ai evaluation, and limitation report"`. Use a feature branch only when it helps isolate a risky/long feature; no empty commits.

Viva questions: 1. What requirement does DOC-04 satisfy? 2. Which data/API/UI boundary does it change? 3. How is invalid or unauthorized input handled? 4. What test proves it works? 5. What limitation remains?

Definition of Done: ☐ Scope met  ☐ Code understood  ☐ Focused tests pass  ☐ No unrelated changes  ☐ Evidence recorded  ☐ Commit created  ☐ Docs updated if affected  ☐ Viva explanation ready

## DOC-05 — Prepare demo script, screenshots, and reset procedure

Proposal lead / workstream assignment: Jointly assigned to Monira Islam and Rukaiya Akther Trisha — follows the proposal split; this is a planned role, not a contribution record.

Hands-on operator: Monira Islam (you) — you will carry out every task, including tasks assigned to the frontend/UI workstream.

Requirement: Capstone demonstration needs a reliable story and state.

Target: Script demonstrates the central data-to-insight value, safety boundary, and limitations.

Why this task matters: Script demonstrates the central data-to-insight value, safety boundary, and limitations. It isolates one change so the student can inspect, test, and explain it before moving on.

Prerequisites: DOC-04

Concepts to understand: Demonstration design; evidence.

Expected files/modules: docs/demo-script.md; screenshots; reset command.

Implementation scope: No staged fake result presented as live.

Not in this task: Other modules, unrelated refactors, new dependencies, and unapproved features.

Ready-to-paste Codex prompt

You are implementing SellerOS, the SE-331 standalone social-commerce seller BI/decision-support capstone. Implement only DOC-05 — Prepare demo script, screenshots, and reset procedure. Requirement: Capstone demonstration needs a reliable story and state. Objective/acceptance target: Script demonstrates the central data-to-insight value, safety boundary, and limitations. Scope allowed: No staged fake result presented as live. Likely files/modules: docs/demo-script.md; screenshots; reset command. Prerequisites: DOC-04. Constraints: follow the approved React/Vite/TypeScript + Django/DRF + PostgreSQL architecture and existing API/data contracts; inspect the repository first; preserve existing working behavior; do not invent unresolved business rules—mark [DECISION REQUIRED]; do not modify unrelated files, add unnecessary dependencies, expose secrets, bypass authentication/store permissions, fabricate AI/ML results, or create autonomous actions. Out of scope for this task: Other modules, unrelated refactors, new dependencies, and unapproved features. Test requirement: Two rehearsal runs complete within allotted time. Run the narrow relevant checks and report exact commands and outcomes. Expected output: focused implementation, meaningful tests, and concise notes on files changed, decisions, risks, and next dependency. Code quality: small readable changes, type/validation/error handling appropriate to the existing project, no duplicated business formulas, and no generated or sensitive data committed.

Expected Codex output: A focused change for DOC-05, relevant tests, a file-change summary, and exact commands/results. No unrelated implementation.

How to inspect: Review the diff for these boundaries: No staged fake result presented as live. Confirm only expected files changed, validation/permissions match the contract, and tests exercise the requirement.

How to understand: Explain in your own words how Demonstration design; evidence. support this task; trace one normal case and one failure case through the code.

Run commands: Use verified environment commands from SETUP-07. Typical checks: backend: `python manage.py check` and the focused Django test module; frontend: `npm run lint`, focused test, and `npm run build`. Run only commands applicable to changed code and report exact outcomes.

Test steps / expected result: Two rehearsal runs complete within allotted time. Success means the target is present, tests pass, and failure behavior is understandable.

Common errors: If the DB is unavailable, verify PostgreSQL service, database name, credentials, and env loading. If imports/routes fail, check app registration and URL inclusion. If an API/UI mismatch appears, compare against docs/api-contract.md and correct the contract or implementation deliberately; do not patch around it.

Git milestone: After review and passing tests, commit only this task. Suggested: `git add <reviewed-files> && git commit -m "DOC-05: prepare demo script, screenshots, and reset procedure"`. Use a feature branch only when it helps isolate a risky/long feature; no empty commits.

Viva questions: 1. What requirement does DOC-05 satisfy? 2. Which data/API/UI boundary does it change? 3. How is invalid or unauthorized input handled? 4. What test proves it works? 5. What limitation remains?

Definition of Done: ☐ Scope met  ☐ Code understood  ☐ Focused tests pass  ☐ No unrelated changes  ☐ Evidence recorded  ☐ Commit created  ☐ Docs updated if affected  ☐ Viva explanation ready

## VIVA-01 — Build module-by-module viva question bank

Proposal lead / workstream assignment: Jointly assigned to Monira Islam and Rukaiya Akther Trisha — follows the proposal split; this is a planned role, not a contribution record.

Hands-on operator: Monira Islam (you) — you will carry out every task, including tasks assigned to the frontend/UI workstream.

Requirement: Both members must explain code, tests, API, and limitations.

Target: Question bank covers architecture, database, security, AI/ML, evaluation, and tradeoffs.

Why this task matters: Question bank covers architecture, database, security, AI/ML, evaluation, and tradeoffs. It isolates one change so the student can inspect, test, and explain it before moving on.

Prerequisites: DOC-05

Concepts to understand: Concept explanation; engineering tradeoffs.

Expected files/modules: docs/viva/questions.md; answer notes.

Implementation scope: Answers must align with implemented evidence and actual contributions.

Not in this task: Other modules, unrelated refactors, new dependencies, and unapproved features.

Ready-to-paste Codex prompt

You are implementing SellerOS, the SE-331 standalone social-commerce seller BI/decision-support capstone. Implement only VIVA-01 — Build module-by-module viva question bank. Requirement: Both members must explain code, tests, API, and limitations. Objective/acceptance target: Question bank covers architecture, database, security, AI/ML, evaluation, and tradeoffs. Scope allowed: Answers must align with implemented evidence and actual contributions. Likely files/modules: docs/viva/questions.md; answer notes. Prerequisites: DOC-05. Constraints: follow the approved React/Vite/TypeScript + Django/DRF + PostgreSQL architecture and existing API/data contracts; inspect the repository first; preserve existing working behavior; do not invent unresolved business rules—mark [DECISION REQUIRED]; do not modify unrelated files, add unnecessary dependencies, expose secrets, bypass authentication/store permissions, fabricate AI/ML results, or create autonomous actions. Out of scope for this task: Other modules, unrelated refactors, new dependencies, and unapproved features. Test requirement: Each member can answer and trace evidence. Run the narrow relevant checks and report exact commands and outcomes. Expected output: focused implementation, meaningful tests, and concise notes on files changed, decisions, risks, and next dependency. Code quality: small readable changes, type/validation/error handling appropriate to the existing project, no duplicated business formulas, and no generated or sensitive data committed.

Expected Codex output: A focused change for VIVA-01, relevant tests, a file-change summary, and exact commands/results. No unrelated implementation.

How to inspect: Review the diff for these boundaries: Answers must align with implemented evidence and actual contributions. Confirm only expected files changed, validation/permissions match the contract, and tests exercise the requirement.

How to understand: Explain in your own words how Concept explanation; engineering tradeoffs. support this task; trace one normal case and one failure case through the code.

Run commands: Use verified environment commands from SETUP-07. Typical checks: backend: `python manage.py check` and the focused Django test module; frontend: `npm run lint`, focused test, and `npm run build`. Run only commands applicable to changed code and report exact outcomes.

Test steps / expected result: Each member can answer and trace evidence. Success means the target is present, tests pass, and failure behavior is understandable.

Common errors: If the DB is unavailable, verify PostgreSQL service, database name, credentials, and env loading. If imports/routes fail, check app registration and URL inclusion. If an API/UI mismatch appears, compare against docs/api-contract.md and correct the contract or implementation deliberately; do not patch around it.

Git milestone: After review and passing tests, commit only this task. Suggested: `git add <reviewed-files> && git commit -m "VIVA-01: build module-by-module viva question bank"`. Use a feature branch only when it helps isolate a risky/long feature; no empty commits.

Viva questions: 1. What requirement does VIVA-01 satisfy? 2. Which data/API/UI boundary does it change? 3. How is invalid or unauthorized input handled? 4. What test proves it works? 5. What limitation remains?

Definition of Done: ☐ Scope met  ☐ Code understood  ☐ Focused tests pass  ☐ No unrelated changes  ☐ Evidence recorded  ☐ Commit created  ☐ Docs updated if affected  ☐ Viva explanation ready

## VIVA-02 — Conduct mock viva and close understanding gaps

Proposal lead / workstream assignment: Jointly assigned to Monira Islam and Rukaiya Akther Trisha — follows the proposal split; this is a planned role, not a contribution record.

Hands-on operator: Monira Islam (you) — you will carry out every task, including tasks assigned to the frontend/UI workstream.

Requirement: Implementation is complete only when the team can explain it.

Target: Mock session log records difficult questions and remediation tasks.

Why this task matters: Mock session log records difficult questions and remediation tasks. It isolates one change so the student can inspect, test, and explain it before moving on.

Prerequisites: VIVA-01

Concepts to understand: Technical communication; reflective review.

Expected files/modules: docs/viva/rehearsal-log.md.

Implementation scope: Do not claim a member implemented work they did not do.

Not in this task: Other modules, unrelated refactors, new dependencies, and unapproved features.

Ready-to-paste Codex prompt

You are implementing SellerOS, the SE-331 standalone social-commerce seller BI/decision-support capstone. Implement only VIVA-02 — Conduct mock viva and close understanding gaps. Requirement: Implementation is complete only when the team can explain it. Objective/acceptance target: Mock session log records difficult questions and remediation tasks. Scope allowed: Do not claim a member implemented work they did not do. Likely files/modules: docs/viva/rehearsal-log.md. Prerequisites: VIVA-01. Constraints: follow the approved React/Vite/TypeScript + Django/DRF + PostgreSQL architecture and existing API/data contracts; inspect the repository first; preserve existing working behavior; do not invent unresolved business rules—mark [DECISION REQUIRED]; do not modify unrelated files, add unnecessary dependencies, expose secrets, bypass authentication/store permissions, fabricate AI/ML results, or create autonomous actions. Out of scope for this task: Other modules, unrelated refactors, new dependencies, and unapproved features. Test requirement: Both can explain end-to-end system and limitations. Run the narrow relevant checks and report exact commands and outcomes. Expected output: focused implementation, meaningful tests, and concise notes on files changed, decisions, risks, and next dependency. Code quality: small readable changes, type/validation/error handling appropriate to the existing project, no duplicated business formulas, and no generated or sensitive data committed.

Expected Codex output: A focused change for VIVA-02, relevant tests, a file-change summary, and exact commands/results. No unrelated implementation.

How to inspect: Review the diff for these boundaries: Do not claim a member implemented work they did not do. Confirm only expected files changed, validation/permissions match the contract, and tests exercise the requirement.

How to understand: Explain in your own words how Technical communication; reflective review. support this task; trace one normal case and one failure case through the code.

Run commands: Use verified environment commands from SETUP-07. Typical checks: backend: `python manage.py check` and the focused Django test module; frontend: `npm run lint`, focused test, and `npm run build`. Run only commands applicable to changed code and report exact outcomes.

Test steps / expected result: Both can explain end-to-end system and limitations. Success means the target is present, tests pass, and failure behavior is understandable.

Common errors: If the DB is unavailable, verify PostgreSQL service, database name, credentials, and env loading. If imports/routes fail, check app registration and URL inclusion. If an API/UI mismatch appears, compare against docs/api-contract.md and correct the contract or implementation deliberately; do not patch around it.

Git milestone: After review and passing tests, commit only this task. Suggested: `git add <reviewed-files> && git commit -m "VIVA-02: conduct mock viva and close understanding gaps"`. Use a feature branch only when it helps isolate a risky/long feature; no empty commits.

Viva questions: 1. What requirement does VIVA-02 satisfy? 2. Which data/API/UI boundary does it change? 3. How is invalid or unauthorized input handled? 4. What test proves it works? 5. What limitation remains?

Definition of Done: ☐ Scope met  ☐ Code understood  ☐ Focused tests pass  ☐ No unrelated changes  ☐ Evidence recorded  ☐ Commit created  ☐ Docs updated if affected  ☐ Viva explanation ready

## VIVA-03 — Freeze final release, evidence, and contribution record

Proposal lead / workstream assignment: Jointly assigned to Monira Islam and Rukaiya Akther Trisha — follows the proposal split; this is a planned role, not a contribution record.

Hands-on operator: Monira Islam (you) — you will carry out every task, including tasks assigned to the frontend/UI workstream.

Requirement: Final submission must match repository and truthful work history.

Target: Tagged release, final regression, report/demo assets, and contribution summary are complete.

Why this task matters: Tagged release, final regression, report/demo assets, and contribution summary are complete. It isolates one change so the student can inspect, test, and explain it before moving on.

Prerequisites: VIVA-02

Concepts to understand: Release management; academic integrity.

Expected files/modules: Git tag; docs/release; contribution record.

Implementation scope: Report actual contributions; never infer credit from planned owners.

Not in this task: Other modules, unrelated refactors, new dependencies, and unapproved features.

Ready-to-paste Codex prompt

You are implementing SellerOS, the SE-331 standalone social-commerce seller BI/decision-support capstone. Implement only VIVA-03 — Freeze final release, evidence, and contribution record. Requirement: Final submission must match repository and truthful work history. Objective/acceptance target: Tagged release, final regression, report/demo assets, and contribution summary are complete. Scope allowed: Report actual contributions; never infer credit from planned owners. Likely files/modules: Git tag; docs/release; contribution record. Prerequisites: VIVA-02. Constraints: follow the approved React/Vite/TypeScript + Django/DRF + PostgreSQL architecture and existing API/data contracts; inspect the repository first; preserve existing working behavior; do not invent unresolved business rules—mark [DECISION REQUIRED]; do not modify unrelated files, add unnecessary dependencies, expose secrets, bypass authentication/store permissions, fabricate AI/ML results, or create autonomous actions. Out of scope for this task: Other modules, unrelated refactors, new dependencies, and unapproved features. Test requirement: Final checkpoint and artifact list approved. Run the narrow relevant checks and report exact commands and outcomes. Expected output: focused implementation, meaningful tests, and concise notes on files changed, decisions, risks, and next dependency. Code quality: small readable changes, type/validation/error handling appropriate to the existing project, no duplicated business formulas, and no generated or sensitive data committed.

Expected Codex output: A focused change for VIVA-03, relevant tests, a file-change summary, and exact commands/results. No unrelated implementation.

How to inspect: Review the diff for these boundaries: Report actual contributions; never infer credit from planned owners. Confirm only expected files changed, validation/permissions match the contract, and tests exercise the requirement.

How to understand: Explain in your own words how Release management; academic integrity. support this task; trace one normal case and one failure case through the code.

Run commands: Use verified environment commands from SETUP-07. Typical checks: backend: `python manage.py check` and the focused Django test module; frontend: `npm run lint`, focused test, and `npm run build`. Run only commands applicable to changed code and report exact outcomes.

Test steps / expected result: Final checkpoint and artifact list approved. Success means the target is present, tests pass, and failure behavior is understandable.

Common errors: If the DB is unavailable, verify PostgreSQL service, database name, credentials, and env loading. If imports/routes fail, check app registration and URL inclusion. If an API/UI mismatch appears, compare against docs/api-contract.md and correct the contract or implementation deliberately; do not patch around it.

Git milestone: After review and passing tests, commit only this task. Suggested: `git add <reviewed-files> && git commit -m "VIVA-03: freeze final release, evidence, and contribution record"`. Use a feature branch only when it helps isolate a risky/long feature; no empty commits.

Viva questions: 1. What requirement does VIVA-03 satisfy? 2. Which data/API/UI boundary does it change? 3. How is invalid or unauthorized input handled? 4. What test proves it works? 5. What limitation remains?

Definition of Done: ☐ Scope met  ☐ Code understood  ☐ Focused tests pass  ☐ No unrelated changes  ☐ Evidence recorded  ☐ Commit created  ☐ Docs updated if affected  ☐ Viva explanation ready

# 9. Responsibility Matrix

This matrix follows the proposal’s workstream split and separately identifies who will perform each task. Monira will carry out all hands-on work at the student’s request, including Trisha-led frontend/UI tasks. Planned proposal leads do not establish who actually contributed; record only completed work and review.

| Work area | Task IDs | Proposal lead | Hands-on operator | Contribution record |
| --- | --- | --- | --- | --- |
| Planning and decisions | PLAN-01–06 | Joint | Monira (you) | Record actual participation |
| Repository/backend/database/auth | SETUP-01–04, BACKEND-01–05, DB-01–05, AUTH-01–04 | Monira | Monira (you) | Record actual participation |
| Frontend and UX | SETUP-05, FRONTEND-01–03, feature UI tasks | Rukaiya | Monira (you) | Record actual participation |
| Operational records | PRODUCT, INV, CUSTOMER, ORDER, EXP | Monira API / Rukaiya UI | Monira (you) | Record actual participation |
| Analytics, profit, dashboard | ANALYTICS, PROFIT, DASH | Monira calculations/API / Rukaiya UI | Monira (you) | Record actual participation |
| AI/ML features | ASSISTANT, ADVISOR, SEGMENT, FORECAST, SIM | Monira services / Rukaiya UI | Monira (you) | Record actual participation |
| Testing, release, documentation, viva | INTEGRATION, TEST, SECURITY, DEPLOY, DOC, VIVA | Joint | Monira (you) | Record actual participation |

# 10. Project Checkpoints

CHECKPOINT-01 — Project skeleton runs. Gate: SETUP-01–07; BACKEND-01–05; FRONTEND-01–03.

CHECKPOINT-02 — Authentication and store isolation work. Gate: DB-01–05; AUTH-01–06.

CHECKPOINT-03 — Core catalogue and stock records work. Gate: DATA-01–04; PRODUCT-01–07; INV-01–06.

CHECKPOINT-04 — Customer and order flow works. Gate: CUSTOMER-01–05; ORDER-01–08; EXPENSE-01–04.

CHECKPOINT-05 — Dashboard and profit calculations verified. Gate: ANALYTICS-01–05; PROFIT-01–06; DASH-01–04.

CHECKPOINT-06 — Assistant returns grounded drafts only. Gate: ASSISTANT-01–08.

CHECKPOINT-07 — Advisor uses verified metrics. Gate: ADVISOR-01–05.

CHECKPOINT-08 — Behavior segmentation is interpretable. Gate: SEGMENT-01–05.

CHECKPOINT-09 — Forecast is evaluated or reports insufficient data. Gate: FORECAST-01–10.

CHECKPOINT-10 — What-if simulator shows estimate and assumptions. Gate: SIM-01–06.

CHECKPOINT-11 — Full end-to-end workflow passes. Gate: INTEGRATION-01–05; TEST-01–05.

CHECKPOINT-12 — Release/demo build and evidence are complete. Gate: TEST-06–07; DEPLOY-01–03; DOC-01–05; VIVA-01–03.

# 11. Progress Tracker Rules

Allowed states: NOT STARTED, READY, IN PROGRESS, BLOCKED, TESTING, COMPLETED. Set READY only when all prerequisites pass. Set BLOCKED with the missing decision/dependency and owner. Set COMPLETED only after the DoD, tests, evidence, and commit are recorded. “Tested” means a named command or manual test was actually run; the commit column records the actual SHA or commit subject.

# 12. Git and Change-Control Rules

Keep one logical task per commit whenever practical. Use a branch for a feature that spans multiple dependent tasks or risks destabilizing main; avoid one branch per trivial edit.

Before asking Codex, state task ID, current branch/status, prerequisite commits, and exact scope. After Codex responds, inspect `git diff --stat` and the full diff before running tests.

Never commit `.env`, provider keys, real customer data, generated database files, model binaries without an approved need, or unreviewed artifacts.

When a schema or API contract changes, update the data dictionary/API docs and add a migration/contract test in the same task where appropriate.

Do not merge a failing task. Revert or repair with a narrow follow-up task and preserve the test evidence.

# 13. Alignment with the Proposal Timeline

The proposal’s 11-week course schedule remains the high-level calendar. This plan expands it into controlled tasks; exact dates depend on the course calendar and approved decisions. Keep the ordering below, and move a feature later rather than compressing its dependency checks.

Week 1: PLAN, SETUP, BACKEND/FRONTEND foundations, ERD/API contracts, initial migrations.

Week 2: Authentication, store isolation, product and inventory core.

Week 3: Customer, order, expense workflows and synthetic data.

Week 4: Sales aggregation, dashboard foundation, AI assistant specification/retrieval.

Week 5: Profit intelligence and business advisor.

Week 6: Customer segmentation.

Week 7: Demand forecast audit, baseline, evaluation; report insufficient data if needed.

Week 8: What-if simulator with approved assumptions.

Week 9: Complete six features, integrate, fix cross-module defects.

Week 10: Security, usability, performance, regression, docs, deployment readiness.

Week 11: Release rehearsal, demo, presentation, viva, final contribution/evidence record.

# 14. Start Gate

This deliverable is the full planning response only. No implementation task or Phase 1 work has started. After reviewing and approving the plan, the user can explicitly say START TASK SETUP-01. Before any code change, verify that required PLAN decisions and the repository audit are recorded; if a prerequisite is missing, resolve it first.

The exact next step remains under the user’s control; no first-task instruction is issued here.